Non-Emergency Patient Transport Services

Delivery Assurance Group

(NEPTS DAG)

# Minutes/Action(s)

Friday 7 February 2020

10:00am to 12:00pm

Venue: NCCU, 1 Charnwood Court, Nantgarw, CF15 7QZ

# Attendees:

| # James Rodaway – NCCU (JR) (Chair) | # Nicola Bowen - WAST (NB) |
| --- | --- |
| # Jonathan Jones – NCCU (JDJ) | # Sharon Brown – WAST (SB) |
| # Andrew Quarrell - PTHB (AQ) | # Jeff O’Sullivan – Velindre (JoS) |
| # Joanne Jones - SBUHB (JJ) | # Melanie Wilkey – CVUHB (MW) |
| # Phill Taylor – WAST (PT) | # Mark Harris - WAST (MH) |
| # Aaron Evans - WAST (AE) | # Beth Roberts – WAST (BR) |
| # James Haley – WAST (JH) | # Karl Hughes – WAST (KH) |
| # Jo Williams – WAST (JW) | # Wayne Lewis – CTMUHB (WL) |
| # Julie Keegan – CTMUHB (JK) | # Olivia Barnes – WAST (OB) |
| # Leanne Hawker – WAST (LH) | # Katie Jones – NCCU (KJ) |
| # Andrew Walsh – ABUHB (AW) |  |
| # Via Video Conferencing |  |
| # Susan Spence – WHSSC (SS) | # Anita Owen – WAST (AO) |

# Apologies Received:

| # Doug Robb – WAST (DR) | # Colin McMillian – CVUHB (CM) |
| --- | --- |
| # Lyndon Powell - WAST (LP) | # Deb Kingsbury – WAST (DK) |
| # Debra Fry – NCCU (DF) |  |

Acronyms:

| # ABUHB | # Aneurin Bevan University Health Board |
| --- | --- |
| # CHC | # Community Health Council |
| # CTMUHB | # Cwm Taf Morgannwg University Health Board |
| # CVUHB | # Cardiff and Vale University Health Board |
| # EMS | # Emergency medical services |
| # HCP | # Health care professional |
| # NEPTS DAG | # Non-emergency patient transport service Delivery and Assurance Group |
| # NCCU | # National Collaborative Commissioning Unit |
| # PECI | # Patient engagement and community involvement |
| # PTHB | # Powys Teaching Health Board |
| # SBUHB | # Swansea Bay University Health Board |
| # WAST | # Welsh Ambulance Services NHS Trust |
| # WHSSC | # Welsh Health Specialised Services Committee |
| # WTE | # Whole time equivalent |

| # Item | Agenda | # Actions / Comments | # Further comments | # Attachments |
| --- | --- | --- | --- | --- |
| # 1. | Welcome, Introductions & Apologies # James Rodaway (Chair) welcomed all to the meeting and all present introduced themselves. |  |  |  |
| # Action Notes of last meeting |  |  |  |  |
| # 2. | Accuracy and progress against action notes | - Minutes confirmed as accurate (Attachment: Item 1) [JJ 7.2.20] |  | # Item 1: |
| # Patient Experience |  |  |  |  |
| # 3. | WAST Patient Experience across the 5 Steps | - NEPTS DAG Members welcomed Leanne Hawker to the meeting. LH discussed the proposed model (Attachment: Item 2) for capturing patient experience using the National Framework for Assuring Service Users Experience (2018). Currently undertaken for EMS across the 5 steps framework so would be looking to follow the same approach for NEPTS. ACTION: LH to share 5 steps model for EMS with DAG members - Previously used ‘Happy or Not’ however the data did not provide enough clarity. The ambition is to set in ‘real time’ and use the data to drill down to the real issues in order to get true value. - MH to work with LH & PECI Team to work through details and provide DAG members with regular feedback through reporting mechanisms via DAG. ACTION: MH & LH to provide update at the next DAG - Patient Questionnaire to go live in March 2020 ACTION: LH to share draft survey ahead of go live date in March. | # 5 Step Model for EMS included (Attachment: Item 3) [JJ 13.2.20] | # Item 2: # Item 3: |
| # NEPTS Quality & Delivery Framework |  |  |  |  |
| 4. | - 1% A Healthier Wales Transport Solutions # - Progress to date b) Commissioning Intentions Reporting & Management - Progress to date (to include joint performance) | - Good progress being made with Transport Solutions: - Dedicated Work streams in place (Pre-contact, Contact, Analysis & Review, Alternative Provision) all with a clear audit trail and robust reporting mechanisms. ACTION: Summary of Workstreams to be sent to DAG members - Regular updates to be provided to DAG members and EASC Joint Committee. ACTION: JR to update EASC Joint Committee in March 2020 on current progress and request clarification from all Chief Executives as to the ‘needs’ from each Health Board. - Internal Steering Group set up. ACTION: Health Board representatives are invited to join the Steering group. Please email Sharon Brown if you wish to join: (Sharon.Brown4@wales.nhs.uk) - Group 1 looking at the key messages and developing communication plan. ACTION: OB & MH to share Communication & Engagement plan and key messages at the next DAG (March’20) - The Future Model will be rolled out to deliver Welsh Health Circular in full and to deliver improvements in line with Commissioning Intentions 2019/20. This will involve direct engagement with Welsh Government, CHC, and Executive Boards etc. - Overall aim to introduce a pan wales approach as each Health Board works slightly different. This will be in line with the NEPTS Business Case - Risk & Impact assessments will be undertaken and form part of the Internal Steering Group. - MH gave update on progress with Group 2 (Attachment: Item 5). Patient Passport Scheme is being rolled out to establish eligibility and to improve booking processes. The new process will be rolled out in two phases: - Phase 1 – Direct patient contact - Phase 2 – HCP Contact - Concerns were raised by DAG members regarding: - Terminology of ‘passport’ as a number of provisions are already in place within Health Boards using this terminology. ACTION: MH & AO to change terminology for Passport Scheme - Avoiding duplication of work & not to be a repetitive process for patients accessing the scheme. ACTION: MH to provide clarity at next DAG around new process taking on board comments raised. - Through the DAG, it will ensure that all Health Boards are kept informed on progress updates, and it will be an open and transparent process as we move towards a dedicated Transfer & Discharge Service. Being able to model the benefits will provide assurance to front line staff and drive forward service improvements. - Internal working groups set up and in progress. - Reduce on the day cancellations - Reduce on the day aborts - Reduce on the day bookings # ACTION: Highlight reports to be presented at next DAG | # Work stream summary enclosed (Attachment: Item 4) [JJ 13.02.20] # Joanne Jones (SBUHB) has offered to join the steering group. Other HB representatives also welcome [JJ 13.02.20] | # Item 4: # Item 5: |
| # Qliksense |  |  |  |  |
| 5. | # Qliksense Demonstration | - Qliksense data was well received and DAG members thanked AE & BR for the demonstrations. All members agreed to utilise the data at Tier 2 & 3 meetings to identify where we can work together to reduce failed discharges, aborts & cancellations. - Important to feedback to EASC joint committee and include the data in summary reports. ACTION: JR to link with AE to develop Performance report for EASC. - JJ suggested it would be beneficial (especially for Tier 3 meetings) for Operational Managers to provide regular reports / handouts for the meeting to drill down to specific problem areas. ACTION: AE to speak to operational colleagues to draft reports/handouts for each meeting. ACTION: AE to share example of reports used in Hywel Dda - New Performance Measures Framework report agreed with WAST Management Group. ACTION: MH to roll out to all Tier 3 meetings and share with DAG members | # Example reports used in Hywel Dda (Attachment: Item 6) | # Item 6: |
| # Tier 2 & 3 Meetings |  |  |  |  |
| # 6. | Health Board current and future plan | - NB thanked DAG members for providing up to date lists of Tier 2 & 3 meetings held within their respective areas (Attachment: Item 7) as these meetings are needed in order to support the delivery of the joint work within the Commissioning Intentions. ACTION: Health Board representatives are asked to contact their Local Operational Managers and develop an action plan & schedule meetings for the next 12 months. Once confirmed please forward to Jonathan.Jones6@wales.nhs.uk |  | # Item 7: |
| # Transfer of Work |  |  |  |  |
| # 7. | # Update on current progress | - Overall aim to improve confidence in the system and identify fears and anxieties. Benefits realisation captured on Air table and updated as transfers are completed. For the Health Boards that have transferred across, positive feedback received to date with no issues reported. # Aneurin Bevan updates: - ‘Go Live’ date of 1st April. Currently liaising with finance teams over WTE figures but positive progress made to date. # Cwm Taf Morgannwg updates: - Currently awaiting Princess of Wales data. ACTION – WL & JK to support # Powys updates: - ‘Go Live’ date of 1st April. Currently liaising with finance teams over what the final figure for in & out of scope. Transfer documents & communication plan produced to show complete transparency. Positive progress made to date. # Betsi updates: - No further progress updates to date. Further discussions to take place. - NB wanted to thank DAG members for the level of support they, and their teams, have throughout the whole Transfer of Work process. - At the last DAG (December’19) members were made aware of an External Audit being undertaken by Shared Services around the Transfer of Work. All documentation has been submitted and currently awaiting feedback. |  |  |
| # Radiopharmaceuticals |  |  |  |  |
| 8. | New procedure for booking & transporting patients from 1 April | - Proposed changes for a new procedure for booking and transporting patients who may have received nuclear meds will be in place from April 1st. Documentation (Attachment: Item 8) ACTION: Health Board representatives to share with Health Board Contacts and Leads. - Supported by Julian McDonald, the proposed changes are evidence based, and all risk assessments etc. have been undertaken. Health Board colleagues should already be aware of the changes following discussions with medical colleagues, welsh government etc. - 700,000 patients conveyed in the last 12 months – additional 100,000 journeys were aborted (Attachment: Item 9). Majority ‘C6 Patients’ - Concerns were raised by DAG members of stopping the ‘Wait & Return’ process without having a transition plan in place. Request were made to urgently look into clinic hot spots and wish for further joint discussions to take place before changes are made. # ACTION: KH to provide report on all Health Boards ‘Hot Spots’ by end of February to support. # ACTION: KH & MH to liaise with Health Boards to take forward | # To become standard agenda item [JJ 14/2/20] | Item 8 Item 9 |
| # AOB |  |  |  |  |
| 7. | a) NEPTS D&C Steering Group b) NEPTS Directorate Change c) Travel Options within Cwm Taf Morgannwg d) Nicola Bowen | - OHR has been appointed to lead the NEPTS Demand & Capacity Review. Requests for Health Board representative to join the Steering Group. ACTION: Health Board representatives are invited to join the Steering group. Please email Mark Harris / Kerri Hitchings for further information (Mark.Harris5@wales.nhs.uk / Kerri.Hitchings3@wales.nhs.uk) - Proposed changes to the NEPTS Division (discussed at the last DAG) went live from 2nd February 2020. DAG members were ensured that the changes will not have any impact on delivery. The changes involve bringing the NEPTS and EMS side of the business under the Operations Division, however both EMS and NEPTS will remain separate functions within WAST as per recommendations from McClelland Review (2013) - WL discussed current plans in pilot process being drawn up within CTMUHB and Merthyr Local Authority of joint working with local authorities improving transport and travel. AW also discussed similar plans in place within ABUHB to look at alternative transports. Further updates to provided once more detail is received. - Nicola Bowen will be leaving her current role end of February 2020 for a secondment with the NCCU. DAG members wish to express their sincere thanks for all the help and support from Nicola and wish her well in this new role. |  |  |