## Slide 1
2023-24
Qtr 1
Qtr 3
Qtr 4
2024-25
Qtr 1
Qtr 2
2022-23
Qtr 1
EASC Commissioning Cycle
2022-2025
Qtr 2
Qtr 3
Qtr 4
Qtr 2
Qtr 3
Qtr 4
Revise NEPTS framework
Issue revised NEPTS framework
Refresh NEPTS framework
Revise EMRTS framework
Issue revised EMRTS framework
Refresh EMRTS framework
Quality & Delivery Framework:
Focus on one framework p.a.
Generally revise framework Qtr 4 for April issue
Ongoing monitoring and review
Commissioning Intentions:
Ongoing dialogue with HBs at each meeting of the EASCMG re emerging system change and implications for commissioned services, informing Commissioning Intentions
Inform IMTP development
EMS - Management Group (approval Aug/Oct meeting)
NEPTS - NEPTS DAG (approval Aug/Oct meeting)
EMRTS - EMRTS DAG (approval September meeting)
Approve Commissioning Intentions (24-25)
Other:
Alignment to WG planning cycle
Commissioning cycle can be revised to incorporate new areas of work
Revise EMS framework
Issue revised EMS commissioning framework
Approve Commissioning Intentions (25-26)
Approve Commissioning Intentions (23-24)
Refresh EMS framework