## Table 1a
Appendix 1 2019/20 Quarter 3 EMS Framework Improvements and Performance Improvements
| Title | Summary Description | Lead | NCCU RAG | WAST Update | WAST RAG | RAG Colour Code |  |  | Table 1a
[8 empty] | Complete/Improved | G | 7
1 | IMTP | Review of 2018/19 IMTP financial assumptions and financial plan v forecast outturn for 2018/19 and 2019/20 financial assumptions and financial plan. | Name Chris Turley Role Director of Finance & ICT Contact chris.turley@wales.nhs.uk |  | Complete. | Complete | G | Ongoing | A | 5
2 | Financial value payable | Financial value payable by EASC and associated assumptions. | Name Chris Turley Role Director of Finance & ICT Contact chris.turley@wales.nhs.uk |  | Complete. | Complete | G | Deterioration | R | 0
3 | Fleet and staff mix | Fleet and staff mix to be reviewed for each heath board area tailoring the delivery of the 5 Step Ambulance Patient Pathway to local population needs. | Name Rachel Marsh Role Director of Planning & Performance Contact rachel.marsh3@wales.nhs.uk |  | Complete via the EMS D&C Review. Implementation Programme a commissioning intention for 2020/21. | Complete | G | Development | - | 0
4 | Operational arrangements to be reviewed by EASC on an ongoing basis. | NCCU and WAST to specifically work on a work programme that feeds into JMAG/PDEG/EASC and the EASC/WAST Performance Meeting. | Name Julian Baker Role National Director of Collaborative Commissioning Contact julian.baker@wales.nhs.uk |  | JMAG/PDEG replaced by EASC Management Group. No work programme document, but collaboration on Amber Review, EMS D&C, NEPTS D&C, Red Improvement Plan, Discharge & Transfer, Winter Plan and Major Trauma Network. Papers provided as requested by NCCU. | Complete | G
5 | IMTP Delivery | Progress review of 2018/19 IMTP actions | Name Rachel Marsh Role Director of Planning & Performance Contact rachel.marsh3@wales.nhs.uk |  |  | Complete | G
6 | Tables 1,2 & 3 | Inclusion of completed IMTP 2019/20 tables following EASC IMTP approval. | Name Rachel Marsh Role Director of Planning & Performance Contact rachel.marsh3@wales.nhs.uk |  | Tables were completed at pace with information uploaded onto Airtable as per NCCU request. | Complete | G
7 | Data repository | Data repository covering A1 Activitiy, RE1 Resource Envelope, R1 Performance Measures, including the AQIs, to be utilised with when, who, when specificallly stated. | Name Rachel Marsh Role Director of Planning & Performance Contact rachel.marsh3@wales.nhs.uk |  | Periodic updates during 2019/20 to reflect in year changes e.g. call answering etc. | Complete | G
8 | Trigger points | Trigger points which indicate poor deteriorating performance against performance metrics within the data repository to be identified by CASC and specific actions to warrant corrective action identified. | Name Julian Baker Role National Director of Collaborative Commissioning Contact julian.baker@wales.nhs.uk |  | Trigger points not agreed; however, WAST establishing a group to review its Performance Management Framework. NCCU will be invited to attend this group. Triggers will be included in the work of this group. | Ongoing | A
9 | Core requirements | The reporting against core requirements to be undertaken twice a year as described under the Commissioning Intention for Care Standards. | Name Rachel Marsh Role Director of Planning & Performance Contact rachel.marsh3@wales.nhs.uk |  | For 2020/21 agreed to amend this intention to once a year with output being an improvement plan agreed with NCCU/WAST. Aim to complete one assessment before 31 Mar-20. | Ongoing | A
10 | Local measures | Development of local measures by health board. | Name Rachel Marsh Role Director of Planning & Performance Contact rachel.marsh3@wales.nhs.uk |  | WAST has started regularly reporting quality & performance, based on the AQIs, to health board quality & safety committees. WAST to share reports with NCCU. | Ongoing | A
11 | Call to door times | Call to door times for STEMI and stroke to be produced. | Name Chris Turley Role Director of Finance & ICT Contact chris.turley@wales.nhs.uk |  | This is dependent on incident number cleansing of PCRs. Clinical Effectiveness and Health Informatics meeting w/c 13 Jan-20 as expectation from NCCU that this data will be available alongside Q3 AQI publication. | Ongoing | A
12 | Band 6 | Development of clinical indicators which compliment the benefit realisation assumptions for Band 6 Paramedic investmet to be produced. | Name Rachel Marsh Role Director of Planning & Performance Contact rachel.marsh3@wales.nhs.uk |  | Two indicators were agreed: COPD and non-cardiac chest pain. The first is linked to the development of pathways and WAST has not been able to progress the second. Will not be achieved in 2019/20. | Ongoing | A
7
5

## Table 1b
Commissioning Intentions 1b
| Title | Summary Description | Measure | Lead |  | Current Performance | [20 empty] | WAST Update | WAST RAG | RAG Colour Code
[5 empty] | Target | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
1 | Clinical Support Desk. | Patient demographics recording to be improved to support patient identifier for linked data. | - | Name Chris Turley Role Director of Finance & ICT Contact chris.turley@wales.nhs.uk | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | This will not be delivered in 2019/20. It will be rolled forward to 2020/21, with the exact intention to be resolved between NCCU and WAST. | Ongoing | A
2 | Clinical Support Desk. | Patient demographics recording to be improved to support patient identifier for linked data. | - | Name Chris Turley Role Director of Finance & ICT Contact chris.turley@wales.nhs.uk | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | This will not be delivered in 2019/20. It will be rolled forward to 2020/21, with the exact intention to be resolved between NCCU and WAST. | Ongoing | A
3 | Clinical Support Desk | Clinical desk activity types to reflect all activity undertaken. | - | Name Chris Turley Role Director of Finance & ICT Contact chris.turley@wales.nhs.uk | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | The CCC Clinical Review has identified that the CSD is undertaking 13 activities of which 4 are hear & treat. WAST is not formally reporting this yet with the intention rolling forward to 2020/21. | Ongoing | A
4 | Resource utilisation will improve | Sickness rates reduced for all direct staff across each of the steps. | % sickness absence for staff (all staff) | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | 6.3% | 7.12% | 6.56% | 6.61% | 6.78% | 7.25% | 6.78% | 7.02% | 7.38% | 7.79% | 7.87% | 7.35% | 6.95% | 6.8% | 6.26% | 6.24% | 6.65% | 7.55% | 7.12% | 7.32% | 6.93% |  | % sickness absence for staff (all staff). | Ongoing | A
5 | Resource utilisation will improve | Overtime use to reduce. | Overtime use to reduce. | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Reduction Trend | Reduction of £56,000 |  |  | Further reduction of £148,000 |  |  | Further reduction of £54,000 |  |  | Further Reduction £157,000 |  |  | Further Reduction of £20,000 |  |  | Increase of £161,000 |  |  | - | - | - | Overtime has increased as a result of the Red Improvement Plan, which is a legitimate and targeted response to improving ambulance capacity. | Deterioration | R
6 | Resource utilisation will improve | Use of external providers to be reduced. | - | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Reduction Trend | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | No external commercial providers are currently used. St John Cymru provider of choice, but third sector not external commercial. WG has subsequently confirmed, as part of winter planning process, that WAST must not use external commercial providers. | Complete | G
7 | Resource utilisation will improve | Rosters aligned to demand (across days and time of day) for direct staff across each step. | - | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Complete Reviews | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Roster reviews for AB and CT complete. Further reviews expected via D&C Implementation Programme. | Complete | G
8 | Resource utilisation will improve | Compliance with planned (that is new) rosters to increase. | Emergency Ambulance unit hours production | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | 95% | 93% | 91% | 91% | 91% | 89% | 91% | 94% | 94% | 95% | 97% | 92% | 91% | 95% | 92% | 91% | 89% | 86% | 88% | 90% | 92% | 91% | EA UHP maintained above 90%, with one exception - Aug-19 - but not achieving 95% regularly due to relief gap. | Ongoing | A
9 | Proportion of spend | Proportion of Spend to Shift from Steps 5 & 4 to Steps 3 & 2. | - | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Increase in CSD/APP capacity | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | CSD expanded to 41 FTEs and additional 23 APPs started MSC programme; however, EMS D&C Review has identified that signficant investment will be required into Step 3 in future years. | Complete | G
10 | Reduced spend | Reduced operating expenses. | - | Name Chris Turley Role Director of Finance & ICT Contact chris.turley@wales.nhs.uk | Reduction Trend | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | This intention has been an area of dispute between NCCU and WAST in 2019/20. Work has been undertaken on weight of spend back to 2013/14. Further work now being undertaken on FTEs. | Ongoing | A
11 | "Net effect" | Known "net effect" in terms of activity impact, resource impact and performance impact from all initiatives. | - | Name Julian Baker Role National Director of Collaborative Commissioning Contact julian.baker@wales.nhs.uk | Positive "net effect" | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | WAST has produced more hours, reduced conveyance and reduced to clear lost hours; however, demand has increased, in particular, Red demand and lost hours to handover has increased signficantly, consequently performance has declined. This measure needs further refinement. Agreement with NCCU to identify "net effect" measures per initiativ for 2020/21. | Ongoing | A
12 | Allocation times | Time to allocation to Red calls to reduce. | - | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Reduction Trend | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not measured as a matter of routine, so work request made to Health Informatics to show a pre and post CAD implementation time series analysis. | Ongoing | A
13 | Clinical Support Desk | The volume of calls assessed and closed by the clinical desk to increase. | Hear & Treat Volumes (calls assessed and closed by the clinical desk) | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Improvement Trend | 2663 | 2820 | 2876 | 2942 | 2854 | 2784 | 2895 | 2937 | 3257 | 3765 | 3011 | 3130 | 3412 | 3280 | 3334 | 3463 | 3321 | 3295 | 3438 | 3630 | 4639 | Hear & Treat Volumes (calls assessed and closed by the clinical desk) | Improved | G
14 | Multiple arrivals | Multiple vehicle arrivals at scene to reduce for Amber and Green incidents. | % of incidents where 2 or more vehicles arrived on scene | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Reduction Trend | 15% | 15% | 14% | 14% | 14% | 14% | 14.9% | 15.3% | 15.8% | 15.2% | 15.6% | 15.8% | 16% | 15.5% | 15.5% | 16.3% | 16.2% | 19% | 18.2% | 19.2% | 20.6% | % of incidents where 2 or more vehicles arrived on scene (AQI 14). Deteriorated i.e. increased, as ideal resouce delayed at hospitals and need to rebalance resource mix as identified in Demand & Capacity Review. | Deterioration | R
15 | Ideal response | The percentage of incidents where the first arriving vehicle is the ideal response to incease. | % of Amber incidents where Ideal resource first on scene (note: Amber 1 used here) | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Improvement Trend | - | - | - | 72.4% | 72.8% | 72.3% | 74.6% | 72.3% | 71% | 71.3% | 71% | 70.5% | 68.1% | 69% | 67.9% | 68% | 66.8% | 66.2% | 66.6% | 65.2% | _ | % of Amber incidents where Ideal resource first on scene (note: Amber 1 used here) AQI 18. See previous point for explanation of deterioration. | Deterioration | R
16 | Red performance | Red performance to be maintained and the 95th percentile to reduce. | % of emergency response to red incidents arriving within 8 minutes |  | 65% | 75.08% | 76.08% | 75.6% | 75.42% | 74.39% | 73.89% | 74.68% | 72.3% | 72.8% | 71.8% | 72.4% | 71.2% | 70.3% | 70.2% | 72.5% | 69.3% | 69% | 68.4% | 66.3% | 60.1% | 62% | % of emergency response to red incidents arriving within 8 minutes. Significiant increase in Red demand due to change in CCC MPDS procedure and reduction in ambulance availalibility linked to handover lost hours. | Deterioration | R
|  |  | Red 95th percentile | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Reduction Trend | 0:15 | 0:14 | 0:15 | 0:16 | 0:16 | 0:15 | 0:15 | 0:16 | 0:16 | 0:15 | 0:16 | 0:16 | 0:17 | 0:16 | 0:16 | 0:17 | 0:17 | 0:17 | 0:17 | 0:18 | 0:19 | Red 95th percentile (AQI 11). See Red 8 minute performance for explanation. | Deterioration | R
|  |  | Red 95th percentile - AB |  | Reduction Trend |  |  |  | - | - | - | - | - | - | - | - | - | 0:15 | 0:15 | 0:15 | 0:16 | 0:16 | 0:17 | 0:17 | 0:17 | 0:18 | Red 95th percentile - AB. See Red 8 minute performance for explanation.
|  |  | Red 95th percentile - BCU |  | Reduction Trend |  |  |  | - | - | - | - | - | - | - | - | - | 0:17 | 0:17 | 0:19 | 0:17 | 0:17 | 0:18 | 0:18 | 0:19 | 0:22 | Red 95th percentile - BCU. See Red 8 minute performance for explanation.
|  |  | Red 95th percentile - C&V |  | Reduction Trend |  |  |  | - | - | - | - | - | - | - | - | - | 0:13 | 0:12 | 0:14 | 0:12 | 0:22 | 0:14 | 0:14 | 0:15 | 0:14 | Red 95th percentile - C&V. See Red 8 minute performance for explanation.
|  |  | Red 95th percentile - CTM |  | Reduction Trend |  |  |  | - | - | - | - | - | - | - | - | - | 0:15 | 0:15 | 0:16 | 0:16 | 0:17 | 0:16 | 0:15 | 0:16 | 0:19 | Red 95th percentile - CTM. See Red 8 minute performance for explanation.
|  |  | Red 95th percentile - CT |  | Reduction Trend | [12 empty] | - | - | - | - | - | - | - | - | - | Red 95th percentile - CT. See Red 8 minute performance for explanation.
|  |  | Red 95th percentile - HD |  | Reduction Trend |  |  |  | - | - | - | - | - | - | - | - | - | 0:17 | 0:20 | 0:19 | 0:21 | 0:19 | 0:18 | 0:20 | 0:22 | 0:22 | Red 95th percentile - HD. See Red 8 minute performance for explanation.
|  |  | Red 95th percentile - P |  | Reduction Trend |  |  |  | - | - | - | - | - | - | - | - | - | 0:20 | 0:21 | 0:20 | 0:22 | 0:24 | 0:21 | 0:24 | 0:25 | 0:25 | Red 95th percentile - P. See Red 8 minute performance for explanation. See Red 8 minute performance for explanation.
|  |  | Red 95th percentile - SB |  | Reduction Trend |  |  |  | - | - | - | - | - | - | - | - | - | 0:17 | 0:14 | 0:13 | 0:15 | 0:18 | 0:16 | 0:16 | 0:17 | 0:19 | Red 95th percentile - SB
|  |  | Red 95th percentile - ABM |  | Reduction Trend | [12 empty] | - | - | - | - | - | - | - | - | - | Red 95th percentile - ABM. See Red 8 minute performance for explanation.
17 | Amber performance | Amber 95th percentile times to reduce across each health board area. | Amber 95th percentile | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Reduction Trend | 2:22 | 2:27 | 2:32 | 2:44 | 2:40 | 2:46 | 2:33 | 2:32 | 2:42 | 2:59 | 2:47 | 2:42 | 3:07 | 2:42 | 2:52 | 3:05 | 3:26 | 3:28 | 4:04 | 4:28 | 5:48 | Amber 95th percentile All Wales (AQI12). See Red 8 minute performance for explanation. | Deterioration | R
|  |  | Amber 95th percentile - AB |  | Reduction Trend | 3:02 | 3:17 | 3:04 | 3:52 | 03:29:22 | 3:54 | 02:43:06 | 3:16 | 3:01 | 3:40 | 3:38 | 2:54 | 3:23 | 3:12 | 3:17 | 4:18 | 4:08 | 4:13 | 4:34 | 5:16 | 7:00 | Amber 95th percentile - AB. See Red 8 minute performance for explanation.
|  |  | Amber 95th percentile - BCU |  | Reduction Trend | 2:01 | 2:01 | 2:23 | 2:33 | 2:18 | 2:14 | 2:25 | 1:39 | 1:40 | 1:52 | 1:40 | 1:41 | 1:55 | 1:50 | 2:07 | 2:13 | 2:26 | 2:05 | 1:55 | 2:12 | 3:43 | Amber 95th percentile - BCU. See Red 8 minute performance for explanation.
|  |  | Amber 95th percentile - C&V |  | Reduction Trend | 3:12 | 4:05 | 3:07 | 2:31 | 3:20 | 3:13 | 3:08 | 3:22 | 4:10 | 3:29 | 3:39 | 3:01 | 2:59 | 3:09 | 3:18 | 3:28 | 4:03 | 3:47 | 5:47 | 5:14 | 5:53 | Amber 95th percentile - C&V. See Red 8 minute performance for explanation.
|  |  | Amber 95th percentile - CTM |  | Reduction Trend | - | - | - | - | - | - | - | - | - | - | - | - | 3:22 | 2:35 | 2:35 | 3:11 | 3:30 | 3:17 | 4:07 | 4:40 | 6:22 | Amber 95th percentile - CTM. See Red 8 minute performance for explanation. See Red 8 minute performance for explanation. See Red 8 minute performance for explanation.
|  |  | Amber 95th percentile - CT |  | Reduction Trend | [12 empty] | - | - | - | - | - | - | - | - | - | Amber 95th percentile - CT
|  |  | Amber 95th percentile - HD |  | Reduction Trend | 1:26 | 1:36 | 1:59 | 1:57 | 1:34 | 1:41 | 1:46 | 1:37 | 4:43 | 2:07 | 1:55 | 2:15 | 2:25 | 1:55 | 2:06 | 2:02 | 2:05 | 2:30 | 2:21 | 3:28 | 4:27 | Amber 95th percentile - HD. See Red 8 minute performance for explanation. See Red 8 minute performance for explanation.
|  |  | Amber 95th percentile - P |  | Reduction Trend | 1:35 | 1:19 | 1:30 | 1:48 | 1:30 | 1:38 | 1:44 | 1:31 | 1:43 | 1:42 | 1:41 | 1:27 | 1:32 | 1:37 | 1:29 | 1:34 | 1:42 | 2:01 | 1:54 | 1:41 | 2:18 | Amber 95th percentile - P. See Red 8 minute performance for explanation.
|  |  | Amber 95th percentile - SB |  | Reduction Trend | - | - | - | - | - | - | - | - | - | - | - | - | 5:14 | 4:21 | 4:23 | 4:24 | 5:08 | 6:24 | 7:46 | 7:52 | 8:40 | Amber 95th percentile - SB. See Red 8 minute performance for explanation.
|  |  | Amber 95th percentile - ABM |  | Reduction Trend | [12 empty] | - | - | - | - | - | - | - | - | - | Amber 95th percentile - ABM. See Red 8 minute performance for explanation.
18 | Call to door times | 95th percentile call to door times (STEMI and Stroke) to reduce across each health board area. | - | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Reduction Trend | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Measure in development | Ongoing | A
19 | Clinical indicator | Clinical indicactors performance to improve, and be above 95% in all health board areas (except ROSC). | % of stroke patients documented as receiving the appropriate stroke bundle of care (AQI 16) | Name Brendan Lloyd Role Medical Director Contact brendan.lloyd@wales.nhs.uk | 95% | 98.1% | 96.2% | 96.6% | 96.8% | 96.3% | 97.4% | 94.2% | 95.8% | 95.3% | 96% | 95.9% | 96.8% | 94.8% | 95.1% | 96.6% | 95.8% | 96.6% | 96.6% | - | - | - | % of stroke patients documented as receiving the appropriate stroke bundle of care (AQI 16) | Improved | G
|  |  | % of patients with a fractured hip/femur who are documented as receiving analgesia (AQI 16) |  | 95% | 90.3% | 90% | 88..0% | 92.6% | 94.4% | 90.9% | 92.1% | 92.5% | 91.5% | 91.7% | 93.3% | 94.3% | 94.2% | 91.4% | 93.7% | 92.8% | 89.8% | 93.8% | - | - | - | % of patients with a fractured hip/femur who are documented as receiving analgesia (AQI 16) | Ongoing | A
|  |  | % of acute coronary syndrome patients who are documented as receiving appropriate STEMI care bundle (AQI 16) |  | 95% | 66% | 73% | 74.3% | 73.8% | 81.1% | 69.1% | 60.8% | 74.7% | 76.3% | 65.9% | 60% | 66.7% | 71.9% | 66.7% | 82.9% | 70.7% | 87% | 71.4% | - | - | - | % of acute coronary syndrome patients who are documented as receiving appropriate STEMI care bundle (AQI 16) | Deterioration | R
|  |  | % older people with suspected hip fracture documented as receiving appropriate care bundle (AQI 16) |  | 95% | 78.7% | 75.1% | 75.5% | 80.8% | 82.3% | 76.6% | 81.2% | 79.1% | 79% | 80.6% | 82.7% | 88.7% | 85% | 80.5% | 83.9% | 81.5% | 80.8% | 83.2% | - | - | - | % older people with suspected hip fracture documented as receiving appropriate care bundle (AQI 16) | Deterioration | R
|  |  | % suspected sepsis patients who had a documented NEWS score (AQI 16) |  | 95% | 100% | 98% | 100% | 97.6% | 98% | 97.4% | 98% | 98.4% | 100% | 100% | 100% | 100% | 100% | 91.7% | 100% | 98.4% | 100% | 97.7% | - | - | - | % suspected sepsis patients who had a documented NEWS score (AQI 16) | Improved | G
|  |  | % patients with suspect febrile convulsion documented as receiving appropriate care bundle (AQI 16) |  | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | - | - | - | % patients with suspect febrile convulsion documented as receiving appropriate care bundle (AQI 16) | Improved | G
|  |  | % of hypoglycaemic patients documented as receiving appropriate care bundle (AQI 16) |  | 95% | 84.4% | 87.5% | 90.5% | 93.3% | 91.7% | 87.3% | 89.9% | 89.8% | 87.2% | 85.3% | 89% | 88.2% | 93.1% | 82.8% | 89.2% | 87.6% | 86% | 89.8% | - | - | - | % of hypoglycaemic patients documented as receiving appropriate care bundle (AQI 16) | Ongoing | A
20 | Handover to clear | Handover to clear times to reduce across all health boards areas. | Number of lost hours following handover to clear over 15 minutes | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Reduction Trend | 862 | 941 | 816 | 909 | 916 | 888 | 961 | 1017 | 962 | 1099 | 926 | 985 | 1062 | 947 | 644 | 342 | 283 | 300 | 327 | 338 | 394.7 | Number of lost hours following handover to clear over 15 minutes | Improved | G
[28 empty] | 8 |  | 3 complete and 5 improved
11
8
27

## Table 2
Table 2
| Title | Summary Description | Lead | Measure |  | Current Performance | [21 empty] | WAST RAG | RAG Colour Code |  |  | Table 2
[5 empty] | Target | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | WAST Update |  |  | Complete/Improved | G | 4
1 | HCP performance | Compliance with HCP time requests to improve across each health board area. | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Compliance with HCP time requests to improve across each LHB | Improvement Trend | 85.3% | 83.49% | 83% | 82.7% | 83.57% | 82.7% | 81.8% | 82.1% | 79.2% | 78.6% | 78.6% | 79.9% | 79.8% | 80.3% | 80.6% | 78% | 77.9% | 83.7% | 90% | 90.9% | 89.3% |  | Improved | G | Ongoing | A | 7
2 | Non-ED conveyance | Proportion of conveyance to locations other than major emergency departments to increase across each health board area. | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Proportion of total conveyance to other locations (i.e. Tier 2 - MIU, Tier 3 - Other, etc.) other than Major ED | Improvement Trend | 8.372% | 8.518% | 8.429% | 8.695% | 8.477% | 8.029% | 8.361% | 8.433% | 8.183% | 8.102% | 8.185% | 8.531% | 9.094% | 8.787% | 8.839% | 8.859% | 7.981% | 8.435% | 7.99% | 7.51% | 7.99% |  | Ongoing | A | Deterioration | R | 8
|  |  |  | Proportion of conveyance to other locations other than major ED's (Tier 2 - MIU, Tier 3 and Other e.g. Maternity or MH Units) - AB | Improvement Trend | 4.885% | 5.455% | 4.844% | 5.362% | 5.314% | 4.382% | 4.811% | 5.073% | 4.826% | 5.532% | 4.425% | 5.382% | 5.101% | 5.315% | 5.486% | 6.397% | 4.952% | 5.01% | 5.18% | 4.58% | 5.33% |  | Improved | G | Development | - | 0
|  |  |  | Proportion of conveyance to other locations other than major ED's (Tier 2 - MIU, Tier 3 and Other e.g. Maternity or MH Units) - BCU | Improvement Trend | 3.037% | 2.85% | 2.92% | 3.278% | 2.515% | 2.301% | 2.33% | 2.489% | 1.757% | 2.147% | 2.548% | 2.423% | 2.892% | 3.094% | 3.178% | 2.82% | 2.663% | 2.486% | 2.656% | 2.311% | 2.502% |  | Improved | G
|  |  |  | Proportion of conveyance to other locations other than major ED's (Tier 2 - MIU, Tier 3 and Other e.g. Maternity or MH Units) - C&V | Improvement Trend | 17.36% | 17.53% | 18.25% | 19.38% | 19.17% | 19.63% | 19.64% | 18.15% | 18.8% | 16.5% | 18.51% | 18.88% | 21.55% | 21.17% | 17.78% | 21.25% | 19.02% | 19.37% | 18.71% | 10.59% | 17.78% |  | Ongoing | A
|  |  |  | Proportion of conveyance to other locations other than major ED's (Tier 2 - MIU, Tier 3 and Other e.g. Maternity or MH Units) - CTM | Improvement Trend | - | - | - | - | - | - | - | - | - | - | - | - | 0.8826% | 0.7616% | 0.665% | 1.248% | 0.9278% | 0.91% | 0.7445% | 0.8916% | 0.5634% |  | Ongoing | A
|  |  |  | Proportion of conveyance to other locations other than major ED's (Tier 2 - MIU, Tier 3 and Other e.g. Maternity or MH Units) - CT | Improvement Trend | 0.7498% | 0.9145% | 0.7925% | 0.7923% | 0.815% | 0.5597% | 0.5737% | 0.7382% | 0.6814% | 0.9103% | 0.5157% | 0.6176% | - | - | - | - | - | - | - | - | -
|  |  |  | Proportion of conveyance to other locations other than major ED's (Tier 2 - MIU, Tier 3 and Other e.g. Maternity or MH Units) - HDd | Improvement Trend | 16.89% | 16.74% | 16.95% | 16.23% | 17.21% | 15.77% | 16.65% | 17.43% | 16.94% | 17.77% | 17.43% | 17.51% | 18.97% | 16.66% | 16.87% | 15.72% | 15.96% | 17.17% | 16.62% | 16.05% | 21.83% |  | Ongoing | A
|  |  |  | Proportion of conveyance to other locations other than major ED's (Tier 2 - MIU, Tier 3 and Other e.g. Maternity or MH Units) - P | Improvement Trend | 9.861% | 8.951% | 9.827% | 9.938% | 8.767% | 7.064% | 9.594% | 10.38% | 10.08% | 8.342% | 7.336% | 9.645% | 8.462% | 9.648% | 8.682% | 9.533% | 8.317% | 8.619% | 8% | 10.81% | 10.34% |  | Ongoing | A
|  |  |  | Proportion of conveyance to other locations other than major ED's (Tier 2 - MIU, Tier 3 and Other e.g. Maternity or MH Units) - SB | Improvement Trend | - | - | - | - | - | - | - | - | - | - | - | - | 15.11% | 14.14% | 16.01% | 14.84% | 12.53% | 12.84% | 11.49% | 12.53% | 11.88% |  | Improved | G
|  |  |  | Proportion of conveyance to other locations other than major ED's (Tier 2 - MIU, Tier 3 and Other e.g. Maternity or MH Units) - ABM | Improvement Trend | 10.94% | 11.34% | 10.08% | 10.9% | 9.785% | 10.4% | 10.4% | 11.06% | 10.88% | 11.25% | 11.36% | 10.79% | - | - | - | - | - | - | - | - | -
3 | Pathways | Proportion of patients referred to alternative pathways/services to increase following "hear & treat" and "see & treat". | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Percentage of calls ended through transfer to alternative care advice services | Improvement Trend | 57.11% | 58.72% | 56.57% | 59.24% | 60.51% | 57.66% | 59.62% | 54.7% | 56.2% | 55.5% | 56.7% | 57.6% | 59.2% | 59.9% | 60% | 57.5% | 57.5% | 55.1% | 56.3% | 57.7% |  |  | Ongoing | A
|  |  |  | Percentage of verified incidents which resulted in non conveyance to hospital - Referred to alternate provider | Improvement Trend | 42.89% | 41.27% | 43.43% | 40.76% | 39.49% | 42.34% | 40.38% | 42.62% | 45.46% | 44.51% | 44.11% | 44.32% | 44.06% | 41.71% | 41.83% | 40.06% | 39.88% | 42.47% | 43.66% | 44.6% |  |  | Ongoing | A
4 | Handover | Notification to handover times to reduce across all health boards areas. | Name Louise Platt Role Operations Director Contact louise.platt@wales.nhs.uk | Number of lost hours following notification to handover over 15 minutes | Reduction Trend | 6134 | 4137 | 3777 | 4562 | 4669 | 5253 | 6020 | 4707 | 6038 | 8781 | 5610 | 6833 | 8766 | 7100 | 7325 | 8048 | 8408 | 10025 | 11132 | 11474 | 13822 | HB responsibility | Deterioration | R
|  |  |  | Number of lost hours following notification to handover over 15 minutes - AB | Reduction Trend | 944 | 639 | 478 | 728 | 931 | 1189 | 1087 | 948 | 1289 | 1712 | 1394 | 1499 | 1915 | 1631 | 1534 | 2465 | 2184 | 2463 | 2824 | 2162 | 2735 | HB responsibility, but WAST collaborating related initiatives: revised daily call arrangement, reducing conveyance (APPs, Band 6 Paramedic, pathways), cohorting and EQDF development. | Deterioration | R
|  |  |  | Number of lost hours following notification to handover over 15 minutes - BCU | Reduction Trend | 2257 | 1304 | 1662 | 1843 | 1852 | 1830 | 2180 | 1072 | 1227 | 1813 | 1067 | 1298 | 1871 | 1561 | 1262 | 2091 | 1863 | 2271 | 2075 | 2037 | 2626 | HB responsibility, but WAST collaborating related initiatives: revised daily call arrangement, reducing conveyance (APPs, Band 6 Paramedic, pathways), cohorting and EQDF development. | Deterioration | R
|  |  |  | Number of lost hours following notification to handover over 15 minutes - C&V | Reduction Trend | 877 | 479 | 309 | 248 | 428 | 453 | 750 | 600 | 628 | 966 | 758 | 522 | 512 | 559 | 758 | 613 | 707 | 757 | 1085 | 1228 | 1091 | HB responsibility, but WAST collaborating related initiatives: revised daily call arrangement, reducing conveyance (APPs, Band 6 Paramedic, pathways), cohorting and EQDF development. | Deterioration | R
|  |  |  | Number of lost hours following notification to handover over 15 minutes - CTM | Reduction Trend | - | - | - | - | - | - | - | - | - | - | - | - | 1005 | 742 | 580 | 645 | 961 | 827 | 1055 | 1009 | 1601 | HB responsibility, but WAST collaborating related initiatives: revised daily call arrangement, reducing conveyance (APPs, Band 6 Paramedic, pathways), cohorting and EQDF development. | Deterioration | R
|  |  |  | Number of lost hours following notification to handover over 15 minutes - CT | Reduction Trend | 18 | 17 | 14 | 19 | 22 | 25 | 34 | 35 | 45 | 36 | 28 | 33 | - | - | - | - | - | - | - | - | - | HB responsibility, but WAST collaborating related initiatives: revised daily call arrangement, reducing conveyance (APPs, Band 6 Paramedic, pathways), cohorting and EQDF development.
|  |  |  | Number of lost hours following notification to handover over 15 minutes - HD | Reduction Trend | 424 | 424 | 375 | 514 | 266 | 417 | 380 | 406 | 523 | 802 | 547 | 906 | 856 | 469 | 619 | 532 | 612 | 788 | 954 | 1564 | 2184 | HB responsibility, but WAST collaborating related initiatives: revised daily call arrangement, reducing conveyance (APPs, Band 6 Paramedic, pathways), cohorting and EQDF development. | Deterioration | R
|  |  |  | Number of lost hours following notification to handover over 15 minutes - P | Reduction Trend | 181 | 126 | 92 | 149 | 158 | 161 | 198 | 150 | 217 | 272 | 233 | 165 | 302 | 181 | 200 | 158 | 228 | 316 | 288 | 303 | 216 | HB responsibility, but WAST collaborating related initiatives: revised daily call arrangement, reducing conveyance (APPs, Band 6 Paramedic, pathways), cohorting and EQDF development. | Deterioration | R
|  |  |  | Number of lost hours following notification to handover over 15 minutes - SB | Reduction Trend | - | - | - | - | - | - | - | - | - | - | - | - | 2306 | 1958 | 2372 | 1544 | 1853 | 2464 | 2851 | 3170 | 3361 | HB responsibility, but WAST collaborating related initiatives: revised daily call arrangement, reducing conveyance (APPs, Band 6 Paramedic, pathways), cohorting and EQDF development. | Deterioration | R
|  |  |  | Number of lost hours following notification to handover over 15 minutes - ABMU | Reduction Trend | 1433 | 1149 | 847 | 1062 | 1012 | 1169 | 1391 | 1496 | 2109 | 3179 | 1583 | 2140 | - | - | - | - | - | - | - | - | - | HB responsibility, but WAST collaborating related initiatives: revised daily call arrangement, reducing conveyance (APPs, Band 6 Paramedic, pathways), cohorting and EQDF development.