## 2021-22 CI
Agenda Item 12; Appendix 1
Ref | Commissioning Intention | Delivery Date | Progress update
EMS
EMS Commissioning Intention – CI1 Clinical Response Model
Aims
CI1-A1 | Increase the proportion of activity resolved at Step 2 – Using the activity within the demand and capacity review as a baseline, this aim requires the proportion of activity resolved at step 2 to increase. No specific proportion of activity will be set for achievement of this aim for 2021/22 but stretch goals will be agreed collaboratively throughout the year. | 2022-03-31 | Includes: - CSD roster review, working groups held, planned go live date of 3 January 22 - implemented January 2022. A lessons learned meeting is scheduled for the 29th March and a feedback meeting is scheduled for 26th April to discuss if the benefits of the roster are being realised in terms of both UHP and staff well-being. - CSD recruitment plan to increase by 36 FTEs as agreed with commissioner, staff currently in training becoming operational during March-May period. - PTAS - ongoing engagement with HBs following virtual event (November) and overcoming firewall/access issues. PTAS live in BCU and HDda, go live date imminent for ABUHB, training dates being arranged for SBUHB and CVUHB. Meetings scheduled with PTHB and CTMUHB. - Code set change - seven MPDS codes now directed straight to telephone triag, work being undertaken to report against use of these codes. Further codes identified as suitable for 'Consult and Close', currently being considered for approval. - ECNS - clinical triage software - good progress made in terms of procurement, recruitment and governance. Key enabler for clinically assessing more 999 calls, go live May 22 - Mental health pracs - anticipated start dates December 21, training and induction almost complete, operational from May 22. Ongoing rectruitment to fill the 6th vacancy.
CI1-A2 | Right response first time – Optimising multiple responses at Step 3 – Using activity within the demand and capacity review as a baseline, this aim requires an improvement in the multiple response rate (excluding Red) and the resolution of that episode of care by a single resource. | 2022-06-30 | - Code set change - seven MPDS codes now directed straight to telephone triage, work being undertaken to report against use of these codes. Further codes identified as suitable for 'Consult and Close', currently being considered for approval. - EMS Roster review - fourth stage commenced 4 April, go live scheduled for Qtr 3 22-23. Key element of the work to increase EAs.
Products
CI1-P1 | Remote Clinical Support Strategy – Development and approval of an overarching remote clinical support strategy that outlines the organisational ambition for remote clinical support at the forefront of ambulance service care. | 2022-03-31 | - Transformation Board established and project definition document being developed. Work has also already taken place in development of the CCC Clinical Review and the organisation's strategic ambition statement, currently working with commissioners around mental health practitioners in the CSD, roster review in CSD etc. - WAST currently conveying c.40%/<40% of patients into ED (previously c.50%). - Remote clinical strategy part of WAST's overall strategy as an organisation and our ambition to “flip/invert the triangle”, bringing together the Clinical Strategy and Digital Patient/Workplace missions within the Digital Strategy. - Commissioning Intention rolled over into the 2022/23 work programme (remit of WAST Gateway to Care Programme Board). Further discussions planned for the end of April to develop strategy.
CI1-P2 | Optimising Conveyance Improvement Plan – Development and implementation of an improvement plan or programme that support the optimisation of conveyance. This will include non-conveyance as well as improving conveyance destination decisions. | 2021-12-31 | Key actions to optimise Conveyance include: - WAST has established a ‘Care Closer to Home Group’ to ‘increase the proportion of conveyances to locations other than major Emergency Departments (ED) across each Health Board area’ - There are 3 key workstreams : alternative care pathway development; Advanced Paramedic Practitioners; and the increase in non-medical prescribing - To date, the Care Closer to Home Group have: - introduced Consultant Paramedic for Urgent & Unscheduled Care role, which will provide effective clinical leadership and work collaboratively with all Health Boards - Agreed National COPD Referral Criteria and Pathway live in ABUHB and CTMUHB. Referral Process agreed with SBUHB, awaiting sign off of SOP and Flowchart by CC2HG - Refreshing the National Non-Injury Falls Referral Pathway; ongoing discussions with TerraFIX on the Functional Design Specification - Recruitment of 5 APPs to provide a 24/7 cover in the CCC - EMS Transition Business Case submitted to EASC to increase APP and IP provision which supports the "Inverting the Triangle" concept - Paramedic Pathway into UPCC (SBUHB) approved CC2HG, implementation plan in development Further modelling is also being commissioned from ORH to model a full "inversion of Triangle"
Indicators
CI1-I1 | Clinical Support Desk Outcomes – By close of 2021/22 quarterly reports will be available that describe the patient level outcomes for clinical support desk care episodes. | 2022-03-31 | Work was undertaken at the beginning of 2021 to change the outcomes. CSD outcomes codes have already changed and we are able to pull this data already. Red Cortex are working to pull this into a Power BI type report. First drafts of this dashboard have been seen. More work is needed and this will be done towards the end of ECNS implementation because by then the outcomes will be configurable. Estimated Go Live of ECNS May 2022
CI1-I2 | Outcomes by Response Type - By close of 2021/22 quarterly reports wil be available that describe the patient level outcomes for different response types. | 2022-03-31 | The CCC Clinical Review programme is ongoing and continues to implement the recommendations from the Clinical Review.
EMS Commissioning Intention – CI2 Availability
Aims
CI2-A1 | Closing of the relief capacity gap - The existence of a relief capacity gap has been understood for over a decade. The most recent demand and capacity review has identified the current gap and whilst the closure of this gap is dependent on a range of factors (Ministerial Taskforce, funding, efficiencies etc.), this gap will be resolved by the close of 2021/22. | 2022-03-31 | The plan to deliver an additional 127 FTEs in 21/22 and close the relief gap was achieved for EMTs and Paramedics with a slight shortfall on UCAs against the plan due to C1 Licence issue and the prioritised decision to recruit 36 Paramedics into the CSD. Commissioning intention for 22-23 to maintain the closed relief gap.
CI2-A2 | Rosters aligned to demand - The current demand profile is not matched by available resource. This has a significant impact on quality of service for patients and wellbeing of staff. By close of 2021/22 rosters aligned to demand will be available for each area and an implementation programme will be in place. | 2022-03-31 | 3 working parties already completed, 4th and final working party due w/c 4th April Majority of stations/teams progressing well and likely to be fine for final vote post working party 4 (vote likely May 22) New roster implementation aimed at Sep-Nov 22 (finalised implementation plan TBC) CHARU role/rosters to be implemeneted on same timeframe as EA/ACA2 rosters Some R+R from certain sections (Cwm Taf) will be heard before the end of March 22.
Products
CI2-P1 | Demand and Capacity Strategy – A collaboratively developed demand and capacity strategy will set out the ongoing arrangements for proactively undertaking this work for the next decade, this will include the use of forecasting, modelling and health economic evaluations. | 2021-12-31 | Forecasting & Modelling group continues to support the organisational strategic priorities through various pieces of work but the work to develop a framework/strategy as specific output for this commissioning intention is currently paused. Paused due to escalation, but now aiming for Q2 22/23.
Indicators
CI2-I1 | Additionality measure – A collaboratively agreed additionality requirement for the end of 2021/22 will be in place by the end of Quarter 1. This will account for vacancy factors, turnover and other confounders. | 2021-06-30 | Internal audits undertaken on commissioning and commissioned side and given reasonable assurance (close to significant assurance). The plan to deliver an additional 127 FTEs in 21/22 and close the relief gap was achieved for EMTs and Paramedics with a slight shortfall on UCAs against the plan due to C1 Licence issue and the prioritised decision to recruit 36 Paramedics into the CSD. Commissioning intention for 22-23 to maintain the closed relief gap.
EMS Commissioning Intention – CI3 – Productivity
Aims
CI3-A1 | Reducing Post-Production Lost Hours – Post-production lost hours have been a significant contributor to reduced productivity. Using an agreed baseline measurement period, Post-production lost hours will be reduced in line with a quarterly agreed improvement trajectory. | Dependent on TU negotiations - Q1 to Q4 action | Delivering the abstractions target remains a concern, linked to the on-going impact of CoVID-19, as does the potential impact of high levels of escalation during the winter plan period. WAST is working on a targeted plan to reduces sickness. Leading Service Change Together (post production lost hours) now forms part of the programme. WAST IMTP for 2022/23 sets out a need to agree a baseline and collaboratively develop options to reduce PPLH where appropriate.
CI3-A2 | Reducing Notification to Handover Time – NHS Wales is a significant outlier in the UK and Internationally for lost productivity due to extended notification to handover times. By the end of 2021/22 NHS Wales will have reduced 1 hour waits to less than 5% of total arrivals and ensured that total lost hours at Welsh Hospitals do not exceed 150 hours per day on 95% of the year. | 2022-03-31 | Anbulance handover delays continue to increase across the system and the Committee has noted that the solution to mitigating the impact of handover delays can not be solely via WAST employing additional staff and delivering efficiencies that they have previously committed to. Cross-system action is required. Noting the previous commitment to delivering a maximum of a 150 hours lost a day, or circa 5,000 hours a month, the Committee has agreed to the following deliverables during the year as the start point of their commitment to reducing handover delays: • No ambulance handover will take more than 4 hours • We will reduce the average lost time per arrival by 25% from the October 2021 level at each site (from 72 minute to 54 minutes at an all Wales level) Handover improvement plans are now being developed by each Health Board with fortnightly meetings for each HB to commence between the CASC, COOs and WAST to monitor the progress made and to resolve issues as they arise. Discussions around handover delays have been included in the wider engagement around system escalation with HB COOs, Medical Directors and Directors of Nursing and discussed at NHS Wales Leadership Board.
Products
CI3-P1 | Modernising Workplace Practices Implementation Plan – There will be an implementation plan and supporting structures in place to ensure workforce practices and policies are reviewed, modernised and improved. The wellbeing of the workforce and safety of patients will be paramount within this. | Dependent on TU negotiations - Q1 to Q4 action | Delivering the abstractions target remains a concern, linked to the on-going impact of CoVID-19, as does the potential impact of high levels of escalation during the winter plan period. WAST is working on a targeted plan to reduces sickness. Leading Service Change Together (post production lost hours) now forms part of the programme. WAST IMTP for 2022/23 sets out a need to agree a baseline and collaboratively develop options to reduce PPLH where appropriate.
Indicators
CI3-I1 | Unit Hour Utilisation Metric – By the end of Quarter 2 A metric and appropriate dashboard will be developed that demonstrates the utilisation rate (and activity type) of various resources types, this will be available at Wales, HB, Locality, Station and individual resource level. | 2021-12-31 | Good engagement undertaken with stakeholders in 21-22 to introduce and explain this concept and then to embed into day to day system planning and escalation within WAST. This has included the weekly Operational Performance Meeting where this has already informed operational adjustments that have improved ambulance performance. WAST have recently started trialling a live utilisation report; however, there are still some data issues for utilisation reporting, in particular, relating to PPLH. Health Informatics have made available new reporting which is an improvement on the previous report, however the ultimate fix is required from the CAD supplier, date TBC. The development of this work will continue as a key part of its emerging Forecasting & Modelling Framework (EASC commissioning intention for 22/23).
EMS Commissioning Intention – CI4 - Value
Aims
C14- A1 | Value-Based Healthcare for the Welsh Ambulance Service Develop and embed a value-based approach for the Welsh Ambulance Service which enables better collective decision making across the whole urgent and emergency care system and accounts for WAST’s use of, and impact on, economic, social and environmental resources over the short, medium and long term. This will include: | See comments | The Commissioning for Value Programme has commenced in line with the Commissioning Intention 4: Value, which sets out a value based approach to Emergency Ambulance Services commissioning and service delivery. A board level briefing pack has been developed, which outlines the model and programme approach to delivering the commissioning intention. EASC team and WAST colleagues have worked collaboratively in developing this approach. EASC team have then engaged with wider stakeholders including Welsh Government, Audit Wales, EASC Committee Chair and WAST Non executive Director, as part of a Board level briefing and feedback exercise with regards to the onward development of the programme. The board briefing pack has also been presented to members of the EASC Management Group where the Value Based Commissioning Model, programme approach and short term priorities were endorsed. While progress on developing this approach was delayed due to the pandemic and the focus on optimising front line resources, further stakeholder engagement and work on programme priorities will now be continued. As part of the move to a recovery phase for the organisation, renewed focus will be provided to the Value agenda with the Trust VBHC group being reconvened especially in light of the recent WG directive to provide activity data linked to better patient outcomes. This remains a long term strategic intention.
| Development of WAST’s strategy and approach to Value-Based healthcare which links outcomes, patient experience and use of resources | 2021-09-30
| Implementation of a costing model for “5 step” pathway | 2022-03-31
| Improvement in ability to identify areas of unwarranted variation in service delivery across Wales | 2022-03-31
Products
CI4-P1 | Value-Based Strategy - The Trust will develop a strategy to implement a value-based approach across the organisation and outline its role in delivering value across the wider UEC system. The value-based strategy will be integrated with and align to existing organisational strategies (e.g. clinical, quality, long term, digital, environmental etc) and the Commissioning Intentions outlined in this document in order to ensure goal congruence. | 2021-09-30
CI4-P2 | Value-Based Tools and Methods - In order to monitor and measure value-based performance, the Trust will need to design, develop and implement a range of tools including, but not limited to, the following: | -
| Patient Level Costing Model | 2021-12-31
| Benchmarking Dashboard(s) | 2022-03-31
CI4-P3 | Value-Based Reporting
| WAST will enable a clear line of sight from commissioner allocation through to utilisation and the outcomes delivered by the services. WAST will holistically demonstrate through its reporting all separate revenue streams and associated costs of broader service provision (e.g. 111, NEPTS, etc). | On-going
| WAST receives a capital allocation directly from Welsh Government. The utilisation of the capital budget and the use of the ring-fenced depreciation allocation will need to be clearly identified in any report. As a result, WAST will be able to demonstrate how its capital allocation is being invested to deliver on the commissioning intentions. | On-going
Indicators
CI4-I1 | Value-Based Core Requirement to be agreed with Commissioner by the end of quarter 2: |  | See above.
| WAST Value Based Strategy | -
| Plan for Value Based Tools and Methods design, development and implementation | -
| Value Based Reports developed for revenue and capital | -
| Value-Based indicators developed in line with broader indicators outlined in CI1 to CI5 | -
| Connections to system-wide urgent and emergency care performance measures as identified in CI6 – Wider Health System | -
EMS Commissioning Intention – CI5 – Harm & Outcomes
Aims
CI5-A1 | Proactively Identifying Harm – The proportion of harm/near misses proactively identified prior to a complaint or report will increase. This will include process for reviewing patient clinical records and engagement with the wider health system (i.e. sharing information around patients impacted by DMP levels) | TBC | Commissioning intention rolled over as agreed ensuring continued focus on reducing harm.
Products
CI5-P1 | Clinical Indicator Plan and Audit Cycle – A clinical indicator plan and audit cycle will be in place, this will provide a forward view of the type, content and regularity of clinical indicator and audit reporting. Specific seasonal and responsive (to emerging trends) reports and audits will be included within the plan. | Plan and cycle to be agreed by end of October 2021 (prior to the roll-out of ePCR). | - The Clinical Intelligence Assurance Group has a wide remit of indicators and audit. Some existing Clinical Indicators have been reviewed and approved, and are awaiting Health Informatics to build a report - Health Informatics have commenced on the Qlicksense Dashboard for existing Clinical Indicators however it is anticipated that the Qlicksense Dashboard may take longer to deliver due to its complexity, estimated that this may be delivered in Q1 2022/23. - Discussions commenced with EASC (Ambulance Service Indicator Group) for the transition from DigiPen to ePCR data when reporting AQIs and 6 suggested areas for future Clinical Indicators have been shared informally with EASC for their view. - Proposal on the governance route submitted to the Ambulance Service Indicator Group, awaiting feedback from Commissioners. Awaiting feedback from Commissioners on the 7 suggested areas for future Clinical Indicators. - COPD Clinical Indicator tested, further clinical clarification required by the Ambulance Practice Steering Group Collaborative work between the Clinical Audit & Effectiveness Department and Health Informatics is ongoing to quality assure clinical data and develop reporting mechanisms for four of the current CIs. Reporting of these AQIs is anticipated to begin in May 2022, using ePCR data from April 2022. The development of suggested new CIs will form part of the annual Clinical Audit Programme to establish if they are appropriate as CIs for reporting or as audits to identify learning and improve patient care
Indicators
CI5-I1 | Call to Door Times – call to door times for STEMI and stroke will be produced on a monthly basis. | 2022-03-31 | This indicator is reliant on linked data between the PCR and CAD systems. Discussions have been held around possibly using MINAP data for some of the times but this did not progress or look like an easy or reliable option (other UK Trusts had issues with this). This work is also dependent on implementation, testing and assurance of ePCR which will include the necessary times to produce this metric. WAST has experienced delays in the operational deployment of the ePCR. There is an ambition, once the full data set is completed that CAD data can be linked to key presentations to enable an assessment of the time stamps. This is part of the work through the Clinical Intelligence Assurance Group. Further discussions with NCCU on agreeing the defintion of and delivery date of this indicator.
EMS Commissioning Intention – CI6 – Wider Health System
Aims
CI6-A1 | System Flow - optimise the flow of ambulances in to hospital sites in Wales, reducing batching and increasing timeliness of patients to accessing secondary care | 2022-03-31 | Delivered as part of EMS Roster Reveiw Project - aim to implement rosters by end of Qtr 2 22-23. 3 working parties already completed, 4th and final working party due w/c 4th April Majority of stations/teams progressing well and likely to be fine for final vote post working party 4 (vote likely May 22) New roster implementation aimed at Sep-Nov 22 (finalised implementation plan TBC) CHARU role/rosters to be implemeneted on same timeframe as EA/ACA2 rosters Some R+R from certain sections (Cwm Taf) will be heard before the end of March 22.
CI6-A2 | Transfer and Discharge Service – To reduce the number of transfers and discharges being undertaken by the EMS fleet. | 2021-09-30 | Scoping of existing transfer and discharge services across the system already undertaken. Project team to be established, followed by facilitation of stakeholder workshops to agree scope, project parameters, forecasting and modelling, identify and evaluate options and develop preferred option in terms of service model and funding, benefits. Development of business case. Agreed at EASC Committee that a comprehensive baseline analysis and scoping exercise will be undertaken as part of the work to develop the case in order to remove duplication and to ensure an efficient and effective service.
Products
CI6-P1 | System wide escalation and demand management plan – A single aligned escalation and demand management plan will be in place, this will include the actions health boards must take to support patients when the EMS service has reached DMP 4. Health Boards will develop an equivalent of the DMP for Emergency Departments. | 2021-12-31 | Discussions around system-wide escalation have taken place at a number of forums across the system, with community therapy representatives including WG representation and mental health services. In addition, plans have been shared and developed with COO’s, MDs and DoTHS and the plan is to share at a joint DONs and MDs meeting on Friday 19th November. Follow ups are also planned with COO’s and DoTHS. An Escalation Tool is also being rolled out via the EDQDF support clinics which is attended by frontline staff from each ED with a view to going live in Quarter 4 (21-22).
CI6-P2 | National Transfer and Discharge Commissioning Framework – A collaborative commissioning framework for a national transfer and discharge service will be agreed by close of 2021/22. | 2022-03-31 | NCCU to lead, with support from WAST, to develop the framework for a national transfer & discharge service
Indicators
CI6-I1 | System Pressures Dashboard – WAST and Health Boards will collaborate to ensure that a live system pressures dashboard is in place that enables users to understand current and emerging pressures. | 2021-12-31 | A systems pressure dashboard with a focus on the utilisation measure (Commissioning Intention 3) has been included within the Urgent & Emergency Care Improvement Plan as part of the work around system escalation. Work required with HB colleagues and WG (DU etc) in the development of this.
NEPTS
NEPTS Commissioning Intention 1- Plurality Model
CI1a | Transfer of Work - Complete the transfer of work from health boards to WAST and develop a plan to novate any outstanding areas | 2021-06-30 | Final transfer of work for CTM completed on the 1st October 2021.
CI1b | Resource Efficiency - Demonstrate that resources are being utilised effectively following transfer of work | 2022-03-31 | Next step to enable effective implementation of the plurality model is to produce the Procurement Strategy, work has already commenced. Regional discussions regarding the Procurement Strategy have commenced. Each region have different levels of demand so will discuss locally and feed back to the Contracts Review and Delivery Group. This process will increase capacity and resilience in the system. The procurement plan has been approved by the Senior Responsible Officer of ACT. The plan is broken down into ten steps including, but not limited to, reviewing the service, creating a framework, monitoring performance through the development of a dashboard within 365, reinvesting efficiency gains back into NEPTS, reviewing estates opportunities, improving relationships with suppliers. The next steps with regards to the procurement plan is to identify the membership of the working groups required for each of the 10 actions. The Quality Framework discussions have begun with the Commissioners (Meeting 8th Oct-21).
CI1b | Plurality Providers - Continue to expand and improve the availability of plurality providers | 2022-03-31 | Next step to enable effective implementation of the plurality model is to produce the Procurement Strategy, work has already commenced. Regional discussions regarding the Procurement Strategy have commenced. Each region have different levels of demand so will discuss locally and feed back to the Contracts Review and Delivery Group. This process will increase capacity and resilience in the system. The Quality Framework discussions have begun with the Commissioners (Meeting 8th Oct-21). The National Project Group, focusing on 'Contract Redesign and Renewal' have completed Alternative Provider engagement meetings with a focus on both quality and value for money and how that will shape procurement going forward.
NEPTS Commissioning Intention 2 – Demand
CI2a | Planning - Implement improved and dynamic planning process that maximise the utilisation of resources | 2022-03-31 | Positive progress being made under five workstreams: − Roster Review: Surgeries are taking place with General Managers regarding reviewing the demand keys. − Oncology: The PID is being reviewed by the ACT D&C project team − Outbound Ready Times: The automated cancellation line and cisco agent tool have been introduced in December 2021 and January 2022 respectively. The PDSA regarding updating the throughput time in Cleric from 90 minutes to 30 minutes is in progress and a review is expected in early April on the findings. − NET Centre, Planning and Day Control: An SBAR has been submitted to EASC regarding an uplift of 12 FTEs. Work in ongoing with regards to NetCall to introduce a ring back service (the patient will not have to stay on hold, they will be called back when they reach the front of the queue) and this is expected to be implemented at the end of March 2022. − T1 Walkers Reduction: A workshop took place with the Chief Ambulance Services Commissioner's office on 4th March 2022 in which the future of eligibility was discussed. Further work will be carried out when guidance is received from Welsh Government and CASC.
CI2b | Reducing Demand – Identify opportunities to reduce and redirect demand to more appropriate transport options (for 2021/22 this should focus on T1 Walker and Renal Patients) | 2022-03-31 | Ongoing. A workshop took place with the Chief Ambulance Services Commissioner's office on 4th March 2022 in which the future of eligibility was discussed. The project will continue to develop options to direct T1 walkers into other available transport options where possible e.g. Fflesci buses. Further work is to be carried out around eligibility once further guidance is received from Welsh Government and Chief Ambulance Services Commissioner, following the workshop. The National Project Group, focusing on 'Contract Redesign and Renewal' have completed Alternative Provider engagement meetings with a focus on both quality and value for money and how that will shape procurement going forward. Local Resource Vehicle Pilot Scheme - The Local Resource Vehicle (LRV) pilot scheme commenced on 08 November 2021 and is due to end on 31 March 2022. To date, the pilot scheme has been successful and an evaluation will now be completed before decisions on further use are made. Standard Operating Procedure (for the booking system) - The SOP has been updated and Health Boards are receiving training on the SOP and booking system as and when requested.
NEPTS Commissioning Intention 3 – Capacity
CI3a | Transforming Capacity – Implement processes to increase NEPTS capacity within current resources | 2022-03-31 | Ongoing. D&C NEPTS roster review will look to right size as opposed to increase workforce by 30 FTE. In terms of the NEPTS Operational Improvement Project: - Oncology: The National Process Document has been agreed in principle by Velindre. The PDSA regarding the national booking process is due to start on the 4th April and be reviewed after two weeks. The results will be shared with the Senior Team within NEPTS to consider the next steps. - Cancellations: The trial regarding maximising the use of the discharge lounge will commence with Ysbyty Gwynedd on the 28th March and run for one month, with weekly reviews. At the end of the trial, the process will be evaluated with a view to extending this across the 3 main sites in BCUHB. - National standardised guidance and risk assessments: The Working Group was established on the 16th March. Work is to be undertaken on the SOPs to support the risk assessments in those areas where a SOP does not currently exist.
CI3b | Reducing lost capacity – Implement improvement plans and oversight arrangements to deliver reduction in lost capacity due to system inefficiencies | 2022-03-31 | Ongoing. - Post Production Lost Hours: Health Informatics have created a new sheet for post production lost hours, which is within the existing Qlik report and the Project team have agreed the codes which need to feed into the report. These include, but are not limited to: Vehicle Moves, Wait and Return, Completing Datix, Training. The project team are exploring the creation of 3 reports within Qlik, the first version of which is available for review. These cover the total PPLH overview, PPLH breakdown, and PPLH trends - Outbound Ready Times: The automated cancellation line and cisco agent tool have been introduced in December 2021 and January 2022 respectively. Work has continued with regards to the PDSA to improve outbound ready times i.e. ensuring both the patient and the vehicle are ready at the required time. Two clinics have utilised for this (one in North Wales, one in Central and West) with an average throughput time of 90 minutes. Cleric has been updated to reflect a throughput time of 30 minutes at these clinics. A review is expected in early April to review all findings evaluate the result of the PDSA in terms of the outcome and benefits. - Standard Operating Procedure (for the booking system) - The SOP has been updated and Health Boards are receiving training on the SOP and booking system as and when requested.
NEPTS Commissioning Intention 4 – System Transformation
CI4a | Demand and Capacity Strategy – A collaboratively developed demand and capacity strategy will set out the ongoing arrangements for proactively undertaking this work for the next decade, this will include the use of forecasting, modelling and health economic evaluations | 2021-12-31 | Led by the WAST Forecasting and Modelling Group, work is underway to develop a robust strategy to tactically plan and forecast seasonal fluctuation and to ensure resource and resilience during times of system pressure. This will ensure a framework for going forward with the required strategic, tactical and operational focus. Workshop planned for May 22 to discuss the scope and development of the framework.
EMRTS
EMRTS Commissioning Intention 1- Service Expansion
CI1a | Evaluation and Review – Undertake evaluation and review relating to the implementation of Phase 1, reporting on lessons learned, service activity and providing the required assurance regarding the realisation of anticipated outcomes and benefits. | 2021-12-31 | Phase 1 night road response commenced July 20 with night HEMS (air response) commenced December 20 - evaluation of first twelve months presented to EMRTS DAG March 22 including activity (by base, response mode and locality), realisation of outcomes and benefits against the EMRTS service expansion review. Also included data relating to unmet need. Next steps include regional analysis, drill down of missed tasking data.
CI1b | Planning – Build on the implementation and consolidation of Phase 1, working collaboratively to plan the implementation of the remaining phases of the EMRTS Service Expansion programme. | Ongoing | Working with stakeholders, evaluation of phase 1 to inform inform further phases of expansion.
EMRTS Commissioning Intention 2 – Adult Critical Care Transfer Service Implementation
CI2a | Project Set-Up and Implementation – Complete the set-up and implementation phases including workforce, governance and operational elements. | 2021-09-30 | Road-based adult critical care transfer service now live with service models in both North (YG, Bangor) and South Wales (Cardiff Heliport). Slightly increased model in North Wales, following engagement with BCUHB colleagues, in order to meet the needs of the population. Good stakeholder engagement reported both locally and across the network, this will continue. Activity significantly higher than anticipated in both North and South.
CI2b | Service Delivery - Evolve to a phase of ongoing service delivery and a shift in focus of the reporting regime. | 2021-12-31 | Demand and capacity review undertaken, specifically to examine the first three months of out-of-hours activity data for north Wales. Comprehensive evaluation to be undertaken at end of Year 1. Focus has now changed from set-up and implementation to ongoing service delivery. Highlight reporting via EMRTS DAG - Risks reported including relating to delivery date for transfer vehilces (mitigated by use of loan vehicles). ACCTS quality and delivery framework to be added as an addendum to the established EMRTS QDF after one year of operation.
EMRTS Commissioning Intention 3 – Service Evaluation
CI3a | Review – Consider and review the EMRTS Service Evaluation Report in order to understand its implications for the service. | 2021-09-30 | Presentation provided on key findings to EMRTS DAG in June. Service evaluation now available.
CI3b | Improvement Plan – Develop and implement an improvement plan in response to the Report. | 2022-03-31 | Plan to be developed
EMRTS Commissioning Intention 4 – System Transformation
CI4a | Demand and Capacity Strategy – A collaboratively developed demand and capacity strategy will set out the ongoing arrangements for proactively undertaking this work for the next decade, this will include the use of forecasting, modelling and health economic evaluations. | 2022-03-31 | Work has been undertaken with WAST colleagues to understand the modelling and planning work undertaken by them, with a view to developing a commissioning strategy that is driven by forecasted demand and activity. Scenario modelling now underway.