AGENDA ITEM

2.7

EMERGENCY AMBULANCE SERVICES COMMITTEE

EASC COMMISSIONING UPDATE

| Date of meeting | 16/05/2023 |
| --- | --- |

| FOI Status | Open/Public |
| --- | --- |

| If closed please indicate reason | Not Applicable - Public Report |
| --- | --- |

| Prepared by | Ross Whitehead, Deputy Chief Ambulance Services Commissioner |
| --- | --- |
| Presented by | Ross Whitehead, Deputy Chief Ambulance Services Commissioner |
| Approving Executive Sponsor | Chief Ambulance Services Commissioner |

| Report purpose | FOR NOTING |
| --- | --- |

| ACRONYMS |  |
| --- | --- |
| CASC EMS EMRTS ICAPs IMTP NEPTS | Chief Ambulance Services Commissioner Emergency Medical Services Emergency Medical Retrieval and Transfer Service (EMRTS Cymru) Integrated Commissioning Action Plans Integrated Medium Term Plan Non Emergency Patient Transport Service |

- SITUATION/BACKGROUND

  - Working with providers on behalf of the Committee, the Chief Ambulance Services Commissioner (CASC) and the EASC Team enact the priorities of the Committee for their populations, with benefits delivered to patients and the Welsh public, Welsh Government, Clinical Networks, Health Boards and other elements of the NHS Wales system.

  - Work is also undertaken with commissioned services to ensure compliance with Ministerial Priorities, Annual Planning Frameworks, Chair’s Priorities etc.

  - The EASC Model Standing Orders outline the expectation that safe, effective and timely services are delivered and that robust quality assurance and risk management systems support this.

  - The established EASC Management Group and Non-Emergency Patient Transport Services (NEPTS) and Emergency Medical Retrieval and Transfer Service (EMRTS Cymru) Delivery Assurance Groups are the key governance and assurance mechanisms that ensure robust collaborative partnership arrangements with key stakeholders.  These groups enable detailed oversight of delivery, performance and the strategic direction of commissioned services and are key elements of the collaborative commissioning approach adopted.

  - These arrangements ensure that health boards and commissioned services jointly plan and take collective action to deliver the Committee’s priorities. Collaborative partnership working and a whole system approach is at the heart of these arrangements, ensuring that there is appropriate challenge, collaboration and a drive to build on the learning and experiences across the system and to improve quality of care and patient outcomes.

  - These groups are tasked with enacting the commissioning responsibilities of the Committee to ensure the provision of safe, effective, equitable and sustainable services for the population of Wales.

- SPECIFIC MATTERS FOR CONSIDERATION BY THIS MEETING (ASSESSMENT)

  - The EASC Commissioning Update has been prepared to provide Members of the Committee with an overview of the progress being made against the key elements of the collaborative commissioning approach, these are:

EASC Commissioning Frameworks

  - The Emergency Ambulance Services Commissioning Framework was revised and approved during 2022 this included the enhancement of the collaborative commissioning approach with the development of local Integrated Commissioning Action Plans (ICAPs).

  - Work to review the Non-Emergency Patient Transport Services (NEPTS) Commissioning Framework will take place during quarter 1 and 2, with a revised framework issued at the end of Quarter 3 2023/24. This work will be led by the NEPTS Delivery Assurance Group and EASC Management Group will be updated through this report.

  - Work to review Emergency Medical Retrieval and Transfer Service Commissioning Framework will take place in quarter 4 2023/24 with a revised framework issued in Quarter 1 2024/25.

Integrated Commissioning Action Plans

  - The EASC Team have continued to progress with the development of the ICAPS, working with health boards and WAST to transition actions from the development to the delivery phase. To reflect the work being undertaken in the delivery phase, health boards and WAST have decided to include additional team members in the ICAP meeting process. The ICAPS are currently on version 4 with version 5 being available from May 2023.

  - Recognising that the work that has been achieved to date and now that the ICAPS have moved to a delivery phase, the EASC Team will be revising the frequency and approach to the ICAP meetings from May 2023.

  - An Internal Audit has been undertaken of the development of the ambulance handover improvement plans and the subsequent transition to the ICAP process. The final report is attached to this report (Appendix 1).

  - The audit provided substantial assurance on this work. With one low priority recommendation to strengthen the capturing of risk. This recommendation is being incorporated immediately into the ICAP meeting structure.

EASC Integrated Medium Term Plan (IMTP)

  - The EASC IMTP was approved by the Joint Committee at the March meeting and has been submitted to Welsh Government. The EASC team  presented to the Collective Review Group on the 27 April 2023.

  - The plan:

- sets out the Committee’s priorities for commissioned services to ensure that clinical risks are minimised and patient safety is improved through efficient and effective service delivery

- identifies a number of wider system work programmes to support transformation over the life cycle of this plan

- is consistent with those of the Welsh Ambulance Services NHS Trust, EMRTS Cymru and Health Boards

- ensures that Welsh Government requirements as defined within planning guidance, other national directives and national programmes are addressed

- confirms that the Committee will continue to adapt and respond to changing service models at a local, regional and national level.

  - The commissioning priorities are reflected in the EASC Commissioning Intentions.

  - The final EASC Integrated Medium Term Plan is attached to this report (Appendix 2) alongside the submission covering letter (Appendix 3).

  - EASC Commissioning Intentions: 2022-23

A quarter 4 update against the Commissioning Intentions for 2022-23 is included at Appendix 4 (EMS and NEPTS). The EMRTS Update will be provided following the next EMRTS Delivery Assurance Group. The update provides information relating to the current position and actions that have already been delivered along with next steps.

Members are asked to note:

EMS:

- CI (Commissioning Intention) 1-A1 Activity resolved at Step 2:  increase in hear and treat rates

- CI1-A2 Multiple responses at Step 3 and CI2-A3 Rosters aligned to demand: implementation of new rosters completed

- CI1-P1 Remote clinical support strategy: work required to develop remote clinical support strategy

- CI1-I2 Outcome by response type: the benefits of ePCR in enabling the collection and sharing of information in a more timely and accurate manner

- CI2-P1 Forecasting and modelling framework: delay of forecasting and modelling due to REAP4 and system pressures; appointment of new resource

- CI3-A1 Reducing post-production lost hours and CI3-P1 Modernising workplace practices: work currently paused due to industrial action (WAST)

- CI3-A2 Notification to handover time – the impact of significant handover delays

NEPTS:

- CI1b - Plurality Providers: Tender process complete.

- CI2a – Planning: working towards NET centre roster review

- CI2b – Demand Management: delays due to system pressures and industrial action

- KEY RISKS/MATTERS FOR ESCALATION TO THE COMMITTEE

  - Members are requested to note the progress being made in relation to commissioning and the role of the EASC Commissioning Cycle, EASC Commissioning Frameworks, EASC IMTP and EASC Commissioning Intentions.

  - The aim of this collaborative commissioning approach is to recognise the role of EASC in enabling commissioned services to support the wider urgent and emergency care system by:

- providing clear commissioning expectations

- ensuring a value-based approach which enables an equitable, sustainable and transparent use of resources to achieve better outcomes for patients

- facilitating the required collaborative and integrated commissioning as part of a system-wide response across the urgent and emergency care services system

- adopting a consistent commissioning process and approach and improved sharing of best practice, supporting sustainable service delivery and commissioning going forward

- supporting an improvement in service delivery, quality, patient safety and performance with a view always to optimise patient outcomes, patient safety and the patient experience.

  - This approach recognises the importance of timely engagement with key stakeholders in the wider urgent and emergency care system and the EASC Commissioning Cycle will be extended during the planning cycle to strengthen this.

  - Whilst the approach does set out the strategic priorities of the EAS Joint Committee, this is complemented by a focus on the delivery of operational improvements across the system in the short term and the inclusion of service deliverables and metrics.

  - This EASC Commissioning Update provides a position update against the different elements of the commissioning approach.

- IMPACT ASSESSMENT

| Quality/Safety/Patient Experience implications | Yes (Please see detail below) |
| --- | --- |
|  | The aim of the Commissioning Intentions and Frameworks to ensure safe and effective ambulance services for the people of Wales |
| Related Health and Care standard(s) | ALL are relevant to this report |
| Equality impact assessment completed | No (Include further detail below) An EIA will be completed on the Commissioning approach |
| Legal implications / impact | There are no specific legal implications related to the activity outlined in this report. |
| Resource (Capital/Revenue £/Workforce) implications / Impact | Yes (Include further detail below) |
|  | The Commissioning Intentions and Framework will have implications for resources including workforce |
| Link to Commissioning Intentions | The Committee’s overarching role is to ensure its Commissioning Strategy for Emergency Ambulance Services utilising the five step patient pathway outlined within the National Collaborative Commissioning Quality and Delivery Agreement and the related outcomes for each care standard aligned with the Institute of Healthcare Improvement's (IHI) ‘Quadruple Aim’ are being progressed. |
| Link to Main WBFG Act Objective | Provide high quality care as locally as possible wherever it is safe and sustainable |

- RECOMMENDATION

  - The Emergency Ambulance Services Committee is asked to:

- NOTE the collaborative commissioning approach

- NOTE the refresh plan for commissioning frameworks.

- NOTE the progress update on ICAPS

- NOTE the approval and submission of the EASC IMTP 2023-26 and the accompanying submission letter.

- NOTE the findings of the Internal Audit report

- NOTE the Quarter 4 update against the EASC Commissioning Intentions and the key priorities from the EASC IMTP 2022-25.