EMERGENCY AMBULANCE SERVICES COMMITTEE

EASC Assurance framework

Section 1 - Summary

| Risk no | Strategic / Principal Risk | Strategic Goal | Lead(s) for this risk | Assurance committee(s) | Current score | Trajectory |
| --- | --- | --- | --- | --- | --- | --- |
|  | Failure to produce agreed Commissioning Frameworks and commissioning intentions | Set the Strategic Commissioning plan | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee | 4 (C4xL1) |  |
|  | Failure to develop an agreed EASC IMTP for endorsement by the Joint Committee seeking approval from the Welsh Government | Meet the Ministerial direction to produce an EASC IMTP | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee | 4 (C4xL1) |  |
|  | Failure to deliver the Ministerial direction that EASC effectively plans, commissions and secures services within its remit; and failure to maintain collaborative relationship with providers | Effective Commissioning | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee | 15 (C5xL3) |  |
|  | Failure to respond to requirements identified within commissioned work related to the ambulance services | Outcome measurement | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee | 12 (C4xL3) |  |
|  | Failure to achieve the agreed Chair's objectives with the Minister | Ministerial direction | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee | 6 (C3xL2) |  |
|  | Failure to achieve agreed performance standard for category red calls which is 65% of calls responded to within 8 minutes | Securing safe ambulance services | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee Audit and Risk Committee | 25 (C5xL5) |  |
|  | Failure to achieve agreed performance standard for amber category calls | Securing safe ambulance services | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee Audit and Risk Committee | 25 (C5xL5) |  |
|  | Failure by the whole system, policy makers, commissioners and providers to utilise EASC in matters which relate to its areas of responsibility during times of escalation | Set the Strategic Commissioning Plan | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee Audit and Risk Committee | 8 (C4xL2) |  |
|  | Failure to take appropriate commissioning actions to support the provider in their management of patient safety and to minimise clinical risk during times of escalation | Effective Commissioning | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee Audit and Risk Committee | 20 (C5xL4) |  |
|  | Failure to receive timely and quality assured information for publication as a result of the transition to new information systems (ECNS, ePCR) | Outcome measurement | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee Audit and Risk Committee | 12 (C3xL3) |  |
|  | ‘New’ Failure to secure sufficient Ambulance capacity to meet the needs of the population | Effective Commissioning | Chief Ambulance Services Commissioner | Emergency Ambulance Services Committee Audit and Risk Committee | 25 (C5xL5) | New |

| CTMUHBs Risk Appetite Statement |  |
| --- | --- |
| CTMUHBs Risk Domain and Scoring Matrix |  |

Section 2	Strategic Risk Heat Map

Current risk scores in black

Target risk scores in grey italic

| Consequence | 5 |  | 3 |  | 9 | 6, 7, 11 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 |  | 4 / 4 | 8 / 6, 7 |  |  |
|  | 3 |  | 5 / 5,10 |  | 10 |  |
|  | 2 |  |  |  |  |  |
|  | 1 | 1,2 / 1,2,3,8,9 |  |  |  |  |
| CxL |  | 1 | 2 | 3 | 4 | 5 |
|  |  | Likelihood |  |  |  |  |

Section 3 –Strategic Risks

| Strategic Goal: Set the Strategic Commissioning plan |  |  | Risk score 4 |
| --- | --- | --- | --- |
| Strategic Risk: Failure to produce an agreed Strategic Commissioning plan and commissioning intentions (Risk No 1 / 4260) |  |  |  |
| If There is a failure to produce and agree Commissioning Frameworks and commissioning intentions | Then: The commissioned providers would not be clear regarding expectations for the quality, effectiveness and efficiency of services within an agreed financial plan. | Resulting in: Lack of clarity in the direction of the commissioned organisations (WAST and EMRTS) |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 4 | 1 | 4 |  |
| Current | 4 | 1 | 4 |  |
| Target | 4 | 1 | 4 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- |

| Controls | Assurances reported to Committee |
| --- | --- |
| Strategies and Plans Ensuring a program approach to planning and delivery with focus on monitoring progress through the EASC Sub Groups Governance Structures Regular reporting from EASC Sub Groups to the EAS Joint Committee on progress Forward look developed for all EASC Sub Groups including receiving progress on the deliverables within the plans Commissioning Processes - Commissioning Intentions collaboratively developed and agreed - Commitment from the EASC for strategic commissioning cycles - Ongoing work to refresh the EMS Commissioning Framework - Local integrated commissioning action plans (iCAPs) developed by HBs and WAST, process supported by EASC Team Improvement Programmes - To be confirmed | - Performance Report - EASC Commissioning Cycle for the development of Commissioning Intentions and Commissioning Frameworks agreed - Commissioning Intentions agreed for EMS, NEPTS and EMRTS monitored at each EASC Management Group (bi-monthly) meeting - Commissioning Frameworks enacted for all commissioned services Bi monthly reporting via report to EASC – the EASC Commissioning Update: - Commissioning Framework - Integrated Medium Term Plan - Commissioning Intentions |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | - EASC IMTP (confirmed as acceptable by WG with accountability conditions) - EASC Commissioning Cycle - EASC Commissioning Intentions - Minutes of EASC Sub Group meetings monitoring progress against plans - Commissioning Frameworks - Local Integrated Commissioning Action Plans developed in each health board |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |
| Six Goals of Urgent and Emergency Care 11. Percentage of total conveyances taken to a service other than a Type One Emergency Department |  |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |
| 4508 | Failure by the whole system, policy makers, commissioners and providers to utilise EASC in matters which relate to its areas of responsibility during times of escalation | 8 |

Click here to go back to the summary Section

| Strategic Goal: Meet the Ministerial direction to produce an EASC IMTP |  |  | Risk score 4 |
| --- | --- | --- | --- |
| Strategic Risk: Failure to develop an agreed EASC IMTP for endorsement by the Joint Committee seeking approval from the Welsh Government (Risk 2 / 4502) |  |  |  |
| If There is no agreement for the EASC IMTP | Then: The Commissioning Frameworks and commissioning intentions would not be supported | Resulting in: Lack of clarity in the direction of the commissioned organisations (WAST and EMRTS) |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 4 | 1 | 4 |  |
| Current | 4 | 1 | 4 |  |
| Target | 4 | 1 | 4 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- |

| Controls | Assurances reported to Committee |
| --- | --- |
| Strategies and Plans EASC IMTP 2022-2025 approved by EASC March 2022; EASC IMTP 2023-2026 drafted (February 2023) EASC IMTP (2020 to 2023) approved by EASC (January 2020) EASC Annual Plan 2021-22 approved EASC 9 March 2021 Governance Structures CASC Quality and Delivery meeting held monthly to discuss Quality and performance matters (under review) Detailed work to deliver EASC IMTP overseen by EASC Management Group Forward look developed for all EASC Sub Groups including receiving progress on the deliverables within the plans CASC IQPD (Integrated Quality and Performance Delivery) meeting with Welsh Government bi-monthly; CASC meetings with Welsh Government planning department Commissioning Processes - EASC IMTP 2022-25 submitted to Welsh Government with bi-monthly updates in-year Improvement Programmes - To be confirmed | Consistency between EASC IMTP with WAST IMTP and also with Health Boards; Awaiting letter of support from the Welsh Government; EASC Approval of the plan; Bi-monthly IMTP updates to EASC EASC IMTP 2022-2025 confirmed as acceptable by WG (with accountability conditions) |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | Bi monthly reporting via report to EASC – the EASC Commissioning Update: - Commissioning Framework - Integrated Medium Term Plan - Commissioning Intentions |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |

Click here to go back to the summary Section

| Strategic Goal: Effective Commissioning |  |  | Risk score 15 |
| --- | --- | --- | --- |
| Strategic Risk: Failure to deliver the Ministerial direction that EASC effectively plans, commissions and secures services within its remit; and failure to maintain collaborative relationship with providers (Risk No 3 /4503) |  |  |  |
| If The EASC fail to plan and secure services and maintain effective collaborative relationships with providers | Then: The purpose and effectiveness of the EAS Joint Committee would not be met | Resulting in: Potential Ministerial and Welsh Government intervention |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 5 | 1 | 5 |  |
| Current | 5 | 3 | 15 |  |
| Target | 5 | 1 | 5 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- |

| Controls | Assurances reported to Committee |
| --- | --- |
| Strategies and Plans - July 2021 Special meeting of EASC with Minister and clear expectations received - Minister meets with the Chair quarterly; - Meet regularly with providers to ensure continued development of open and transparent relationship - Governance Structures Regular reporting to the EAS Joint Committee on progress - Effective function of the EASC Joint committee - Independent Chair - Effective governance arrangements in place - CASC and Welsh Government IQPD meetings (bimonthly) - Model Standing Orders agreed for EASC Commissioning Processes - Agreed collaborative commissioning methodology - review and refine commissioning arrangements and refresh Commissioning Framework; Improvement Programmes - To be confirmed | - Internal and external audit - Welsh Government - EASC Committee members - Annual Governance Statement - Strategic Commissioning intentions and Commissioning Frameworks - Continued engagement with the commissioning process and EASC Governance - EASC Action Plan with monthly update to the Minister and review - Chairs appraisal letter with Minister - Integrated Commissioning Action plans – implementation plan agreed |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | - Commissioning framework and monitoring at EASC and its sub groups - Annual Governance Statement - Monitoring of EASC IMTP at EASC and sub groups - Review and refine governance arrangements - Maintaining close working and collaborative relationships during unprecedented system pressures - EASC action plan for Ministerial priorities and monthly monitoring return commitment including Integrated Commissioning Action Plans |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |
| 5005 | Failure to take appropriate commissioning actions to support the provider in their management of patient safety and to minimise clinical risk during times of escalation | 15 |

Click here to go back to the summary Section

| Strategic Goal: Outcome measurement |  |  | Risk score 12 |
| --- | --- | --- | --- |
| Strategic Risk: Failure to respond to requirements identified within commissioned work related to the ambulance services (Risk No 4 / 4504) |  |  |  |
| IF: Work commissioned is failed to be acted upon | Then: risks and issues identified will not be acted upon and implemented | Resulting in: a missed opportunity to improve services for patients |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 4 | 1 | 4 |  |
| Current | 4 | 3 | 12 |  |
| Target | 4 | 1 | 4 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- |

| Controls | Assurances reported to Board and committees |
| --- | --- |
| Strategies and Plans - Forward plan (Annual Business Plan) for EASC and all sub groups - Development of action plans which are received, endorsed and approved by the EASC for action - EASC IMTP confirmed as acceptable by WG with accountability conditions - EASC Action Plan and monthly monitoring return commitment Governance Structures - Forward plan (Annual Business Plan) for EASC and all sub groups - Regular review of Ambulance Service Indicators; Commissioning Processes - Commissioning intentions - including measurement across the system - Commissioner request for system wide measures - Refresh of Commissioning Frameworks Improvement Programmes - To be confirmed | - Amber Review - ORH Report D&C EMS - Emergency Ambulance Services Framework - updated and approved at EASC in September 2022 - McClelland Review of Welsh Ambulance Services (2013) - Internal and external audit - CASC IQPD meeting with Welsh Government - Annual Governance Statement |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | - Governance and planning for EASC and all sub groups and supporting meetings - review of the commissioning frameworks - EASC action plan and monthly monitoring return commitment |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |
| 5006 | Failure to receive timely and quality assured information for publication as a result of the transition to new information systems (ECNS, ePCR) | 9 |

Click here to go back to the summary Section

| Strategic Goal: Ministerial Direction |  |  | Risk score 6 |
| --- | --- | --- | --- |
| Strategic Risk: Failure to achieve the agreed Chair's objectives with the Minister (Risk No 5 / 4505) |  |  |  |
| IF: The agreed Chair's objectives with the Minister are not delivered | Then: Then the confidence of the Minister will be potentially compromised | Resulting in: The Minister not being assured that necessary progress has been made in the commissioning of ambulance services and the wider connections to unscheduled care services in Wales |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 3 | 2 | 6 |  |
| Current | 3 | 2 | 6 |  |
| Target | 3 | 2 | 6 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- |

| Controls | Assurances reported to Board and committees |
| --- | --- |
| Strategies and Plans - Cross reference to the work to deliver the Six Goals for Urgent and Emergency Care Programme and particularly Goal 4 Governance Structures - Regular meetings with the EASC team to discuss any issues as well as quality issues and the development of improved reporting arrangements Commissioning Processes - Regular meetings with the Minister Improvement Programmes - To be confirmed | Minister's response following Chair's appraisal Six Goals for Urgent and Emergency Care Programme delivery particularly Goal 4 Updated Chair’s Objectives received |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | - Commissioner support for commissioning - Commissioning intentions - Refresh Commissioning Frameworks - EASC IMTP - 'Focus on' sessions at EASC to discuss wider system issues |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |
| Six Goals of Urgent and Emergency Care 11. Percentage of total conveyances taken to a service other than a Type One Emergency Department |  |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |

Click here to go back to the summary Section

| Strategic Goal: Securing Safe Ambulance Services |  |  | Risk score 25 |
| --- | --- | --- | --- |
| Strategic Risk: Failure to achieve agreed performance standard for category red calls which is 65% of calls responded to within 8 minutes(Risk No 6 / 4506) |  |  |  |
| IF: The red performance level is less than 65% for each health board area and across Wales as a whole on a monthly basis | Then: The core target will be missed | Resulting in: Unsatisfactory service for the people of Wales (or within specific health board areas) with increased likelihood of harm, disability and death. |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 4 | 3 | 12 |  |
| Current | 5 | 5 | 25 |  |
| Target | 4 | 3 | 12 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee |  | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- | --- |

| Controls | Assurances reported to Board and committees |
| --- | --- |
| Strategies and Plans - The necessary resources secured in the EASC IMTP - performance monitoring on a daily basis and month to date position - EASC Action Plan includes detailed clinical review of red incidents to understand clinical need of patients to assess improvement opportunities Governance Structures - CASC monthly Quality and Delivery Meeting with the Welsh Ambulance Services NHS Trust - Bi monthly CASC IQPD meetings with Welsh Government Commissioning Processes - Commissioner element of EMS Demand and Capacity plan for additional staff supported Improvement Programmes - To be confirmed | - Ambulance Service Indicators - Daily weekly and monthly performance reports - Remedial Action plans (if required) - Specific targeted actions as required - Commissioner Ambulance Availability Taskforce - Implementation of the Demand and Capacity Review - EASC Action Plan including monthly submission and review - CASC liaison with Chief Operating Officers - Quality and Safety Report presented at every EASC meeting - Commissioner element of EMS Demand and Capacity plan for additional staff supported – implementation being monitored - Quality and Safety Report presented at every EASC meeting - Commissioner element of EMS Demand and Capacity plan for additional staff supported |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | - Delivery of EASC IMTP and WAST IMTP - Implementation of the commissioning intentions through the commissioning agreement - Role of the EASC Management Group to provide oversight on operational performance - Development of WAST performance improvement plan - Additional £3m investment in year to support front line services which will also support the commencement of the Cymru High Acuity Response Unit (CHARU) |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |
| Six Goals of Urgent and Emergency Care 11. Percentage of total conveyances taken to a service other than a Type One Emergency Department |  |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |
| 4507 | Failure to achieve agreed performance standard for amber category calls | 25 |

Click here to go back to the summary Section

| Strategic Goal: Securing Safe Ambulance Services |  |  | Risk score 25 |
| --- | --- | --- | --- |
| Strategic Risk: Failure to achieve agreed performance standard for category amber calls (Risk No 7 / 4507) |  |  |  |
| IF: The average time for amber performance calls does not reduce year on year | Then: Patients will not receive the care they need in a timely manner | Resulting in: unsatisfactory service for the people of Wales (or within specific health board areas with increased likelihood of harm, disability and death. |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 4 | 3 | 12 |  |
| Current | 5 | 5 | 25 |  |
| Target | 4 | 3 | 12 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- |

| Controls | Assurances reported to Board and committees |
| --- | --- |
| Strategies and Plans The necessary resources secured in the EASC IMTP/ Annual Plan EASC Action plan includes detailed clinical review of amber incidents to understand clinical need of patients to assess improvement opportunities - Governance Structures - performance monitoring on a daily basis and month to date position - CASC Monthly quality and delivery meetings with WAST - Bi monthly CASC Quality and Delivery meeting with Welsh Government - CASC monthly Quality and Delivery Meeting with the Welsh Ambulance Services NHS Trust Commissioning Processes - Commissioner element of EMS Demand and Capacity plan for additional staff supported Improvement Programmes - To be confirmed | - Ambulance Service Indicators - Daily weekly and monthly performance reports - Remedial Action plans (if required) - Specific targeted actions as required - Commissioner Ambulance Availability Taskforce - Implementation of the Demand and Capacity Review - EASC Action Plan for Minister including monthly submission and review - CASC liaison with Chief Operating Officers |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | - Delivery of EASC Annual Plan and WAST IMTP Implementation of the commissioning intentions through the commissioning agreement - Role of the EASC Management Group to provide oversight on operational performance - Development of WAST performance improvement plan - Weekly dashboard of management information developed and shared across NHS Wales to capture progress - Quality and Safety Report presented at every EASC meeting - Weekly dashboard shared across NHS Wales – sent to all EASC members and key senior NHS staff |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |
| Six Goals of Urgent and Emergency Care 11. Percentage of total conveyances taken to a service other than a Type One Emergency Department |  |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |
| 4506 | Failure to achieve agreed performance standard for category red calls | 25 |

Click here to go back to the summary Section

| Strategic Goal: Set the Strategic Commissioning plan |  |  | Risk score 8 |
| --- | --- | --- | --- |
| Strategic Risk: Failure by the whole system, policy makers, commissioners and providers to utilise EASC in matters which relate to its areas of responsibility during times of escalation (Risk No 8 / 4508) |  |  |  |
| If The system does not utilise the arrangements in place at EASC | Then: The governance and purpose of EASC will be undermined | Resulting in: a lack of consistency, duplication of services and resources, poor governance and non compliance with the Statutory Instrument leading to unnecessary system pressures |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 4 | 1 | 4 |  |
| Current | 4 | 2 | 8 |  |
| Target | 4 | 1 | 4 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- |

| Controls | Assurances reported to Committee |
| --- | --- |
| Strategies and Plans EASC IMTP developed and submitted (confirmed as acceptable by WG with accountability conditions) Governance Structures - Accountable officers are members of EASC - Memorandum of understanding and commitment from all EASC members - Model Standing Orders agreed and reviewed annually Commissioning Processes - Sharing information on service developments - Alignment to the 6 Goals for Urgent and Emergency Care Policy Steering Board - Commissioning Frameworks reviewed Improvement Programmes - To be confirmed | - Memorandum of understanding and commitment from all EASC members - Independent Chair - Governance arrangements - Commitment to collaborative nature of working - External audit - Welsh Government and Commissioner support for EASC - EASC Standing orders and Standing Financial Instructions - EASC Action Plan - Accountable officers of health boards are members of EASC - Sharing information on service developments - Alignment to the 6 Goals for Urgent and Emergency Care Programme Board - Model Standing Orders agreed and reviewed annually - Commissioning Frameworks reviewed |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | - Collaborative commissioning agreements - EASC Management group representing all organisations - Aligning EASC IMTP with WAST and Health board IMTPs - CASC meeting with Welsh Government planners - CASC IQPD meeting with Welsh Government - CASC Quality and Delivery meeting with WAST - Chair of EASC and CASC meetings with Health Boards - CASC Member of NHS Leadership Board |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |
| Six Goals of Urgent and Emergency Care 11. Percentage of total conveyances taken to a service other than a Type One Emergency Department |  |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |
| 4260 | Failure to produce an agreed Strategic Commissioning plan and commissioning intentions | 4 |

Click here to go back to the summary Section

| Strategic Goal: Effective Commissioning |  |  | Risk score 20 |
| --- | --- | --- | --- |
| Strategic Risk: Failure to take appropriate commissioning actions to support the provider in their management of patient safety and to minimise clinical risk during times of escalation (Risk No 9 / 5005) |  |  |  |
| If Commissioning actions are not taken to manage patient safety and minimise clinical risks | Then: Patients are more likely to come to harm | Resulting in: poorer patient outcomes and patient experience, increased SAIs, litigation and reputational damage |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 5 | 1 | 5 |  |
| Current | 5 | 4 | 20 |  |
| Target | 5 | 1 | 5 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- |

| Controls | Assurances reported to committee |
| --- | --- |
| Strategies and Plans EASC IMTP developed and submitted (confirmed as acceptable by WG with accountability conditions) Governance Structures - Discussion at EASC Committee - Discussion at EASC Management Group - CASC and WAST Quality & Delivery meeting - Agree red lines for handover delays to improve ambulance availability Commissioning Processes - Sought clarification from WAST re Equality Impact Assessment Improvement Programmes - To be confirmed | - WAST Equality Impact Assessment (to be completed - Commitment to collaborative nature of working and implementation of system-wide escalation policy - Ongoing discussions around system-wide escalation - Agree red lines for handover delays to improve ambulance availability - Securing of funding for emergency ambulance capacity - EASC Management Group agreed to set up two task and finish groups - Response to Healthcare Inspectorate Wales review related to handover delays - Appendix B |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | - Joint escalation plan developed and approved at NHS Leadership Board - Commissioning Operational Delivery Unit to avoid unilateral WAST decision-making - Provide necessary funding to WAST |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |
| 4503 | Failure to deliver the Ministerial direction that EASC effectively plans, commissions and secures services within its remit; and failure to maintain collaborative relationship with providers | 15 |

Click here to go back to the summary Section

| Strategic Goal: Outcome measurement |  |  | Risk score 12 |
| --- | --- | --- | --- |
| Strategic Risk: Failure to receive timely and quality assured information for publication as a result of the transition to new information systems (ECNS, ePCR) (Risk No 10 /5006) |  |  |  |
| IF: Timely and quality assured data is not provided | Then: EASC will be unable to publish data or assure itself of the quality of service provision | Resulting in: a lack of consistency and public confidence, duplication of services and resources, poor governance and noncompliance with reporting requirements set out in the commissioning framework |  |

|  | Consequence | Likelihood | Score | Risk Trend |
| --- | --- | --- | --- | --- |
| Inherent | 3 | 2 | 6 |  |
| Current | 3 | 3 | 9 |  |
| Target | 3 | 2 | 6 |  |
| Risk Appetite | Cautious (quality and safety; trust and confidence; legal and regulatory) |  |  |  |

| Risk Lead | - Chief Ambulance Services Commissioner | Assurance committee | - Emergency Ambulance Services Committee - CTMUHB Audit and Risk Committee (for assurance) |
| --- | --- | --- | --- |

| Controls | Assurances reported to Board and committees |
| --- | --- |
| Strategies and Plans EASC IMTP developed and approved subject to accountability conditions Governance Structures - Regular meetings with the project team to discuss any issues as well as with the clinical audit team around the development of reporting arrangements - Weekly dashboard of management information developed and shared Commissioning Processes - Commissioning updates provided to every EASC meeting Improvement Programmes - To be confirmed | - Ambulance Service Indicators - Daily weekly and monthly performance reports - Remedial Action plans (if required) - Specific targeted actions as required - Ambulance service indicator group recommenced |
| Gaps in Controls and Assurances | Actions and mitigations |
|  | - Provide oversight on operational performance - Implementation plans for new information systems (ECNS, ePCR |

| Linked National Priority Measures | Current Performance - Highlights |
| --- | --- |

| Associated Risks on the Organisational Risk Register |  |  |
| --- | --- | --- |
| Risk no. | Description | Current score |
| 4504 | Failure to respond to requirements identified within commissioned work related to the ambulance services | 12 |

Click here to go back to the summary Section