AGENDA ITEM

2.5

EMERGENCY AMBULANCE SERVICES COMMITTEE

UPDATE ON PROGRESS RELATED TO THE EMERGENCY MEDICAL RETRIEVAL AND TRANSFER SERVICE (EMRTS CYMRU) SERVICE REVIEW

| Date of meeting | 14/03/2023 |
| --- | --- |

| FOI Status | Open/Public |
| --- | --- |

| If closed please indicate reason | Choose an item. |
| --- | --- |

| Prepared by | Matthew Edwards, Head of Commissioning and Performance, EASC Team |
| --- | --- |
| Presented by | Lee Leyshon, Assistant Director Communications and Engagement, EASC Team |
| Approving Sponsor | Chief Ambulance Services Commissioner |

| Report purpose | FOR APPROVAL |
| --- | --- |

| Engagement (internal/external) undertaken to date (including receipt/consideration at Committee/group) |  |  |
| --- | --- | --- |
| Committee/Group/Individuals | Date | Outcome |
| EASC Management Group | 16 Feb 2023 | Noted |

| ACRONYMS |  |
| --- | --- |
| CASC EMRTS WAST | Chief Ambulance Services Commissioner Emergency Medical Retrieval and Transfer Service (EMRTS Cymru) Welsh Ambulance Services NHS Trust |

- SITUATION/BACKGROUND

  - The purpose of this report is to update Members on the progress made on the Emergency Medical Retrieval and Transfer Service (EMRTS) Service Development Proposal received by the Committee at the meeting on 8 November 2022.

  - At the meeting Members agreed that additional scrutiny would be undertaken in a number of key areas.

  - Members will recall that, given the above requirements and the challenges raised both by Committee members, members of the public, politicians, Community Health Council members and community groups; and in order to avoid protracted discussions over the process, content and transparency of the original proposal, the EASC Team undertook to begin the process of undertaking this EMRTS Service Review afresh.

  - Further updates have been provided at subsequent meetings of the Committee.

- SPECIFIC MATTERS FOR CONSIDERATION BY THIS MEETING (ASSESSMENT)

EMRTS Service Review

  - The EMRTS Service Review (undertaken by the EASC Team) will be independent of the assumptions, comparisons and modelling included within the original proposal.

  - At the EASC meeting held on 6 December 2022, Members received the report on the next steps regarding the process around delivering improvements to the Emergency Medical Retrieval and Transfer Service.

  - Members noted the paper that described the current service provision and the historical activity that has been delivered. Four areas related to base activity were focused on:

- Geographical coverage

- Rapid Response Vehicle Usage (RRV)

- Utilisation

- Unmet need.

  - Members noted that each area had indicated an opportunity to explore service improvement, particularly the level of utilisation.

  - Whilst Members noted that both Caernarfon and Welshpool bases experienced levels of utilisation far below Llanelli and Cardiff it was agreed that an element of this would be related to rurality and population density.  However, low levels of utilisation suggest that the service could be provided more efficiently.

  - When combined with unmet need this demonstrates that the service could potentially do more within its existing resource if changes took place to increase utilisation.

  - Members agreed to explore and maximise the additional activity that could be achieved from existing bases; they also agreed to explore how options to reconfigure the service could increase the number of patients receiving a service from EMRTS.

  - The report also provided clarity on the role and purpose of modelling, and Members noted that any modelling outputs should act as an adjunct for decision making, not as a sole determinant; they are a guide to a potential future state that could be delivered.

  - As per the request at the last meeting, activity data from 2022 and weather probability information has been integrated into the modelling system, in preparation for further scenario modelling.

Formal Public Engagement Process

  - Ahead of further modelling, Members agreed the need to engage upon the constraints, investment objectives and weightings as part of Phase 1 of the formal engagement process.  It was agreed that those applied as part of the decision-making process for the EMRTS 24/7 Service Expansion Review would also be appropriate for this present review.

  - At the December 2022 meeting of EASC, it was agreed that the EASC Team would need to work closely with health board engagement, communication and service change leads and with Community Health Council (CHC) colleagues in the development and agreement of appropriate engagement materials including the engagement document and the stakeholder engagement timetable.

  - It was agreed that the formal public engagement process could commence, subject to agreement of engagement materials by health boards and CHCs.  This process would include:

# Phase 1: Explain how the current service works, test the constraints, investment objectives and weightings

# Review after six weeks, agree options to be modelled

# Phase 2: Undertake the modelling and use to inform a robust option appraisal process using the agreed investment objectives and weightings

# Recommendation to EASC Members.

  - Members approved Chair’s Action to commence the formal engagement process once engagement materials were agreed by all parties but not before 9 January 2023.

  - Since the last Committee meeting, Members will be aware that the Wales Air Ambulance Charitable Trust announced (February 22, 2023) its new aviation partner as Gama Aviation Plc that successfully bid for the seven-year contract to provide aviation services to the air ambulance in Wales, starting on January 01, 2024. The Charity also confirmed that it is extending its contracts with Caernarfon Airport and Welshpool Airport, where two of its operations are currently based, until 2026, as detailed on their website.

  - Notwithstanding the Charity’s announcement, there is still a requirement for the CASC to undertake the EMRTS Service Review in order to make sure that the patients who need this important critical care service can have access to it no matter where they live in Wales or when they need it.  Given that EMRTS saves lives and that patients who are treated by EMRTS recover better and quicker, the impartial Review by the CASC will proceed to consider how as many people as possible in Wales could benefit from this service, as well as considering the most effective use of clinical skills, and other resources, as per the formal Committee decision aforementioned in 1.1.

# Engagement Materials

  - The EASC Team has continued to work with health board engagement, communication and service change leads in finalising the required core engagement materials.

  - These core documents were shared with CHC colleagues, to test the initial drafts and comments have been received and considered recognising the level of detail needed to clarify complex information.

  - Given the high level of public interest (in specific areas) in the service and in taking part in the engagement process, a substantial amount of information has now been published on the EASC website in readiness for the engagement process.  This has taken account of information, queries and misinformation in order to clarify the facts for participants recognising the technical and service operational complexities that need to be conveyed.

  - It is recognised how important it is that complex information is set out as clearly as possible in order for the engagement dialogue to be clear and constructive. The EASC team has been actively seeking ongoing feedback about how this can be continually improved to ensure this engagement is as meaningful as possible for all involved.

  - Notwithstanding the importance of the pre-engagement readiness phase, and whilst recognising the urgency to get the engagement phase underway, equally, there is a need to get this process right and to ensure that plenty of notice is provided to ensure that those that want to participate are provided with the opportunity to do that.  Appreciating that the engagement timescales have changed to what were originally thought were deliverable, the commitment remains in ensuring this is a robust and transparent engagement process, and as such the need to get the detail right. The time needed for practical logistics and mechanics has been acknowledged in ongoing dialogue with key stakeholders who have been supportive in the planning of activities.

  - An external supplier is currently being secured to undertake the data collation, analysis and reporting, to include representative sample focus group engagement, that will complement the engagement activities already being developed by the EASC team.

EASC Team Resource

  - The impact of service pressures on the capacity of the EASC team has been reported to Members at previous meetings of the Committee.

  - The Committee agreed to consider providing temporary additional support as formal public engagement is commenced. The Chief Ambulance Services Commissioner wrote to health boards to explore how dedicated resource could be secured and this was agreed in mid-January.

  - Lee Leyshon joined the EASC Team on January 30, 2023 from Cwm Taf Morgannwg University Health Board on secondment as Assistant Director Communications and Engagement to lead the engagement process.

  - This key role will plan and co-ordinate the engagement and communications activities working with Comms and Engagement leads across all organisations involved.

  - Whilst the capacity of the EASC team to support the engagement on this work and maintain the business as usual commissioning arrangements for all EASC commissioned services has been impacted since taking on this item, the recent appointment of the Assistant Director Communications and Engagement has provided further momentum on arranging the formal public engagement process.

  - Additional specialist resource is also being secured for data collation, analysis and reporting as detailed earlier.

Activities and Engagement Update

2.29 	The Plan can be summarised as below, based on 3 key activity phases:

| Phase | Stage | Purpose | Timing |
| --- | --- | --- | --- |
| 0 | Brief (We are asking…) | Pre-engagement phase to aid understanding and create optimal conditions for engagement dialogue in Phase 2. | October 2022 – March 2023 |
| 1 | Engage (You are telling us…) | Gathering of feedback on factors, weightings, and other suggestions to inform Options. | March-May 2023 |
| 2 | Share (We are doing…) | Outline of Options from Phase 2 to explain Options going forward to EASC for decision. | June-July 2023 |

Phase 1 approach to include:

- Online and print questionnaire

- Representative samples focus groups

- In person and virtual public meetings focused on targeted areas particularly where there is strong interest in the original EMRTS Service Development Proposal.

- Raising awareness with all identified stakeholders to encourage syndication through their channels

- Offering of meetings via extant infrastructures of:

  - CHCs/CVB (from April 01, 2023)

  - HB SRGs

  - Local Authorities

  - One Voice Wales

- Reactive engagement by responding to requests for information

Core bilingual engagement documents pack:

- Full technical document

- Everyday summary document

- Easy read document

Supplementary materials:

- FAQs (agile)

- Presentation slides

- Video explainer of services

- Signposting to organisational websites and formal corporate documents (annual reports and plans etc.)

  - Efforts of the CASC and EASC team have continued to build trust and confidence in the CASC as impartial facilitator of the engagement and thereby the process itself.

  - The EASC Team has continued to meet with stakeholders, these have been in person, via Microsoft Teams, emails and phone calls.  Stakeholders have included:

- Health Board Communication and Engagement Leads (weekly)

- EASC Team and CSAM Optima – meeting to discuss modelling process, weather etc (6 January)

- Face to face meetings as part of continuous engagement with interested stakeholders

- Updating Community Health Councils (CHCs) and subgroups

- Informal meetings with politicians

- Various journalists and media outlets.

- FAQ feedback collated, updated, and published

- More detailed stakeholder mapping completed, and assets developed

- Engagement programme visual identity finalised

- Extant website housekeeping completed with the Charity and EMRTS to clarify some of the misunderstanding that has emerged.

- Dedicated webpages for the Service Review https://easc.nhs.wales/engagement/sdp/ have been launched to include:

- Enhanced FAQs https://easc.nhs.wales/engagement/sdp/frequently-asked-questions/

- A video explainer https://youtu.be/KMPoUanPalE

- Updated Briefings archive

- Queries e-form https://easc.nhs.wales/engagement/sdp/

- Dedicated e-mail address

- Dedicated answerphone service (being finalised).

  - As at 07 March 2023, 107 comments and questions have been submitted by stakeholders via the online contact / feedback form on the dedicated page on the EASC website or by email.  Each stakeholder has been informed that they will be added to the stakeholder list so that we can keep them informed as the work progresses, with a request that they let us know if they wish to be removed from the list (in line with information governance requirements).

  - Briefing Notes 5 and 6 have been circulated to stakeholders and published (26 January and 7 March 2023) on the EASC website providing updates regarding discussions at EASC Committee meetings, next steps to be undertaken, and additional information available about how the services works now, the need for an engagement process, and what the engagement process will involve.

  - The Chief Ambulance Services Commissioner (CASC) has provided an update to CHC lead representatives since the last meeting, clarifying a process of scrutiny that is independent of the assumptions, comparisons and modelling included within the original EMRTS Service Development Proposal. CHC colleagues have provided support and advice on the engagement materials (ensuring the required public perspective) and the handling of meetings that continue to inform the engagement planning and development.

  - Weekly meetings continue to be held with health board communication and engagement leads. These meetings have been extremely productive and have helped to clarify realistic timelines for developing appropriate engagement materials and have also confirmed the expertise and infrastructure available within health boards to support the process ahead, to explore local arrangements and to agree robust methodology and engagement materials.

  - It is the expectation that each health board will support the engagement in their areas including sharing through normal practice and existing networks, ensuring inclusion on key meetings and using digital and social media channels.

  - The team continue to liaise with the Board Secretary/Directors of Governance to ensure that the work is also included for health board public meetings.

  - All updates related to the EMRTS Service Review will continue to be published on the EASC website as this work progresses.

- KEY RISKS/MATTERS FOR ESCALATION TO THE COMMITTEE

  - Significant public and political concerns continue to be raised around any proposed changes to the operation of the EMRTS and the Wales Air Ambulance Charity (WAAC), particularly in relation to the potential closure of bases. This has resulted in challenges for the Committee, EMRTS and the Charity.

  - Members are asked to consider and discuss the above risks.

- IMPACT ASSESSMENT

| Quality/Safety/Patient Experience implications | Yes (Please see detail below) |
| --- | --- |
|  | Specific areas identified will impact quality safety and patient experience matters – although how the service is provided to patients is not changing |
| Related Health and Care standard(s) | Governance, Leadership and Accountability |
|  | All health and care standards apply. |
| Equality impact assessment completed | Not required |
| Legal implications / impact | There are no specific legal implications related to the activity outlined in this report. |
| Resource (Capital/ Revenue £/Workforce) implications / Impact | Yes (Include further detail below) |
|  | There are ongoing implications which are identified within the report |
| Link to Main Strategic Objective | The Committee’s overarching role is to ensure its Commissioning Strategy for Emergency Ambulance Services utilising the five step patient pathway outlined within the National Collaborative Commissioning Quality and Delivery Agreement and the related outcomes for each care standard aligned with the Institute of Healthcare Improvement's (IHI) ‘Quadruple Aim’ are being progressed. This report focuses on all the above objectives, but specifically on providing strong governance and assurance. |
| Link to Main WBFG Act Objective | Provide high quality care as locally as possible wherever it is safe and sustainable |

- RECOMMENDATION

  - Committee Members are asked to:

- NOTE the appointment of dedicated engagement and communication expertise

- NOTE that the EASC Team continue to work with health board engagement, communication and service change leads to commence the engagement process

- NOTE the testing, development and publishing of content and engagement materials in preparation for the engagement process;

- NOTE the activities and pre-engagement work undertaken since the previous meeting including the engagement timetable of sessions currently being arranged

- NOTE the pending proposal for external supplier support to undertake data collation, analysis and reporting to include a representative sample

- APPROVE the commencement of the formal engagement process, straight away following the EASC meeting on March 14, 2023.