Agenda Item

2.1

Emergency Ambulance Services Committee

PERFORMANCE REPORT

| Dyddiad y Cyfarfod / Date of Meeting | 19/03/2024 |
| --- | --- |
| Statws Cyhoeddi / Publication Status | Open/ Public |
|  | Not Applicable |
| Awdur yr Adroddiad / Report Author | Phill Taylor, Head of Commissioning & Performance |
| Cyflwynydd yr Adroddiad / Report Presenter | Ross Whitehead, Deputy Chief Ambulance Services Commissioner |
| Noddwr Gweithredol yr Adroddiad / Report Executive Sponsor | Stephen Harrhy, Chief Ambulance Services Commissioner |

| Pwrpas yr Adroddiad / Report Purpose | For Noting |
| --- | --- |

| Engagement (internal/external) undertaken to date (including receipt /consideration at Committee/Group) |  |  |
| --- | --- | --- |
| Committee / Group / Individuals | Date | Outcome |
| N/A |  | Noted |

| Acronyms / Glossary of Terms |  |
| --- | --- |
| CASC DAG EMRTS IQPD NEPTS WAST WG EMS | Chief Ambulance Services Commissioner Delivery Assurance Group Emergency Medical Retrieval and Transfer Service Integrated Quality, Planning and Delivery Meeting Non-Emergency Patient Transport Service Welsh Ambulance Services NHS Trust Welsh Government Emergency Medical Services |

- SITUATION/BACKGROUND

  - The purpose of the report is to present to EASC Members the most recent publication of the:

- Ambulance Service Indicators (ASIs) – Attached at Appendix 1

- EASC Performance Dashboard – Attached at Appendix 2.

- SPECIFIC MATTERS FOR CONSIDERATION BY THIS MEETING (ASSESSMENT)

Ambulance Service Indicators

  - The narrative and overview document for the latest reporting period – January 2024 is available at Appendix 1.

  - Full access to the ASI information for all publication is available at https://easc.nhs.wales/asi/asipublicnarrative/

EASC Performance Dashboard

  - The Performance Dashboard is available at Appendix 2.

  - The dashboard presents time series information across a number of periods, including daily, monthly and annual time periods.

  - Of particular note within the dashboard for this reporting period:

- 999 call volumes in January 2024 were 20.1% higher than January 2023.

- 17.5% increase in incidents in January 2024 compared to January 2023

- Hear and Treat levels are 0.75% lower in January 2024 compared to January 2023

- Red incidents increased by 8.3% between November 2023 and January 2024 and have increased by 21.9% between January 2023 and January 2024.

- Amber incidents in January 2024 were 10% higher compared to January 2023.

- Ambulance handover lost hours in January 2024 were 13.9% higher compared to January 2023. In 2023, some improvements were made on a number of metrics, % handed over in 15 min and handovers over 4 hours. Between November 2023 and January 2024 there has been a 34.2% increase in handover lost hours.

EASC Action Plan

  - Following receipt of confirmation of the EASC IMTP 23/26 from Welsh Government officials, further revisions to the EASC Action Plan were required (letter shared at the EASC Joint Committee meeting on 21 November 2023).

  - At the EASC Joint Committee meeting on 21 November 2023, members approved the revised approach to the EASC Action Plan, with future actions (2024/25) will be delivered through the Integrated Commissioning Action Plans (ICAPs).

Immediate Release Requests

  - The EASC team have continued to work with health boards and WAST in the development and delivery of recommendations from the immediate release request task and finish group.

  - A development and delivery plan has been established for the delivery of the recommendations. WAST has made notable progress in the delivery of WAST related actions but further work is required with health boards and the 6 Goals for Urgent and Emergency Care for all health board related actions.

  - The recommendations are aligned to all areas of the immediate release request process but health boards had raised specific concerns regarding the validation of immediate release request data. The work has now reviewed and updated the validation process. Via the task and finish group, health boards have reported recognised improvements in the validation process and that there is now confidence in the quality of data being produced.

  - All recommendations and actions are planned to be completed by Q2 24/25. Future updates on this work will be presented to the new JCC.

Statistical Process Control (SPC) Charts

  - Following feedback received from the meeting in December 2023 SPC charts provided at Appendix 3 will now form part of standard performance reporting.

Integrated Commissioning Action Plans (ICAP)

  - In line with the requirements set out in the IMTP response letter, and as approved by members at the November Joint Committee meeting, the ICAPs are undergoing a review to reflect the challenges in 2023/24 and the requirement set out within the letter.

  - A revised draft will be shared through ICAP meetings and EASC Management Group for comment and amendments prior to submission to the Committee.

  - The actions contained within ICAPs have been jointly analysed and remain appropriate for the delivery of improved ambulance services.

  - It is recognised that ICAP actions are aligned to all goals of the Six Goals for Urgent and Emergency Care Programme. ICAP actions contribute to improvements in ambulance handover delays and wider system improvements through improved delivery of services between health boards and WAST.

  - At the NHS Leadership Board meeting on the 20 December 2023, Welsh Government representatives requested that all health boards provide an update on the top 2/3 key actions being taken by each health board, to reduce ambulance handover delays.

  - All health boards have provided an update on their key actions and are included in Appendix 4.

  - The EASC Team will continue monitor progress against these key actions via the ICAP meetings.

EASC IMTP Performance Improvements and Enablers Tracker

  - The 2023-26 EASC IMTP set out a number of performance improvement ambitions and performance enablers for Emergency Ambulance Services. Appendix 5, provides a slide deck that sets out the progress to date against each of the commitments.

- KEY RISKS/MATTERS FOR ESCALATION TO THE COMMITTEE

  - Whilst some improvements are being made, Members will note that within the ASIs and the Performance Dashboard there are a number of areas of concern regarding response performance and lost hours and the resulting impact on patient care.

- ASSESSMENT

| Objectives / Strategy |  |
| --- | --- |
| Dolen i Nod (au) Strategol BIP CTM / Link to CTMUHB Strategic Goal(s) | Improving Care |
|  | If more than one applies please list below: |
| Dolen i Feysydd Strategol BIP CTM / Link to CTMUHB Strategic Areas | Living Well |
|  | If more than one applies please list below: |
| Dolen i Ddeddf Llesiant Cenedlaethau'r Dyfodol – Nodau Llesiant / Link to Wellbeing of Future Generations Act – Wellbeing Goals 150623-guide-to-the-fg-act-en.pdf (futuregenerations.wales) | A Healthier Wales |
|  | If more than one applies please list below: A more equal Wales |
| Dolen i Hwyluswyr Ansawdd (Canllawiau Statudol Dyletswydd Ansawdd (llyw.cymru)) / Link to Enablers of Quality (Duty of Quality Statutory Guidance (gov.wales)) | Data to Knowledge |
|  | If more than one applies please list below: Whole systems perspective Leadership Learning, improvement and research |
| Dolen i Feysydd Ansawdd (Canllawiau Statudol Dyletswydd Ansawdd (llyw.cymru)) / Link to Domains of Quality (Duty of Quality Statutory Guidance (gov.wales)) | Effective |
|  | If more than one applies please list below: Efficient Equitable Patient centred Timely Safe |
| Effaith Amgylcheddol/ Cynaliadwyedd (5R) / Environmental /Sustainability Impact (5Rs) | No - Not Applicable |
|  | If more than one applies please list below: |

| Impact Assessment |  |  |
| --- | --- | --- |
| Ansawdd Ydych chi wedi ymgymryd â Sgrinio Asesiad o’r Effaith ar Ansawdd? / Quality Have you undertaken a Quality Impact Assessment Screening? | Yes: ☐ | No: ☒ |
|  | Outcome: | If no, please include rationale below: Reporting on performance matters from last EASC meeting. |
| Cydraddoldeb Ydych chi wedi ymgymryd â Sgrinio Asesiad o'r Effaith ar Gydraddoldeb? / Equality Have you undertaken an Equality Impact Assessment Screening? | Yes: ☐ | No: ☒ |
|  | Outcome: | If no, please include rationale below: Reporting on performance matters and the impact on the wider health system. Quality and safety matters also considered. |
| Cyfreithiol / Legal | There are no specific legal implications related to the activity outlined in this report. |  |
| Enw da / Reputational | Yes (Include further detail below) |  |
|  | Ambulance performance of significant concern to the public and impacts on health boards reputation |  |
| Effaith Adnoddau (Pobl /Ariannol) / Resource Impact (People / Financial) | There is no direct impact on resources as a result of the activity outlined in this report. |  |

5.	RECOMMENDATION

  - The Emergency Ambulance Services Committee is asked to:

- NOTE the content of the report

- NOTE the Ambulance Services Indicators

- DISCUSS and NOTE the information within the performance dashboard

6.	NEXT STEPS

  - New arrangements for the Joint Committee will be in place for the next meeting and the spotlight on performance will need to be maintained.