|  | AGENDA ITEM 3.2 10 September 19 |
| --- | --- |

Emergency Ambulance Services Committee Report

1% A HEALTHIER WALES COMMISSIONING ALLOCATION 2019/20

| Executive Lead: | Julian Baker, Director Collaborative Commissioning |
| --- | --- |
| Author: James Rodaway |  |
| Contact Details for further information: James.Rodaway@wales.nhs.uk |  |

Purpose of the Emergency Ambulance Services Committee Report

The purpose of this report is to provide EASC with an update on progress on the proposals agreed through the Healthier Wales Awarding & Evaluation Panel (HWAEP) on the EASC 1% ‘A Healthier Wales’ Commissioning Allocation 2019/20 and ongoing evaluation.

| Governance |  |
| --- | --- |
| Link to the Commissioning Agreement | The Committee’s overarching role is to ensure its Commissioning Strategy for Emergency Ambulance Services utilising the five step patient pathway outlined within the National Collaborative Commissioning Quality and Delivery Agreement and the related outcomes for each care standard aligned with the Institute of Healthcare Improvement's (IHI) ‘Quadruple Aim’ are being progressed. This report focuses on all the above objectives, but specifically on providing strong governance and assurance. |
| Supporting evidence | The Collaborative Commissioning Quality and Delivery Framework for Emergency Medical Services |
| Engagement – Who has been involved in this work? |  |
| Chair of EASC, CASC, NCCU, all HBs, C3 Faculty Swansea University |  |

| Emergency Ambulance Services Committee Resolution to: |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| APPROVE |  |  | ENDORSE | √ | DISCUSS | √ | NOTE |  |
|  | The Emergency Ambulance Services Committee is asked to: - ENDORSE: the Chairs action on the advice of the Healthier Wales Awarding Evaluation Panel (HWAEP) for the Green and rejected submissions. - DISCUSS: the next steps of the Amber + & - submissions to progress the potential Chair’s actions contained within Appendix 1 & 2 in light of the emerging financial and service delivery risks around Emergency Ambulance Services. (WAST Relief Gap Paper & EASC: Reference Document circulated to EASC Members in August 19.) |  |  |  |  |  |  |  |
| Summaries the Impact of the Emergency Ambulance Services Committee Report |  |  |  |  |  |  |  |  |

| Equality and diversity | There are no implications arising directly from this report. |
| --- | --- |
| Legal implications | There are no implications arising directly from this report. |
| Population Health | No impact |
| Quality, Safety & Patient Experience | Ensuring the Committee and its Sub Groups make fully informed decisions is dependent on the quality and accuracy of the information presented and considered by those making decisions. Informed decisions are more likely to impact favorably on the quality, safety and experience of patients and staff. |
| Resources | No direct impact |
| Risks and Assurance | Identified within the report. |
| Health & Care Standards | The 22 Health & Care Standards for NHS Wales are mapped into the 7 Quality Themes: Staying Healthy; Safe Care; Effective Care; Dignified Care; Timely Care; Individual Care; Staff & Resources http://www.wales.nhs.uk/sitesplus/documents/1 064/24729_Health%20Standards%20Framework _2015_E1.pdf The work reported in this summary and related annexes take into account many of the related quality themes in particular timely care. |
| Workforce | Identified within the report. |
| Freedom of information status | Open |

1% A HEALTHIER WALES COMMISSIONING ALLOCATION 2019/20

1.	   SITUATION / PURPOSE OF REPORT

The purpose of this report is to update EASC on the progress made since the committee meeting July 19 on the EASC 1% ‘A Healthier Wales’ Allocation.

This report asks EASC to:

- ENDORSE: the Chairs action on the advice of the Healthier Wales Awarding Evaluation Panel (HWAEP) for the Green and rejected submissions.

- DISCUSS: the next steps of the Amber + & - submissions to progress the potential Chair’s actions contained within Appendix 1 & 2 in light of the emerging financial and service delivery risks around Emergency Ambulance Services.  (WAST Relief Gap Paper & EASC: Reference Document circulated to EASC Members in August 19.)

2.  BACKGROUND / INTRODUCTION

The 1% ‘A Healthier Wales’ funding is provided to support additionality as clarified by the Welsh Government in correspondence dated 18 January 2019, with their expectations that:

- Evidence is provided to demonstrate this additional allocation is used to secure further service provision

- EASC discusses with the Welsh Ambulance Services NHS Trust (WAST) how this additional funding can be best utilised to further improve performance and outcomes

- The Welsh Government is advised in due course on the detail of the additional service provision which has been funded.

At the meeting of EASC in March 2019, the Committee discussed and approved the proposed use of the 1% ‘A Healthier Wales’ funding commissioning allocation for WAST.

At the July 19 meeting of EASC discussed and approved:

- The recommendations of the HWAEP Chair by correspondence following the HWAEP Panel discussion on the 26th July 19.

- The EASC 1% A Healthier Wales additionality funding to develop and enable evaluation of NPUC Winter Funded and 1% A Healthier Wales initiatives across HBs & WAST.

- Funding from the 2019/20 1% A Healthier Wales allocation to recruit a band 6 researcher to fully support the design of the evaluation framework and delivery of evaluation against the Quadruple Aim.

3.   ASSESSMENT / GOVERNANCE AND RISK ISSUES

The EASC Management Group met on the 12 July 2019 to discuss the 23 submissions received by WAST & Health Boards. The Management Group categorised the bids into National and Local ahead of the HWAEP.

The HWAEP panel met on 26 July 2019 to review the 23 submissions received by WAST & Health Boards.

The submissions were categorised into the following categories:

- Green: required level of information and relevance within the bid for immediate approval.

- Amber +: Bid approved for funding following HWAEP actions being implemented or provided.

- Amber -: Bid approved for funding following HWAEP actions being implemented or provided.

- Further work needed: These were submitted as ‘local projects’ but have the potential to be scaled up nationally. Further discussions to take place around these areas.

- Rejected: Rejected by the panel as they did not meet the criteria, worthwhile exploring other sources of funding (external and internal) in order to progress further.

Chairs Action on HWAEP Submissions

The HWAEP panel has met and reviewed the submissions. It was agreed at EASC 23 July 19 that following the panel meeting, the bids would be signed off through Chairs action. The following appendices contain a summary of the bids and Chair’s Action and a summary of the associated finances.

- Appendix 1: 1% Healthier Wales Awarding Evaluation Panel, Summary of shortlisted bids & actions.

- Appendix 2: 1% HWAEP financial summary of shortlisted bids & actions.

The HWAEP requested supplementary information to finalise the bids and progress to delivery. The supplementary information is included in full in the following appendices:

- Appendix 3: Mental Wellbeing By Design - enabling colleagues to sustain a longer, more fulfilling, healthier and happier working life

- Appendix 4: Transport solutions: Right transport, right patient, right time

- Appendix 5: Intelligence Led Joint Response Unit Pilot (WAST and Police)

- Appendix 6: Shifting left on mental health and crisis care – building a more responsive workforce and a more efficient response

- Appendix 7: Welsh Ambulance Service NHS Trust - Volunteer Strategy

Monitoring financial performance

NCCU will monitor and report the financial performance of these initiatives to EASC. Any slippage in available funding will be utilised as a commissioning allocation in line with the principles agreed for HWAEP and service continuity for EASC commissioned services.

EASC Priorities

An allocation of £150k was listed in the EASC IMTP to support the 24/7 expansion of EMRTS.

EASC are asked to discuss the potential Chair’s actions for the Amber + & - submissions in light of the emerging financial and service delivery risks around Emergency Ambulance Services (WAST Relief Gap Paper & EASC: Reference Document circulated to EASC Members in August 19.)

4.   RECOMMENDATION

Members of the Emergency Ambulance Services Committee are asked to:

- ENDORSE: the Chairs action on the advice of the Healthier Wales Awarding Evaluation Panel (HWAEP) for the Green and rejected submissions.

- DISCUSS: the next steps of the Amber + & - submissions to progress the potential Chair’s actions contained within Appendix 1 & 2 in light of the emerging financial and service delivery risks around Emergency Ambulance Services. (WAST Relief Gap Paper & EASC: Reference Document circulated to EASC Members in August 19.)

| Freedom of information status | Open |
| --- | --- |

Appendix 1: 1% ‘A Healthier Wales’ Awarding Evaluation Panel, Summary of shortlisted bids & actions

Green Category:

| Reference | Organisation | Title | Lead | HWAEP Actions | Chairs Action |
| --- | --- | --- | --- | --- | --- |
| WAST5 | Welsh Ambulance | The Welsh Ambulance Services NHS Trust (WAST) Older Peoples Framework: making better decisions with Older People by bringing additionality to the older people we come into contact with in the community | Rachel Marsh | - Final Figure to be determined - Make clear what are we expecting WAST to delivery in the future with this scheme - Identify any gaps in the system, and the impact - Possible considerations around it being a joint appointment, and to reconsider the analyst function | - Approved - WAST to recruit lead but delay recruitment of other posts until Lead is in post. |
| WAST6 | Welsh Ambulance | Mental Wellbeing By Design - enabling colleagues to sustain a longer, more fulfilling, healthier and happier working life | Rachel Marsh | - Final Figure to be determined - Supportive in principle, however considerations are needed around delivery model e.g. job roles and possibilities of buying in this service | - Approved |

Amber + Category:

| Reference | Organisation | Title | Lead | Actions | Chairs Action |
| --- | --- | --- | --- | --- | --- |
| WAST1 | Welsh Ambulance | Transport solutions: Right transport, right patient, right time | James Rodaway / Mark Harris / Nicola Bowen | - Needs further clarity surrounding outcomes and benefits to patients. - Also clarification around outputs - Finalise costings - What would ongoing costs be? What level of support is required etc. (Initial start-up costs, and longer term running costs) | Awaiting Decision |
| WAST2 | Welsh Ambulance | Falls Response Model- Providing a timely, appropriate and proportionate response to patients who have fallen | Rachel Marsh | - Should this be managed from within WAST? - Currently operating hours 12hrs, 7 days, are we targeting at the right time? Review what the optimum hours would be? - How will other falls resources be affected? | Awaiting Decision |
| WAST3 | Welsh Ambulance | Intelligence Led Joint Response Unit Pilot (WAST and Police) | Rachel Marsh | - Needs further clarification in terms of: 1) Funding commitments 2) Evaluation process – who would lead? 3) Governance structures for a JRU - What additional benefits would this service bring to the NHS (as opposed to benefits to the police service) | Awaiting Decision |

Amber - Category:

| Reference | Organisation | Title | Lead | Actions | Chairs Action |
| --- | --- | --- | --- | --- | --- |
| P1 | Powys | Respiratory MDT Response | Samantha Ruthven-Hill / James Houston / Rachel Marsh | - Stephen Harrhy to discuss with Welsh Government in the first instance. - Bid needs to be worked up in more detail and clarification around outcomes and costs to be confirmed | Awaiting Decision |
| WAST4 | Welsh Ambulance | Shifting left on mental health and crisis care – building a more responsive workforce and a more efficient response | Rachel Marsh | - More work around contextual information needed - Merit in pursuing this scheme but costings etc. need to be confirmed. | Awaiting Decision |
| WAST7 | Welsh Ambulance | Welsh Ambulance Service NHS Trust - Volunteer Strategy | Rachel Marsh | - Refine bid submission (restrict/refine) - Greater clarity around the scheme needed – how will this be embedded into the organisation | Awaiting Decision |

Further work needed category:

These were submitted as ‘local projects’ but have the potential to be scaled up nationally. Further discussions to take place around these areas.

| Reference | Organisation | Title | Actions |
| --- | --- | --- | --- |
| BC1 | Betsi Cadwaladr | Development of SICAT to support community hospital and care homes | Develop proposals for EASC to consider. |
| SB1 | Swansea Bay | Acute GP Review of patients waiting on the WAST Live Stack |  |
| SB2 | Swansea Bay | Swansea Bay Health Board Acute Clinical Teams (Swansea and NPT) provide an alternative integrated response model to ED |  |

Rejected bids:

The submissions below were rejected by the panel as they did not meet the criteria, however there is merit in the bids and would be worthwhile exploring other sources of funding (external and internal) in order to progress further.

| Reference | Organisation | Title | Comments | Chairs Action |
| --- | --- | --- | --- | --- |
| BC2 | Betsi Cadwaladr | APP joint working in Ysbyty Alltwen Minor Injury Unit | - Candidate for Winter Funding. - At present no resources to pull APP for a period of 3 months | Rejected |
| CTM1 | Cwm Taf Morgannwg | Increasing Capacity to Improve Handover Times | - Local - Internal Funding | Rejected |
| CTM2 | Cwm Taf Morgannwg | Extension to 3rd Sector Discharge Scheme from A&E | - Local - Internal Funding | Rejected |
| CV1 | Cardiff & Vale | Increasing the Use of Alternative Referral Pathways : Improving and Evolving the Use of the Community Falls Pathway and Services in Cardiff & the Vale UHB | - Local Level - HB staff. How do we target the resource better? Conversation to take place between WAST & Cardiff | Rejected |
| CV2 | Cardiff & Vale | Clinical Pathway Redesign for Patients Diagnosed with non-ST Elevation Acute Coronary Syndrome (NSTEACS) | - Local- not suitable for EASC funding | Rejected |
| HD1 | Hywel Dda | WAST & Hywel Dda University Health Board - Hospital Ambulance Liaison Officer (HALO) | - Local Internal Funding - needs a HB person to co-ordinate. Happy to have the conversation | Rejected |
| HD2 | Hywel Dda | WAST & Hywel Dda University Health Board – Out of Hours primary Care / GP Services Collaboration with Advanced practitioners (Paramedic / Nurse) | - There will be discussions with Health Boards as part of the APP Scheme | Rejected |
| HD3 | Hywel Dda | Hywel Dda University Health Board – radiology Support and extended operational hours of Minor Injury Unit (MIU) in rural areas | - Would encourage Radiology service to put in place - not appropriate source of funding | Rejected |
| HD4 | Hywel Dda | WAST & Hywel Dda University Health Board – Category 1 Falls Assistance / Welfare | - Local Level - HB staff. How do we target the resource better? Conversation to take place between WAST & Hywel Dda | Rejected |
| HD5 | Hywel Dda | WAST & Hywel Dda University Health Board – Inter-Hospital Transfer Vehicle | - Conversation around the need of changes in service (Demand & Capacity review) would need conversation of what resources are needed | Rejected |
| SB3 | Swansea Bay | Hospital Ambulance Liaison Officer (HALO) | - Local Internal Funding - needs a HB person to co-ordinate. Happy to have the conversation | Rejected |
| SB4 | Swansea Bay | Frequent services users nurse – Morriston ED | - Local Health Board Funded | Rejected |

Appendix 2: 1% HWAEP financial summary of shortlisted bids & actions

Appendix 3: Mental Wellbeing by Design

Welsh Ambulance Service NHS Trust

1% Healthier Wales Fund – Mental Wellbeing by Design

Note to Panel following discussion on 26 July 2019

GREEN – FULL YEAR COST £197K

Introduction

- This brief note seeks to respond to the panel’s queries and provide additional supporting information regarding the bid titled “Mental Wellbeing by Design”. In summary, the proposal is to enhance our existing occupational health and wellbeing services with in-house professional psychology.

Background / Context

- We have been working with Dr Adrian Neal, Consultant Psychologist, Employee Wellbeing, Aneurin Bevan University Health Board to assist our thinking about our future organisational wellbeing needs, reflecting upon learning from current evidence and research.  A recent report from the Health Education England - Commission into NHS Staff and Learner Mental Wellbeing set out a compelling, powerful narrative of the importance of promoting and supporting the wellbeing of NHS staff and learners. This description could be speaking directly to the experiences of our own workforce. The report states ‘working and learning in the healthcare sector is like no other employment environment. Daily our staff are confronted with the extremes of joy, sadness and despair. [..] this emotional labour is often exhausting.’ It goes on to describe how, ‘many of our clinical staff retain a collection of curated, traumatic memories of death and dying. Many […] see the horrors of extreme trauma; they see the aftermath of major road traffic accidents, suicide, and they see children in distress or dying and they help families cope with the loss of a loved one. They see the effects of deprivation and many see […] ‘life in the raw.’

- These inherent demands of the job can profoundly impact upon the wellbeing of staff. Cumulatively, exposure to primary stress may bring about psychosocial injury and disruption to lifestyles, and in more extreme circumstances, may require a significant period of recovery. The knock on effects may also affect family, friends, work colleagues and wider communities.

Most of us can all think of individuals among our staff whose personal experiences and stories move us to want to do better.

- Our proposal is to invest into in-house professional psychology in order to increase the capacity, skills and capability within the Trust to shape development of our Wellbeing by Design Strategy and to offer greater access to a higher level of psychological support and individual intervention for those individuals at greatest need.  Reflecting upon the recommendations of the HEE Commission report (recommendation 2) it is proposed this post could fulfill the role of Workplace Wellbeing Lead – working closely with the Executive Director of Workforce and OD, across the Board and Executive Management Team and wider organisation to safeguard individual and organisational health and wellbeing.

- The rationale and what we hope to achieve has been set out within the EARTH template and has been approved in principle subject to some additional information and clarity on the following points:

Why professional psychology input?  Is this clinical psychology or occupational psychology?

- Our reading points to a need for employers to develop a deeper, more psychosocially informed understanding of the complex demands and psychological aspects of their work as well as what internal and external resources employees need over time to do their job safely.  Traditional Occupational Health is mostly focused on illness and in particular reactive interventions to help with physical illness. We now know that the best performing and sustainable workforces work in environments where the psychosocial aspects of wellbeing is proactively addressed. The HSE, and legislation, do a good job protecting and understanding physical health at work but given now most of sickness absence (and potentially also underperformance, conflict, errors and poor morale) is linked to psychological and social factors it seems logical to draw upon the expertise of a professional psychologist to lead workplace wellbeing going forward.

- What’s more, a psychologist will help the organisation identify, measure and understand the psychosocial needs of the workforce allowing us to design wellbeing proactively into the way we do business – into our jobs, systems, practices and environments – this challenge sits at the heart of our emerging strategic wellbeing ambitions.   A consultant psychologist, preferably a clinical psychologist with an understanding of occupational psychology / organisation behaviours, would enable us to substantially develop our capacity to address (both reactively and, importantly, proactively) the psychological needs of our workforce and deliver patient facing care as appropriate.

- At a simple level, most high performing sports teams now have direct input from a professional psychologist to help address their psychosocial needs, why should #TeamWAST be any different?

Employ or Buy In?

How will WAST ensure appropriate professional leadership and clinical supervision for an in house psychology resource?

- Given the scope and expectations of these roles, we believe full time employment / secondment (see above) is a preferable option to buying in resource on a sessional basis.  We require individuals who will immerse themselves in understanding the organisation, the cultures, frontline roles and demands, build relationships and feel personally and professionally invested in delivering positive outcomes for the organisation and its workforce.

- We understand the Healthier Wales funding is recurrent which would allow for substantive appointments to be made. This may be an appropriate arrangement at consultant level provided arrangements can be made with Health Board colleagues to access professional leadership necessary for appraisal, revalidation and CPD requirements – we are confident this can be agreed.   We are basing this on the experience and advice of Dr Adrian Neal, presently employed as a Consultant Psychologist, Employee Wellbeing Lead within the Organisational Development Directorate of Aneurin Bevan University Health Board, who has minimal contact with the Health Board’s clinical psychology department.

- However, we are advised that a secondment arrangement whereby the overall responsibility for professional leadership continues to lie with the originating/seconding organisation, would be a more appropriate arrangement for the Band 8a clinical psychologist. This post holder will carry a much more direct patient facing case management role, providing clinical leadership, supervision and oversight of our TRiM practitioner network and development of our mental wellbeing pathways.  In this circumstance, the Professional Lead from the host organisation would still hold ultimate responsibility for all matters professional (planning CPD, Governance, HCPC related matters). It would however be important to establish clear line management within the host organisation (WAST) and this is best placed within OH. Without this there may be issues around agreed goals, accountability and appraisal. Typically the host manager will conduct the annual appraisal and the professional lead will attend to offer guidance.

- We are keen to move swiftly to recruit to these crucial posts so that we may begin to describe what an enhanced Occupational Health Service might look like, and to realise the benefits of meeting agreed organisational priorities around the psychosocial needs of staff. These include, for example, improved wellbeing; improved morale and engagement; improved psychologically based mental health; improved team work;  a strengthened culture of compassion & psychological safety, supported by appropriate leadership training and development; improved management of complex cases where mental illness is implicated; better psychosocial risk assessment (suicide, DSH and capability to work); and the design of validated psychometric tools specifically for this population; and delivery of a range of evidence based psychological therapies.

Please let me know if further information is required.

Claire Vaughan, Executive Director of Workforce & OD

06 08 2019

Appendix 4: Transport solutions: Right transport, right patient, right time

Welsh Ambulance Service NHS Trust

1% Healthier Wales Fund – Non Emergency Patient Transport Service

Note to Panel following discussion on 26 July 2019

AMBER PLUS - £272K for first year, one post to be reviewed thereafter

Introduction

- This brief note seeks to respond to the panel’s queries in relation to the bid entitled “Transport solutions: Right transport, right patient, right time’.

Background and Context

- The NEPTS Healthier Wales bid “Right transport, right patient, right time”, was developed in partnership through the NEPTS Delivery Assurance Group and with the full support of all partners. Members of the DAG held several sessions to develop the bid and to develop the proposed concept into a deliverable proposal.

- During the development process we have also sought the views of Welsh Government, CHC Cymru and other parties and the proposal has received their support and has been welcomed as a positive way forward.

- The bid has been developed to contribute towards achieving several of the aims of the NEPTS business case which was approved by the Minister in 2016 and to contribute to achievement of the 2019/20 commissioning intentions for NEPTS.

- A small scale trial of this service was undertaken for patients with a T1 mobility in Aneurin Bevan in July 2018. The trial saw no concerns raised by patients or their representatives and reduced both overall numbers of journeys undertaken and the level of social conveyance.

- Should the bid be approved, it will allow us to enhance and transform the interface between the public, Health Care Professionals and the service, whilst also delivering improvements to quality and transforming service delivery across all 5 steps of the NEPTS pathway.

Expected Benefits and Outcomes

- The panel indicated that they would want to be assured of the benefits and outcomes for this scheme, both from a qualitative and quantitative perspective. The following paragraphs therefore attempt to describe more succinctly the purpose of the service solution against each of the NEPTS steps.

Step 1

- There is very little consistency across Wales, either from Health Boards or WAST, in how NEPTS is promoted or accessed. This has led to a patchwork quilt of provision across Wales where different access routes are promoted from a clinic level upwards and patients are uninformed and confused about what NEPTS is, who it is for and how it is accessed. This is demonstrated by a study undertaken of one Health Board’s appointment confirmation letters, where over 40 different versions were identified with wide variation on the guidance provided for NEPTS provision and the methods of accessing the service.

- The variability and inadequacies of this aspect of provision was also identified and highlighted by the CHC Cymru report, Non-emergency transport: The picture across Wales, which stated, “Any framework must be well communicated to front line staff and patients and ensure equitable and safe provision across Wales.”

- The proposal will establish a focus on step 1 of the NEPTS 5-step model that currently does not exist. The proposal will identify the key messages that patients need to know to allow them to make informed decisions about NEPTS and how they can access healthcare provision. The proposal will introduce NEPTS ‘help me choose’ messaging that will help meet the current unmet needs of patients and deliver a system that is clear, well publicised and reflects actual service provision.

- As the signposting of non-eligible patients increases and the alternative options for provision grow, the list of local alternative provision will need to be kept live and reflect actual provision available to ensure a good patient experience. The proposal will provide the required staffing capacity to ensure this happens.

- The NEPTS business case and CASC commissioning intentions both require a reduction in the conveyance of non-eligible patients. This shift away from the current situation of almost universal provision for non-eligible patients will make it more important than ever that clear guidance and advice is given to patients and HCP’s on eligibility and the alternatives to NEPTS provision.  This proposal will allow us to do this without having to divert resources away from other areas of service delivery and risk reducing patient care.

Step 2

- The current process required to make bookings for NEPTS journeys also varies across Wales with bookings being made on line, by telephone, in person and by fax. There are also 2 separate Health Board operated centres in Powys & Ty Elai.

- When a patient contacts NEPTS to make a booking for transport they are subjected to several sets of questions (Patient Needs Assessment – PNA) to establish:

- Are they a HCP? If so, there is an assumption that the HCP has undertaken the assessment for eligibility and the patient is automatically determined as being medically eligible.

- Are they medically eligible – if yes, booking accepted. If no, booking could be accepted or passed to alternative providers.

- For all non-eligible patients, the WHC advises that the provider only has to “consider” the request for transport, but does not define what this consideration should take account of.

- The proposal will allow for the PNA to be reviewed to ensure it correctly identifies medically eligible patients and also supports those without a medical need for transport to identify and secure alternatives. The proposal will define what ‘consideration’ means and establish a framework to establish a conversation with patients to identify what non-medical needs for transport exist and match these to the most suitable available alternative provision.

- The proposal also allows the service to Quality Assure booking requests and ensure that the operators and the process are most effectively meeting patients’ transport needs. This audit will also allow the service to identify areas of unmet need and to link with the Help Me Choose lead and the Alternative Provider team to develop/access appropriate solutions within the community and build these additional services into future call scripts.

Step 3

- NEPTS journeys are currently planned the day prior to travel and the resource availability is based on historical activity. However, NEPTS demand is highly variable with significant differences in volume, acuity and location of journeys every day. The current system timeframes do not allow enough time to adjust resource availability to ensure optimal service provision. This can result in either not enough or too much resource being available or the wrong type/location of resource being in the plan.

- As most NEPTS journeys are planned journeys, it should be possible to predict demand and to adjust resource availability/profile to ensure it is more closely aligned with actual demand.

- The proposal allows for the development of a daily analysis of actual demand and historical demand to identify shortfalls or surplus of resource in a more timely manner that allows the service to respond appropriately.

- This analysis, combined with the work of the Alternative Provision team, will ensure that our utilisation of additional resources is minimised and that the most cost effective appropriate solution is procured.

Step 4 & 5

- All of the above steps will contribute to an overall improvement, where demand into the service is managed appropriately, where the quality of bookings will increase and therefore patient needs are captured more consistently and accurately. This, combined with increased awareness of NEPTS demand and appropriate resourcing, will increase the likelihood of the appropriate resource being available to meet the patients’ needs. Right transport, right patient, right time.

- Our proposal will also deliver the following specific performance improvements, as well as contributing to performance improvements across many of the NEPTS indicators. It should be noted at this stage that further discussions will need to take place through the DAG with partners to confirm and agree these planned improvements and they may therefore be subject to some change as the detailed service implementation planning commences.

Step 1

- a 20% increase month on month for the first 12 months in the number of patients signposted to alternative providers

Step 2

- a 50% reduction on 2018-19 levels on the level of abandoned calls

- a 100% reduction on 2018-19 levels of bookings taken by fax in year 1

Step 3

- a 20% reduction on 2018-19 levels on bookings received after 12 noon the day before travel

Will the resources identified be required recurrently?

- The panel requested further clarification as to whether the resources put forward in the bid would be required recurrently or whether an element would be considered as non-recurrent implementation costs.

- The additional resources described in steps 1 & 2 and the Demand Planning Manager would be required for the initial set up of the proposals and would then become a key part of any future service provision. These posts would be required to both manage the service provision and also to ensure that the service remained live and continued to maximise the  impact going forward. These posts will also allow for the service to respond to future changes in service provision, so will need to be funded on a recurrent basis.

- Although there will always be a need to have high quality analyst support within the service, it is accepted that once the demand analysis and reporting system is established and mature there may not always be a need for the proposed level of analyst support. It is therefore proposed to review the post of NEPTS demand analyst after 12 months to establish if it is still required.

Mark Harris

Interim Deputy Director for NEPTS

Appendix 5: Intelligence Led Joint Response Unit Pilot

Welsh Ambulance Service NHS Trust

1% Healthier Wales Fund – Joint Response Unit

Note to Panel following discussion on 26 July 2019

AMBER PLUS - £46k non recurrent

Introduction

- This brief note seeks to respond to the panel’s queries in relation to the bid entitled “Intelligence Led Joint Response Unit Pilot”. This should be read in conjunction with the EARTH template previously submitted.

Background and Context

- WAST have been operating Joint Response Units (JRU’s) for several years together with the three Southern Wales Police Forces. Following constructive challenges both internally at WAST, from our Senior Clinical Directorate colleagues, and externally, from JESG Chief officers and the Tri-service Demand & Intelligence Hub Team, a decision was made to review the value of the JRU(s) and to test any variation or waste.

- The WAST Assistant Director of Operations worked with the Health Informatics Team to look at an Intelligence Led list of criteria, to establish if the remaining three JRU’s were located appropriately, and operated with the right skills in the right places. A clear objective was to test if the JRU’s use of a paramedic was proportionate and necessary as compared with the alternative of working on a conventional RRV.

- It was agreed that the previous self-tasking JRU models would need to be tested against the more auditable and accountable methodology of being tasked by the WAST Clinical Contact Centre in partnership with the Police Public Service Centre. The WAST calls/code sets were agreed as being mutually beneficial to patients and the communities across  South Wales, allowing clear Terms of Reference for the service.

What are the proposed benefits of the service, from a WAST and a police perspective?

- It is proposed that the Call Code sets that the JRUs respond to are Mental Health, RTCs, Deaths and Overdoses and Violent calls. The aim of the pilot will be to establish the benefit of the joint response to these types of calls. The paragraphs below attempt to describe the benefits that are expected.

- Improved attendance at Mental Health Calls: The benefit here is that the right resources are sent in a timely fashion together. If there is violence, the police will take primacy. If the patient needs treatment then the paramedic will assess the patient and consider A&E or an alternative pathway. We will measure the number of calls which provide added value from both emergency services perspective.

- Improved attendance at RTCs: We will measure the number of calls which provide added value from both emergency services. The joint response to these calls should allow the paramedic to assess, treat and address patient needs, and allow the police to assess the danger and deal with RTC.

- Improved service provided in the event of a death or overdose: Both police and WAST are called to deaths and overdoses. The benefits here will be in relation to timely joint responses which avoids long delays waiting for one of the emergency services to assist the other.

- Improved attendance at calls with potential violence: It is anticipated that this will bring significant benefits to both parties. Having the police presence will allow the paramedic to treat the patient and decide on the best course of medical intervention without risk of getting hurt themselves.

- Reduction in adverse incidents: Adverse incidents are often raised by both WAST and the police where there are delays in attendance to mental health patients. This will reduce the number of adverse incidents raised therefore, at the same time as improving the patients experience and keeping staff safe.

- As the three proposed pilot sites use a WAST Rapid Response Vehicle and respond primarily to WAST calls, it is likely that the main benefits will accrue to WAST. However, the ability for a police officer to support a paramedic is seen as a win-win by avoiding the need for the police units to attend themselves and to have to convey patients or attempt to deal with Mental health or other vulnerable patients without the requisite skills.

- In conclusion, whilst both WAST and SWP/Gwent Police will benefit through reducing inappropriate attendances, it is clear that the main beneficiaries will be our patients and the wider communities of South Wales and Gwent.

What will the governance arrangements be for this service and how will decisions be made about long term recurrent funding?

- The Governance route will be via the leads from the Tri-service Demand & Intelligence Hub reporting into the Chief Officers from JESG Executive. This will involve briefing CFO Hugh Jakeaway SWFR as the ambassador of JESG who will agree any additional criteria for measuring success. It was hoped that the leads from the Tri-service Demand & Intelligence Hub could present initial findings to the next JESG in November 2019. However, this will depend on whether the bid is successful, and the project is able to commence as soon as possible, to meet that deadline. Alternatively it would need to be presented at the following JESG in April 2020 which may allow for a longer evaluation window and for the benefits to be delivered over the busy winter months.

- However, whilst it is proposed that the evaluation and review of these pilots would be taken to JESG, it is clear that any funding requirements would need to be agreed by EASC as the WAST commissioner. WAST can confirm that any agreement to these pilots does not constitute an agreement for long term funding.

Submitted By

Robert Tooby

Assistant Director of Operations

(WAST Lead for the Tri-Service Demand & Intelligence Hub)

Appendix 6: Shifting left on mental health and crisis care – building a more responsive workforce and a more efficient response

Welsh Ambulance Service NHS Trust

1% Healthier Wales Fund – Mental Health Bid

Note to Panel following discussion on 26 July 2019

AMBER – FULL YEAR COST £222K

Introduction

- This brief note seeks to respond to the panel’s queries regarding the bid titled “Shifting left on mental health and crisis care – building a more responsive workforce and a more efficient response”.

Have other bids been submitted to other funding bodies?

- WAST can confirm that no other mental health bids have been submitted to Welsh Government, or indeed to any other funding body in Wales or the wider UK. The 1% Healthier Wales submission is our only live or proposed bid on mental health.

Will it be possible to recruit staff to these posts? Could this undermine frontline mental health services?

- Practice development roles are relatively common in the UK and these roles are benchmarked against existing roles in the NHS. Our market testing tells us that these posts will be attractive to mental health professionals in Wales and beyond, particularly people who want to grow into clinical teaching or academic positions, and this proposal provides a career structure for them within WAST.

- The three Band 7 posts will be situated to support staff and work with partners across three regions in Wales, and as such we will only be looking to recruit one person in each region (North Wales, Central and West Wales, South East Wales). This will have a minor impact workforce planning within Health Board areas.

- WAST will also work in partnership with Directors of Nursing to explore joint appointments with Health Boards or other organisations to share skills and extend the reach of practice improvement across the crisis care systems. However this approach may require additional investment from LHBs/others to achieve this approach with regards to travel costs etc.

How is WAST ensuring that newly qualified paramedics emerge from university with all of the skills required? Wouldn’t that reduce the need for practice development?

- WAST is currently working with Swansea University to develop the degree programme for paramedicine, and specifically the mental health content included within it. However, this degree programme will not commence until 2020, and first graduates will only emerge in 2023. The existing diploma programme content is set, and not something Swansea are keen to change given that it will soon be phased out.

- Furthermore, the degree programme will have little impact on our existing staff. Ongoing learning of the nature described in the bid will be key to helping keep our staff in post across all our services up to date with changes to population needs, new interventions and maintaining good practice, ultimately to provide safe timely and effective evidence based care and to ensure patients are signposted to the right service.

Is this proposal additional to what WAST has been doing already?

- The proposal is significantly different and additional to our current offer, or what we are currently funded for. The paper attached below sets out our delivery plan for 2019-20 that is set within our current resource allocation. The longer term strategy is not articulated in a document, and therefore the delivery plan provides the best information on the work that is currently on-going.

- This plan for 2019-20 has been agreed with commissioners and Welsh Government. Our three year mental health improvement plan is embedded within that document. The plan for this year reflects a substantial amount of work that is underway in readiness for the outcomes from the mental health and crisis care access review.

- WAST is already providing education to our staff around mental health, including e-learning and single day training on suicide intervention. However, whilst we know this is beneficial, the evidence suggests that this model is expensive to buy-in. Furthermore, we know that releasing staff to participate in training is costly and difficult, particularly over winter. This currently represents a minimum offer.

- This proposal for the practice educators seeks to support learning as people work. Rather than release people for training away from their workplace, practice develop facilitators will work alongside an individual or a small group in their role to support applying new interventions in real practice circumstances, to grow confidence and competence, to reflect and embed skills in the context that they will be used in, and to ensure that the skills are used. An example of application in practice:

- Have a short introduction to the intervention being learned

- ‘Hear and treat’ or ‘see and treat’ patients together

- Try out the intervention in the real world

- Reflect on how things went

- Try the skill again, until confidence and competence is achieved

- Practice development facilitators will all work to the same model of practice, ensuring that there is consistency to what is being delivered and how it is being taught. They will collect substantial amounts of data on practice change, and on outcomes for the public. This model is sustainable, achieve better skills within the workforce and improve outcomes for the public.

Summary

- We feel that this proposed offers a sustainable approach that will embed better crisis care practice in WAST without hollowing out existing mental health services. It will improve outcomes for people, provide better data for commissioners and a better learning experience for our staff.

- We hope that this note clarifies key points for the panel. However we would welcome any further questions to assist the panel.

Appendix 7: Volunteer Strategy

Welsh Ambulance Service NHS Trust

1% Healthier Wales Fund – Volunteer Strategy

Note to Panel following discussion on 26 July 2019

AMBER – REVISED FULL YEAR COST OF C£59K

Introduction

- This brief note seeks to respond to the panel’s queries in relation to the bid entitled “Volunteer Strategy” and refines the resources requested accordingly.

Background and Context

- Our inaugural three year Volunteer Strategy will articulate our ambition and form an integral part of our three year People and Culture Strategy, which aims to enable people to be their best. The strategy will also make an important contribution to the implementation of the Wellbeing of Future Generations (Wales) Act 2015 and Welsh Governments ‘A Healthier Wales’ vision. It is currently anticipated that the Strategy will be considered at the September Trust Board meeting.

What additionality is delivered as a result of this bid?

- At the evaluation panel meeting, the panel expressed the view that a large part of the bid related to work that was ‘business as usual’, given that we have supported volunteering within the Trust for many years. As such, a number of elements of the bid were not supported.

- The panel indicated that it would be supportive however of a reduced bid, where this demonstrated additionality.

- Our vision is to create an organisation that embraces volunteering as a means of uniting the Trust with our communities and enabling the public to give something back. Working with our Patient Engagement, Community Involvement team  our focus will be to increase the diversity of our volunteers so that we embrace cultural diversity, engage with young people and those that are most marginalised within our communities and face segregation due to language barriers, isolation and loneliness, mental health conditions and religious beliefs. This will be one area of additionality.

- The strategy will also look more widely at the greater contribution that volunteers can make to enhancing all parts of the organisation and services, not just as Community First Responders or as volunteer car drivers.

- The proposed Senior Volunteer Manager role is seen as integral, offering leadership and direction to ensure we deliver our ambitions set out in our strategy. There will also be considerable focus on ensuring that all our current and future volunteer opportunities and in particular community first responders are effectively recruited, developed and deployed to support WAST in achieving target response times and improving the experience and service we offer our patients and service users across Wales.

- We are therefore proposing that we put forward a revised bid for the Senior Volunteer Manager. The annual cost for this post would be £59k, with an in year cost of £20k for a candidate starting in December 2019.

- The revised offer should still be read in the context of the full information in the EARTH template, which sets out the benefits of the implementation of the Volunteer Strategy.