## Organisational Risk Register
Datix ID | Portfolio | Risk Domain (Strategic Objective) | Risk Title | Risk Description | Controls in place | Action Plan | Sources of Assurance | Rating (current) | Rating (Target) | Trend | Opened | Review date
4260 | Chief Ambulance Services Commissioner | Set the Strategic Commissioning Plan | Failure to produce an agreed Strategic Commissioning plan and commissioning intentions | IF: There is a failture to produce and agree a strategic commissioning plan and commissioning intentions Then: The commissioned providers would not be clear regarding expectations for the quality, effectiveness and efficiency of services within an agreed financial plan . Resulting in: Lack of clarity in the direction of the commissioned organisations (WAST and EMRTS) | Ensuring a programmatic approach to planning and delivery with focus on monitoring progress through the EASC Sub Groups Strategic Commissioning Intentions developed and agreed EASC IMTP / Annual Plan developed and approved Forward look developed for all EASC Sub Groups including receiving progress on the deliverables within the plans Regular reporting from EASC Sub Groups to the EAS Joint Committee on progress Commitment from the EASC for strategic commissioning cycles | 3 Year commissioning intentions agreed for EMS; annual commissioning intentions in place for NEPTS and EMRTS; agreed annual commissioning cycle for the development of strategic Commissioning Intentions agreed; monitored at each EASC Management Group (quarterly) meeting | EASC IMTP EASC Strategic Commissioning Intentions Minutes of EASC Sub Group meetings monitoring progress against plans | 4x1 = 4 | CXL 4x1=4 | ê | 2020-08-01 | 2022-08-01
4502 | Chief Ambulance Services Commissioner | Meet the Ministerial direction to produce an EASC IMTP / Annual Plan | Failure to develop an agreed EASC IMTP for endorsement by the Joint Committee seeking approval from the Welsh Government | IF: There is no agreement for the EASC IMTP Then: The Strategic Commissioning plan (commissioning intentions) would not be supported Resulting in: Lack of clarity in the direction of the commissioned organisations (WAST and EMRTS) | CASC Quality and Delivery meeting held monthly to discuss Quality and performance matters Detailed work to develop EASC IMTP overseen by EASC Management Group EASC IMTP (2020 to 2023) approved by EASC (January 2020) EASC Annual Plan 2021-22 approved EASC 9 March 2021 WAST and EMRTS response received to the EASC IMTP /Annual Plan CASC Quality and Delivery meeting with Welsh Government bi monthly CASC meetings with Welsh Government planning department EASC one year plan for formal approval at EASC 9 March 2021; formal confirmation received from Welsh Government in relation to the plan and regular meetings take place | Agreed timescales with EASC for the development and receipt of the draft IMTP / Annual Plan and included on the Forward Look for the Committee - all completed and included in the commissioning intentions cycle for the IMTP | Consistency between EASC IMTP / Annual Plan with WAST IMTP and also with Health Boards Letter of support from the Welsh Government EASC Approval of the plan Quarterly IMTP /Annual Plan updates to EASC Formal approval of plan received from Welsh Government | 4x1=4 | CXL 4x1= 4 | ê | 2020-08-01 | 2022-08-01
4503 | Chief Ambulance Services Commissioner | Effective Commissioning | Failure to deliver the Ministerial direction that EASC effectively plans, commissions and secures services within its remit; and failure to maintain collaborative relationship with providers | IF: The EASC fail to plan and secure services and maintain effective collaborative relationships with providers Then: The purpose and effectiveness of the EAS Joint Committee would not be met Resulting in: Potential Ministerial and Welsh Government intervention | Agreed collaborative commissioning methodology review and refine commissioning arrangements - agreed EASC 9 March 2021 Effective function of the EASC Joint committee Independent Chair Effective governance arrangements in place CASC and Welsh Government Quality and Delivery meetings (bimonthly) Minister meets with the Chair quarterly Meet regularly with providers to ensure continued development of open and transparent relationship Model Standing Orders agreed for EASC July 2021 Special meeting of EASC with Minister and clear expectations received | Commissioning framework and monitoring at EASC and its sub committees Annual Governance Statement Monitoring of EASC IMTP at EASC and sub groups Review and refine governance arrangements Maintaining close working and collaborative relationships during unprecedented system pressures Ministerial action plan and monthly monitoring return commitment | Internal and external audit Welsh Government EASC Committee members Annual Governance Statement Strategic Commissioning intentions Continued engagement with the commissioning process and EASC Governance Ministerial action plan Chairs appraisal letter with Minister | 5x2=10 | CXL 5x1=5 | ↔ | 2020-08-01 | 01/08/2022 (reviewed 01/08/2021)
4504 | Chief Ambulance Services Commissioner | Outcome measurement | Failure to respond to requirements identified within commissioned work related to the ambulance services | IF: Work commissioned is failed to be acted upon Then: risks and issues identified will not be acted upon and implemented Resulting in: a missed opportunity to improve services | Forward plan for EASC and all sub groups Development of action plans which are received , endorsed and approved by the EASC for action Action log for EASC and all sub groups Regular review of Ambulance Quality Indicators Commissioning intentions - including measurement across the system Ministerial request for system wide measures | Governance and planning for EASC and all sub groups and supporting meetings Review of the commissioning framework Ministerial action plan and monthly monitoring return commitment | Amber Review ORH Report D&C EMS EMS Framework - review by April 2021 McClelland Review of Welsh Ambulance Services (2013) Internal and external audit CASC Quality and Delivery meeting with Welsh Government Annual Governance Statement Commissioner Ambulance Availability Taskforce | 4x2=8 | CXL 4 x2 = 8 | ↔ | 2020-08-01 | 2022-08-01
4505 | Chief Ambulance Services Commissioner | Ministerial direction | Failure to achieve the agreed Chair's objectives with the Minister | IF: The agreed Chair's objectives with the Minister are not delivered Then: Then the confidence of the Minister will be potentially compromised Resulting in: The Minister not being assured that necessary progress has been made in the commissioning of ambulance services and the wider connections to unscheduled care services in Wales | The Chair's objectives are shared with the Committee Chair's objectives are utilised when developing commissioning intentions and the EASC IMTP The Chair encourages the Committee to explore the link between Ambulance Services and urgent and emergency care services | Ministerial support for commissioning Commissioning intentions EASC IMTP / Annual Plan Focus on sessions at EASC to discuss wider system issues | Minister's response following Chair's appraisal | 3x2=6 | CXL 3 x2 = 6 | ↔ | 2020-08-01 | 2022-08-01
4506 | Chief Ambulance Services Commissioner | Securing | Failure to achieve agreed performance standard for category red calls | IF: The red performance level is less than 65% for each health board area and across Wales as a whole on a monthly basis Then: The core target will be missed Resulting in: Unsatisfactory service for the people of Wales (or within specific health board areas) | The necessary resources secured in the EASC IMTP / Annual Plan performance monitoring on a daily basis and month to date position Bi monthly CASC Quality and Delivery meeting with Welsh Government CASC monthly Quality and Delivery Meeting with the Welsh Ambulance Services NHS Trust Commissioner element of EMS Demand and Capacity plan for additional staff supported | Delivery of EASC Annual Plan and WAST IMTP Implementation of the commissioning intentions through the commissioning agreement Role of the EASC Management Group to provide oversight on operational performance Commissioner requirement for WAST Improvement Plan (June 2021) | Ambulance Quality Indicators Daily weekly and monthly performance reports Remedial Action plans (if required) Specific targeted actions as required Commissioner Ambulance Availability Taskforce Implementation of the Demand and Capacity Review Ministerial Action plan (monthly) CASC liaision with Chief Operating Officers | 4x5=20 | CXL 4x3= 12 | ↑ | 2020-08-01 | 2022-08-01
4507 | Chief Ambulance Services Commissioner | Securing | Failure to achieve agreed performance standard for amber category calls | IF: The average time for amber performance calls does not reduce year on year Then: The core target will be missed. Resulting in: unsatisfactory service for the people of Wales (or within specific health board areas). | The necessary resources secured in the EASC IMTP/ Annual Plan performance monitoring on a daily basis and month to date position CASC Monthly quality and delivery meetings with WAST Bi monthly CASC Quality and Delivery meeting with Welsh Government CASC monthly Quality and Delivery Meeting with the Welsh Ambulance Services NHS Trust Commissioner element of EMS Demand and Capacity plan for additional staff supported | Delivery of EASC Annual Plan and WAST IMTP Implementation of the commissioning intentions through the commissioning agreement Role of the EASC Management Group to provide oversight on operational performance Commissioner requirement for WAST Improvement Plan (June 2021) | Ambulance Quality Indicators Daily weekly and monthly performance reports Remedial Action plans (if required) Specific targeted actions as required Ministerial Ambulance Availability Taskforce Implementation of the Demand and Capacity Review Ministerial Action plan (monthly) CASC liaision with Chief Operating Officers | 4x5=20 | CXL 4x3= 12 | ↑ | 2020-08-01 | 2022-08-01
4653 | Chief Ambulance Services Commissioner | Set the Strategic Commissioning Plan | Failure by the whole system, policy makers, commissioners and providers to utilise EASC in matters which relate to its areas of responsibility | IF: The system does not utilise the arrangements in place at EASC Then: The governance and purpose of EASC will be undermined Resulting in: a lack of consistency, duplication of services and resources, poor governance and non compliance with the Statutory Instrument leading to unnecessary system pressures | Accountable officers are members of EASC Memorandum of understanding and commitment from all EASC members Sharing information on service developments Alignment to the 6 Goals for Urgent and Emergency Care Policy Steering Board Model Standing Orders agreed Commissioning Framework | Collaborative commissioning agreement EASC Management group representing all organisations Aligning EASC IMTP/ Annual Plan with WAST and Health board IMTPs CASC meeting with Welsh Government planners CASC Quality and Delivery meeting with Welsh Government CASC Quality and Delivery meerting with WAST Chair of EASC and CASC meetings with Health Boards CASC Member of NHS Leadership Board | Memorandum of understanding Independent Chair Governance arrangements Commitment to collaborative nature of working External audit Welsh Government and Ministerial support for EASC | 4x2 =8 | CXL 4x1= 4 | ↔ | 2020-08-01 | 2022-08-01