|  | AGENDA ITEM 3.2 12 November 2019 |
| --- | --- |

Emergency Ambulance Services Committee Report

ALIGNMENT OF EASC COMMISSIONING INTENTIONS WITH INTEGRATED MEDIUM TERM PLANS (IMTPs)

| Executive Lead: Commissioning | Julian | Baker | – | Director | of | National | Collaborative |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Author: James Rodaway |  |  |  |  |  |  |  |
| Contact Details for further information: Julian.Baker@wales.nhs.uk |  |  |  |  |  |  |  |

Purpose of the Emergency Ambulance Services Committee Report

The purpose of this report is to outline for EASC the proposed approach to the Commissioning Intentions for EASC commissioned services and their alignment with Welsh Ambulance Services NHS Trust (WAST) and Health Board Integrated Medium Term Plans (IMTPs).

| Governance |  |
| --- | --- |
| Link to the Commissioning Agreement | The Committee’s overarching role is to ensure its Commissioning Strategy for Emergency Ambulance Services utilising the five step patient pathway outlined within the National Collaborative Commissioning Quality and Delivery Agreement and the related outcomes for each care standard aligned with the Institute of Healthcare Improvement's (IHI) ‘Quadruple Aim’ are being progressed. This report focuses on all the above objectives, but specifically on providing strong governance and assurance. |
| Supporting evidence | The Collaborative Commissioning Quality and Delivery Framework for Emergency Medical Services |
| Engagement – Who has been involved in this work? |  |
| WAST’s Planning & Performance Directorate; NEPTS Delivery Assurance Group (DAG); Planning Programme Team, Welsh Healthcare Strategy and Planning Division, Welsh Government |  |

| Emergency Ambulance Services Committee Resolution to: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| APPROVE | √ | ENDORSE | √ | DISCUSS | √ | NOTE |
| Recommendation |  | The Emergency Ambulance Services Committee is asked to: - APPROVE the proposed approach to the Commissioning Intentions for EASC commissioned services and their alignment with Welsh Ambulance Services NHS Trust (WAST) and Health Board Integrated Medium Term Plans (IMTPs). - DISCUSS & ENDORSE the content of presentation on the 2020/21 Commissioning Intentions. |  |  |  |  |
| Summaries the Impact of the Emergency Ambulance Services Committee Report |  |  |  |  |  |  |
| Equality and diversity |  | There are no implications arising directly from this report. |  |  |  |  |
| Legal implications |  | There are no implications arising directly from this report. |  |  |  |  |
| Population Health |  | No impact |  |  |  |  |
| Quality, Safety & Patient Experience |  | Ensuring the Committee and its Sub Groups make fully informed decisions is dependent on the quality and accuracy of the information presented and considered by those making decisions. Informed decisions are more likely to impact favorably on the quality, safety and experience of patients and staff. |  |  |  |  |
| Resources |  | No direct impact |  |  |  |  |
| Risks and Assurance |  | Identified within the report. |  |  |  |  |
| Health & Care Standards |  | The 22 Health & Care Standards for NHS Wales are mapped into the 7 Quality Themes: Staying Healthy; Safe Care; Effective Care; Dignified Care; Timely Care; Individual Care; Staff & Resources http://www.wales.nhs.uk/sitesplus/documents/1 064/24729_Health%20Standards%20Framework _2015_E1.pdf The work reported in this summary and related annexes take into account many of the related quality themes in particular timely care. |  |  |  |  |
| Workforce |  | Identified within the report. |  |  |  |  |
| Freedom of information status |  | Open |  |  |  |  |

ALIGNMENT OF EASC COMMISSIONING INTENTIONS WITH INTEGRATED MEDIUM TERM PLANS (IMTPs)

1.	   SITUATION / PURPOSE OF REPORT

The purpose of this report is to outline the approach for sharing the Commissioning Intentions and financial assumptions by the Emergency Ambulance Services Committee (EASC), and their conversion into:

- An agreed Balanced Financial Plan 2020/21; and

- Action Plans for Improvement within organisations IMTPs 2020/21.

A presentation on the 2020/21 Commissioning Intentions will accompany this paper for discussion at the Joint Committee meeting on the 12 November 2019.

2.  BACKGROUND / INTRODUCTION

NHS Planning Framework 2020-23

The NHS Planning Framework 2020-23 (issued in September 2019) detail that organisations will be required to develop their IMTPs in accordance with its approach and expectations.

The expectation is for fully completed and balanced plans to be submitted by the end of January 2020.

EASC & Welsh Ambulance Services NHS Trust (WAST) IMTPs 2019 / 2020

EASC and WAST both had approved IMTPs for 2019/20. WAST have indicated their intention is to refresh their approved 2019/20 IMTP for 2020-23.

NHS Wales, National Integrated Medium Term Plan (IMTP) - An All-Wales Review of NHS IMTPs for 2019–22 referenced the positive observations around the collaborative commissioning arrangements for EASC.

EASC’s collaborative commissioning method is a service that aligns annual Commissioning Intentions into the IMTP cycle for EASC Commissioned Services, which then enables the production of the following products (Figure 1):

- Framework Improvements – updating of the Collaborative Commissioning Quality & Delivery Frameworks;

- WAST Performance Improvements – WAST performance improvements;

- Joint Performance Improvements – WAST and Health Board Joint performance improvements.

- A mid-year progress review of Framework Improvements, WAST Performance improvements and joint performance improvements for EMS & NEPTS as detailed in both the EASC & WAST 2019/20 IMTPs (completed by the NCCU by 12 October 2019.)

This review has been submitted to WAST for them to report on any outstanding actions across Quarters 1 & 2 so that an updated position can be reported to both the Chief Ambulance Services Commissioner (CASC) and EASC Management Group. The detailed position on each of the services is included in the following appendices:

- Mid-year progress review of EMS Framework Improvements and WAST Performance Improvements (Appendix 1)

- Mid-year progress review of NEPTS Framework Improvements and Performance improvements (Appendix 2)

Emergency Medical Services (EMS)

There were 14 Framework Improvements and 13 WAST Performance Improvements issued and accepted by WAST within the 2019/20 Commissioning Intentions for EMS. (Summarised in the table below).

There has been a deterioration in the following key WAST Performance Improvements:

- Red performance to be maintained and the 95th percentile to reduce

- Amber 95th percentile times to reduce across each health board [Carried Forward from 2018/19]

- Resource utilisation will improve: [Carried Forward from 2018/19]:

- sickness rates reduced for all direct staff across each of the steps

- use of external providers to be reduced

- rosters aligned to demand (across days and time of day) for direct staff across each step

- compliance with planned (that is the new) rosters to increase

- Known ‘Net Effect’ in terms of activity impact, resource impact and performance impact from all initiatives

The CASC has commissioned the NCCU to undertake or deliver the following programmes of work with WAST to support improvement in the areas that have shown deterioration:

- Amber Review Implementation Programme

- Red Performance Improvement Plan

- Demand and Capacity Review

- Relief Gap Reference Document

- Regional Escalation Programme

Progress on these programmes are reported into the monthly WAST/EASC performance meetings, through the EASC Management Group and to EASC Joint Committee. They are also reported through the monthly joint quality and deliver meeting with Welsh Government (jointly chaired by the CASC).

WAST have improved performance in these areas:

- The volume of calls assessed and closed by the clinical desk to increase

- Handover to clear times to reduce across all health board areas. [Carried Forward from 2018/19]

These 2019/20 Commissioning Intentions have been completed:

- Review of 2018/19 IMTP financial assumptions and financial plan versus forecast outturn for 2018/19 and 2019/20 financial assumptions and financial plan.

- Financial Value Payable by EASC and associated assumptions.

- Operational arrangements to be reviewed by EASC on an ongoing basis

- Progress review of 2018/19 IMTP actions.

- Inclusion of completed IMTP 2019/20 tables following EASC IMTP approval.

Progress is being made on the delivery of these 2019/20 Commissioning Intentions and an update against these at the mid-year point is being developed by WAST.

- Data repository covering A1 Activity, RE1 Resource Envelope, R1 Performance Measures, including the AQIs, to be utilised with when, who, when specifically stated.

- Trigger points which indicate poor deteriorating performance against performance metrics within the data repository to be identified by CASC and specific actions to warrant corrective action identified

- Development of local measures by Health Board

- Clinical Support Desk : Patient demographics recording to be improved to support patient identifier for linked data

- Proportion of spend will shift from Steps 5 & 4 to Steps 3 & 2

- Reduced spend on operating expenses

- Time to allocation for Red calls to reduce

- Multiple vehicle arrivals at scene to reduce for Amber and Green Incidents

- The percentage of incidents where the first arriving vehicle is the ideal to increase

- [Carried Forward from 2018/19] Clinical Indicator performance to improve, and be above 95% in all health board areas (except ROSC)

At the time of completing the mid-year review the EASC Commissioning Team were unable to ascertain performance against the following 2019/20 Commissioning Intentions. WAST have provided assurance that updates will be provided in their response to the mid-year review:

- [Carried Forward from 2018/19] Fleet and staff mix to be reviewed for each health board area tailoring the delivery of the 5 Step Ambulance Patient Pathway to local population needs.

- The reporting against core requirements to be undertaken twice per year as described under the Commissioning Intention for Care Standards

- [Carried Forward from 2018/19] Call to door times for STEMI (pPCI door) and Stroke to be produced.

- Development of Clinical Indicators which complement the benefit realisation assumptions for Band 6 Paramedic investment to be produced.

- [Carried Forward from 2018/19] 95th percentile call to door times (STEMI & Stroke) to reduce across each health board area

Table 1: EMS summary at mid-year progress review

| EMS | Column Labels |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Row Labels | Completed | Deterioration | Improved |  | Ongoing | Unknown | Grand Total |
| Framework Improvements | 5 |  | 1 |  | 4 | 4 | 14 |
| WAST Performance Improvements |  | 4 | 2 |  | 6 | 1 | 13 |
| Grand Total | 5 | 4 | 3 |  | 10 | 5 | 27 |

Non-Emergency Patient Transport Services (NEPTS)

There were 19 Framework Improvements and 10 WAST Performance Improvements issued and accepted by WAST within the 2019/20 Commissioning Intentions for NEPTS.

WAST have improved performance in these areas:

- Step 1 - Ensure NEPTS specific engagement activity can be identified

- Update O2 Schedule – Application of the Model of Care following enactment of plurality model for each HB

- Implement improvements identified within the Internal Audit of NEPTS provision November 2018.

WAST have completed work to deliver these Commissioning Intentions:

- Financial Value Payable by EASC and associated assumptions

- Operational arrangements to be reviewed by EASC on an ongoing basis.

- IMTP 2019/20 tables following EASC IMTP Inclusion of completed approval

- NEPTS QDF to be signed December 2018.

Work is ongoing to deliver these Commission Intentions and progress is being monitored monthly through the NEPTS DAG:

- Data repository aligned to report activity against relevant step

- Step 4/5 – ensure activity is clearly described within the relevant step

- Review of 2018/19 IMTP financial assumptions and financial plan versus forecast outturn for 2018/19 and 2019/20 financial assumptions and financial plan

- Model of Care wiring diagram updated following implementation of plurality model.

- To record and manage the framework of providers used to deliver the NEPTS plurality model.

- Develop Schedule R2:

- Maintain data repository covering A1 Activity, RE1 Resource Envelope, R1 Performance Measures

- Recording of baseline data for all NEPTS activity& resources for each HB.

- Creation of Evaluation methods and programme of work.

- Development of a fully costed business case to meet the Cabinet Secretary expectations from the 2015 business case.

- Demonstrate WAST NEPTS resources are being utilised effectively following transfer of HBs.

- WAST to ensure robust quality assurance to manage providers required to deliver the plurality model

- WAST to demonstrate how activity performance is improved in each HB following enactment of the plurality model.

- Report & consider improvements following measuring staff experience

- Report & consider improvements following measuring patient experience.

At the time of completing the mid-year review the EASC Commissioning Team were unable to ascertain performance against the following 2019/20 Commissioning Intentions. WAST have provided assurance that updates will be provided in their response to the mid-year review:

- Develop infrastructure to be able identify how much is spend at a HB level across the 5 steps

- Update O3 Schedule – extant policies, protocols & pathways following enactment of plurality model for each HB

- WAST undertake self-assessment related to the Core Requirements in Care Standards

- Evaluation programme for NEPTS overseen by PDEG

- Compliance with care standards for previously extant Health Board/WHSSC/Velindre services

- Compliance with core requirements of care standards reported on a six monthly basis.

- WAST to demonstrate savings and efficiencies in each HB following enactment of the plurality model

Table 2: NEPTS summary at mid-year progress review

| NEPTS | Column Labels |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Row Labels | completed | Improved | ongoing | Unknown | Grand Total |
| Framework Improvements | 4 | 2 | 9 | 4 | 19 |
| WAST Performance Improvements |  | 1 | 6 | 3 | 10 |
| Grand Total | 4 | 3 | 15 | 7 | 29 |

The mid-year review for the Joint Performance Improvements is currently underway due for completion by mid November 2019. Appendix 2 details the initiatives that are being delivered jointly between WAST & health boards.

These Joint Performance Improvements have been identified through the local operational meetings between WAST and Health Board leads. They are the  initiatives  identified to drive performance at a local level.

3.   ASSESSMENT / GOVERNANCE AND RISK ISSUES

Figure 1 outlines the process for sharing 2020/21 Commissioning Intentions and Financial Assumptions by EASC, and their conversion into:

- An agreed Balanced Financial Plan 2020/21; and

- Action Plans for Improvement within organisations IMTPs 2020/21.

This process was developed for the 2018/19 IMTP round. The NHS Wales, National Integrated Medium Term Plan (IMTP) - An All-Wales Review of NHS IMTPs for 2019–22 recognised that this process enables collaboration and will be utilised for 2020/21-23.

This should enable the following process and details for inclusion for EASC, WAST & Health Board 2020/21-23 IMTPs:

- 2020/21 Commissioning Intentions and Financial Assumptions developed and shared by NCCU on behalf of EASC.

- Health Boards and WAST develop Actions Plans for improvement in response to the Commissioning Intentions; and Financial Plans in response to the Financial Assumptions.

Figure 1

EASC IMTP 2020/21-23

Will contain the following:

- Commissioning Intentions for EMS & NEPTS

- Financial Assumptions for EASC Commissioned Services.

- WAST & HB action plans in response to the commissioning intentions:

  - Framework Improvements

- WAST Performance Improvements

- Joint Performance Improvements

The IMTP specification outlined above delivers Ministerial expectation, alignment with A Healthier Wales and is enabled through the use of National Collaborative Commissioning: Quality & Delivery Frameworks to commission services.

- 2020/21 service deliverables/specification for:

- Emergency Medical Services

- Non-Emergency Patient Transport Services

- Emergency Medical Retrieval Transfer Services

The EASC 2020/21 IMTP will also contain details on the collaborative commissioning process to be followed to develop the following new services:

- National Transfer & Discharge Services

- National Critical Care Transfer Services

The EASC 2020/21 IMTP will outline the mechanism for ensuring performance is delivered in line with the commission intentions and the available financial envelope and expectations. It will also contain the additional resources implications for the NCCU EASC Commissioning Team and regulatory requirements as outlined in newly issued EASC Standing Orders.

WAST IMTP 2020/21-23

WAST have indicated their intention to refresh their approved 2019/20 IMTP for 2020-23. EASC approval of their refreshed plan will be contingent on the commitment to delivery of the actions contained within their approved 2019/20 IMTP. WAST will continue their commitment to progress and deliver the 2019/20 commissioning intentions.

EASC expectations are that the WAST 2020/21 refreshed IMTP will contain the following:

- WAST Action Plans for EMS & NEPTS:

  - Framework Improvements

- WAST Performance Improvements

- Joint Performance Improvements

- Financial Plans in response to the Financial Assumptions for EMS & NEPTS (including inflationary uplifts)

- Reporting mechanism & frequency on progress against action plans

- Mechanisms for shifting proportion of front line spend in line with 2013/14 levels and targeting a reduction in non-front line spend.

Health Boards IMTPs 2020/21-23

The EASC Commissioning Team will support local IMTP development by drafting the narrative around core EASC Commissioned Services. The Health Board IMTP’s will contain the following:

- Health Board Action Plan for EMS & NEPTS:

- Joint Performance Improvements

- Financial Plans in response to the Financial Assumptions for EMS, NEPTS & EMRTS (including inflationary uplifts)

- Reporting mechanism & frequency on progress against action plans.

- Joint Initiatives requiring WAST, EASC Commissioning Team and Health Board collaboration.

Table 3 outlines the timescales for development of the process illustrated above (Figure 1):

Table 3

| EASC Commissioned Services |  |
| --- | --- |
| Date | Completed |
| By end of October 2019 | - A mid-year progress review of IMTP was completed by 12th October 2019 for EMS (Appendix 1) & NEPTS (Appendix 2); it included: - Framework Improvements - WAST Performance Improvements |
|  | Next Steps |
|  | - Awaiting a WAST response on mid-year progress Review. - Joint Performance Improvements to be reviewed & updated by WAST (Appendix 3) |
| By end of November 2019 | - Discussion and presentation on 2020/21 Commissioning Intentions on EASC Commissioned Services. - Progress report by 12/11/2019 to EASC on: - Commissioning Intentions and Financial Assumptions for EASC Commissioned Services - EASC IMTP 2020/21 - Update / Refresh of EMS & NEPTS Commissioning Intentions to be undertaken with WAST. - EASC Management Group to finalise 2020/21 EMS & NEPTS - Commissioning Intentions - Financial Assumptions - NCCU circulate agreed 2020/21: - Commissioning Intentions EMS & NEPTS - Financial Assumptions for EASC Commissioned Services - Guidance notes to inform IMTP planning for EASC Commissioned Services |
| By 28 January 2020 | - Report to EASC for noting on final Commissioning Intentions & EASC/NCCU IMTP - Report to EASC on potential approval of WAST 2020/23 IMTP |
| By end of January 2020 | - Submit EASC/NCCU IMTP to Welsh Government |

Lessons Learned

We have clearer insight into the resource requirements to deliver Collaborative Commissioning of EASC Commissioned Services through, for example; the production of the Relief Gap: reference document that was circulated to EASC members and Welsh Government.

This issuing of annual Commissioning Intentions, Financial Plans and the monitoring of progress against these plans enables Health Boards as commissioners to exercise their responsibilities and drive improvement locally.

The NCCU Commissioning Team on behalf of the CASC will develop strategic commissioning plans for EASC Commissioned Services enabling long term ambitions and improvements to be realised.

NCCU Commissioning Team on behalf of the CASC will continue to support IMTP development across all Health Board areas as outlined within this paper.

The NCCU Commissioning Team will also work collaboratively with WAST and Health Boards to develop the mechanisms that underpin robust performance improvement for EASC Commissioned Services.

EASC are committed to honouring the work identified in its commissioning intentions and will reflect this within its 2020/21 IMTP.

4.   RECOMMENDATION

Members of the Emergency Ambulance Services Committee are asked to:

- APPROVE the proposed approach to the Commissioning Intentions for EASC commissioned services and their alignment with Welsh Ambulance Services NHS Trust (WAST) and Health Board Integrated Medium Term Plans (IMTPs).

- DISCUSS & ENDORSE the content of presentation on the 2020/21 Commissioning Intentions.

| Freedom of information status | Open |
| --- | --- |

Appendix 1: Mid-year progress review of EMS Framework Improvements and Performance improvements

| Reference | CAREMORE™ | 5 Step Model | Area | Carried over from 2018/19 | Description | Lead | Timescale | Status | Q1 & Q2 updates |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Framework Improvements | Resource Envelope | Across the steps | Update Framework Agreement | No | Review of 2018/19 IMTP financial assumptions and financial plan versus forecast outturn for 2018/19 and 2019/20 financial assumptions and financial plan. | Chris Turley | <3 Months | Completed | Within Quality & Delivery Framework |
| Framework Improvements | Resource Envelope | Across the steps | Update Framework Agreement | No | Financial Value Payable by EASC and associated assumptions. | Chris Turley | <3 Months | Completed | Within Quality & Delivery Framework |
| Framework Improvements | Model of Care | Across the steps | WAST Improvement | Yes | [Carried Forward from 2018/19] Fleet and staff mix to be reviewed for each health board area tailoring the delivery of the 5 Step Ambulance Patient Pathway to local population needs. | Rachel Marsh | <12 Months | Unknown | Position unknown |
| Framework Improvements | Operational Arrangements | Across the steps | Update Framework Agreement | No | Operational arrangements to be reviewed by EASC on an ongoing basis | Julian Baker | <3 Months | Completed | Management Team Stakeholders |
| Framework Improvements | Operational Arrangements | Across the steps | Update Framework Agreement | No | Progress review of 2018/19 IMTP actions | Rachel Marsh | In Place | Completed | Within IMTP |
| Framework Improvements | Operational Arrangements | Across the steps | Update Framework Agreement | No | Inclusion of completed IMTP 2019/20 tables following EASC IMTP approval | Rachel Marsh | <3 Months | Completed | Within IMTP |
| Framework Improvements | Review of Performance | Across the steps | Update Framework Agreement | No | Data repository covering A1 Activity, RE1 Resource Envelope, R1 Performance Measures, including the AQIs, to be utilised with when, who, when specifically stated. | Rachel Marsh | <6 Months | Ongoing | Ongoing discussions, Hugh Bennett leading |
| Framework Improvements | Review of Performance | Across the steps | Update Framework Agreement | No | Trigger points which indicate poor deteriorating performance against performance metrics within the data repository to be identified by CASC and specific actions to warrant corrective action identified | Julian Baker | <3 Months | Ongoing | Ongoing discussions, Ross Whitehead leading |
| Framework Improvements | Review of Performance | Across the steps | Update Framework Agreement | No | The reporting against core requirements to be undertaken twice per year as described under the Commissioning Intention for Care Standards | Rachel Marsh | <12 Months | Unknown | Position unknown |
| Framework Improvements | Review of Performance | Across the steps | Update Framework Agreement | No | Development of local measures by Health Board | Rachel Marsh | <6 Months | Ongoing | Workshop booked for 28/10/19 |
| Framework Improvements | Review of Performance | Step 4 | Update Framework Agreement | Yes | [Carried Forward from 2018/19] Call to door times for STEMI (pPCI door) and Stroke to be produced. | Chris Turley | <3 Months | Unknown | Position unknown |
| Framework Improvements | Review of Performance | Step 4 | Update Framework Agreement | No | Development of Clinical Indicators which compliment the benefit realisation assumptions for Band 6 Paramedic investment to be produced. | Rachel Marsh | <3 Months | Unknown | Position unknown |
| Framework Improvements | Activities | Step 2 | Update Framework Agreement | No | Clinical Support Desk : Patient demographics recording to be improved to support patient identifier for linked data | Chris Turley | <6 Months | Ongoing | No change |
| Framework Improvements | Activities | Step 2 | Update Framework Agreement | No | Clinical Support Desk: Clinical Desk activity types to reflect all activity undertaken. | Chris Turley | <6 Months | Improved | review ongoing on role of Clinical Desk |
| WAST Performance Improvements | Resource Envelope | Across the steps | WAST Improvement | Yes | [Carried Forward from 2018/19]: Resource utilisation will improve: * sickness rates reduced for all direct staff across each of the steps * overtime use to reduce * use of external providers to be reduced * rosters aligned to demand (across days and time of day) for direct staff across each step * compliance with planned (that is the new) rosters to increase | Claire Roche | <6 Months | Deterioration | Resource utilisation not improving |
| WAST Performance Improvements | Resource Envelope | Across the steps | WAST Improvement | No | Proportion of spend will shift from Steps 5 & 4 to Steps 3 & 2 | Chris Turley | <12 Months | Ongoing | work in progress - awaiting information from Jason Collins |
| WAST Performance Improvements | Resource Envelope | Across the steps | WAST Improvement | No | Reduced spend on operating expenses | Chris Turley | <12 Months | Ongoing | work in progress - awaiting information from Jason Collins |
| WAST Performance Improvements | Resource Envelope | Across the steps | WAST Improvement | No | Known ‘Net Effect’ in terms of activity impact, resource impact and performance impact from all initiatives | Julian Baker | >12 Months | Deterioration | Red & Amber performance deteriorating. Awaiting July to September data |
| WAST Performance Improvements | Review of Performance | Step 2 | WAST Improvement | No | Time to allocation for Red calls to reduce | Claire Roche | In Place | Ongoing | Ongoing work taking place - metric to be produced |
| WAST Performance Improvements | Review of Performance | Step 2 | WAST Improvement | No | The volume of calls assessed and closed by the clinical desk to increase | Claire Roche | In Place | Improved | Number of Calls: April - 2019, May - 1850, June 1911. July to September data to be produced slight improvements seen but part of ongoing work |
| WAST Performance Improvements | Review of Performance | Step 3 | WAST Improvement | No | Multiple vehicle arrivals at scene to reduce for Amber and Green Incidents | Claire Roche | In Place | Ongoing | Number of Vehicles: April - 21757, May - 22321, June - 20999. July to September data to be produced Improvements being made, although still work in progress |
| WAST Performance Improvements | Review of Performance | Step 3 | WAST Improvement | No | The percentage of incidents where the first arriving vehicle is the ideal to increase | Claire Roche | In Place | Ongoing | Ideal Responses:- AMBER: April 68.1%, May 69%, June 67.9%. GREEN2 April 57%, May 58.5%, June 59.4%. GREEN3 April 65%, May 65.1%, June 67.4%. July to September data to be produced, however signs of improvements being made, although still work in progress |
| WAST Performance Improvements | Review of Performance | Step 3 | WAST Improvement | No | Red performance to be maintained and the 95th percentile to reduce | Claire Roche | In Place | Deterioration | 95% (in seconds): April - 992, May - 963, June - 964. July to Sept to be produced however it is known to show a deterioration in performance |
| WAST Performance Improvements | Review of Performance | Step 3 | WAST Improvement | Yes | [Carried Forward from 2018/19] Amber 95th percentile times to reduce across each health board | Claire Roche | In Place | Deterioration | 95% (in seconds): April - 11212, May - 9699, June 10316. July to Sept to be produced however it is known to show a deterioration in performance |
| WAST Performance Improvements | Review of Performance | Step 4 | WAST Improvement | Yes | [Carried Forward from 2018/19] 95th percentile call to door times (STEMI & Stroke) to reduce across each health board area | Claire Roche | In Place | Unknown | Position unknown, metric still to be produced |
| WAST Performance Improvements | Review of Performance | Step 4 | WAST Improvement | Yes | [Carried Forward from 2018/19] Clinical Indicator performance to improve, and be above 95% in all health board areas (except ROSC) | Brendan Lloyd | In Place | ongoing | Ongoing work, although there are signs of improvements being seen over recent months. |
| WAST Performance Improvements | Review of Performance | Step 5 | WAST Improvement | Yes | [Carried Forward from 2018/19] Handover to clear times to reduce across all health board areas | Claire Roche | In Place | Improved | April - 74.3%, May - 75.8%, June - 82.5%: July to Sept to be produced, however figures show an increase in handover to clear within 15 mins |

.

Appendix 2: Mid-year progress review of NEPTS Framework Improvements and Performance improvements

| Reference | CAREMORE™ | 5 Step Model | Summary | Full Description | Lead | Timescale | Status | Q1 & Q2 updates |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Framework Improvements | Activities | Across the steps | Data repository | Data repository aligned to report activity against relevant step | Nicola Bowen - NEPTS Head of Transformation | <12 Months | ongoing | Undertaking a review of progress to date |
| Framework Improvements | Activities | Step 1 | Activity Step 1 | Step 1 - Ensure NEPTS specific engagement activity can be identified | Nicola Bowen - NEPTS Head of Transformation | <6 Months | improved | Current activity defined. Transport Solutions proposal will aid this |
| Framework Improvements | Activities | Step 4,Step 5 | Activity Step 4&5 | Step 4/5 – ensure activity is clearly described within the relevant step | Nicola Bowen - NEPTS Head of Transformation | <3 Months | ongoing | Ongoing work but to be scoped fully by end October 19 |
| Framework Improvements | Resource Envelope | Across the steps | Expenditure by HB across 5 steps | Develop infrastructure to be able identify how much is spend at a HB level across the 5 steps | James Haley - Finance Business Partner | >12 Months | Unknown | Local Measures in place to montior this alongside transfer of work. To date only 3 HB left to transfer: AB, CTMUHB & PTUHB |
| Framework Improvements | Resource Envelope | Across the steps | 2018/19 Financial Assumptions and Plan vs 2019/20 | Review of 2018/19 IMTP financial assumptions and financial plan versus forecast outturn for 2018/19 and 2019/20 financial assumptions and financial plan | James Haley - Finance Business Partner | <3 Months | ongoing | review of financial plan in progress |
| Framework Improvements | Resource Envelope | Across the steps | Financial value payable by EASC | Financial Value Payable by EASC and associated assumptions | James Haley - Finance Business Partner | <3 Months | completed | ongoing review, forms part of EASC discussions |
| Framework Improvements | Model of Care | Across the steps | Wiring diagram | Model of Care wiring diagram updated following implementation of plurality model. | Nicola Bowen - NEPTS Head of Transformation | >12 Months | ongoing | Position unknown - work outstanding |
| Framework Improvements | Operational Arrangements | Across the steps | 02 Schedule | Update O2 Schedule – Application of the Model of Care following enactment of plurality model for each HB | Nicola Bowen - NEPTS Head of Transformation | >12 Months | improved | Last update of 02 schedules completed June 2019. 3 Health Boards yet to submit, although work in progress - AB, CTMUHB & PTUHB |
| Framework Improvements | Operational Arrangements | Across the steps | 03 Schedule | Update O3 Schedule – extant policies, protocols & pathways following enactment of plurality model for each HB | Nicola Bowen - NEPTS Head of Transformation | >12 Months | Unknown | Outstanding until the development of the national model - in progress |
| Framework Improvements | Operational Arrangements | Across the steps | Operational Arrangements | Operational arrangements to be reviewed by EASC on an ongoing basis. | James Rodaway - NCCU Head of Commissioning & Programming | In Place | completed | Operational Groups set up, NEPTS DAG and Management Group |
| Framework Improvements | Operational Arrangements | Across the steps | 2019-22 IMTP Actions | IMTP 2019/20 tables following EASC IMTP Inclusion of completed approval | Mark Harris - Interim Deputy Director | >12 Months | completed | Work in progress - summaries to be provide to HB's to help shape HB's IMTP Project Proposals |
| Framework Improvements | Operational Arrangements | Across the steps | Commissioning Templates | NEPTS QDF to be signed December 2018. | TBC - Planning & Performance | <3 Months | completed | NEPTS QDF produced, with WAST for signing |
| Framework Improvements | Operational Arrangements | Step 3,Step 4,Step 5 | Provider Framework | To record and manage the framework of providers used to deliver the NEPTS plurality model. | Nicola Bowen - NEPTS Head of Transformation | >12 Months | ongoing | Lyndon Powell undertaking work to provide robust information with all providers. Moving across to 365. Also the development of Dynamic Purchasing Procurement Framework will support this |
| Framework Improvements | Review of Performance | Across the steps | R2 Schedule | Develop Schedule R2: Data repository covering A1 Activity, RE1 Resource Envelope, R1 Performance; enabling self-assessment against the Core Requirements of Care Standards; plus local measures by organisations. | Nicola Bowen - NEPTS Head of Transformation | <12 Months | ongoing | Internal work being undertaken in WAST to develop further but will be managed as part of the QDF |
| Framework Improvements | Review of Performance | Across the steps | Data Repository | Maintain data repository covering A1 Activity, RE1 Resource Envelope, R1 Performance Measures | Nicola Bowen - NEPTS Head of Transformation | <12 Months | ongoing | Internal work being undertaken in WAST to develop further but will be managed as part of the QDF |
| Framework Improvements | Review of Performance | Across the steps | Self Assessment of Care Standards | WAST undertake self-assessment related to the Core Requirements in Care Standards | Nicola Bowen - NEPTS Head of Transformation | <6 Months | Unknown | Position unknown |
| Framework Improvements | Evaluation | Across the steps | Baseline Data | Recording of baseline data for all NEPTS activity& resources for each HB. | Nicola Bowen - NEPTS Head of Transformation | In Place | ongoing | work in progress as part of the Transfer of Work. 3 Health Boards to transfer across |
| Framework Improvements | Evaluation | Across the steps | Role of PDEG | Evaluation programme for NEPTS overseen by PDEG | Hugh Bennett - Assistant Director Performance & Commissioning | <12 Months | Unknown | Position unknown - work outstanding |
| Framework Improvements | Evaluation | Across the steps | Evaluation Programme | Creation of Evaluation methods and programme of work. | James Rodaway - NCCU Head of Commissioning & Programming | <6 Months | Ongoing | EASC researcher being appointed through C3 Faculty |
| WAST Performance Improvements | Care Standards | Step 1 | Care Standards | Compliance with care standards for previously extant Health Board/WHSSC/Velindre services | Nicola Bowen - NEPTS Head of Transformation | >12 Months | Unknown | Position unknown |
| WAST Performance Improvements | Resource Envelope | Across the steps | Review of Business Case | Development of a fully costed business case to meet the Cabinet Secretary expectations from the 2015 business case. | Mark Harris - Interim Deputy Director | <3 Months | ongoing | Transport Solutions proposals agreed |
| WAST Performance Improvements | Resource Envelope | Across the steps | WAST Resources | Demonstrate WAST NEPTS resources are being utilised effectively following transfer of HBs. | James Haley - Finance Business Partner | >12 Months | ongoing | Transfer of Work providing greatly clarity and quality of data (includes in and out of scope). To date only 3 HB left to transfer: AB, CTMUHB & PTUHB |
| WAST Performance Improvements | Operational Arrangements | Across the steps | Quality Assurance | WAST to ensure robust quality assurance to manage providers required to deliver the plurality model | Nicola Bowen - NEPTS Head of Transformation | >12 Months | ongoing | Lyndon Powell undertaking work to provide robust information with all providers |
| WAST Performance Improvements | Operational Arrangements | Across the steps | Internal Audit recommendations | Implement improvements identified within the Internal Audit of NEPTS provision November 2018. | Mark Harris - Interim Deputy Director | <12 Months | improved | improvements being delivered consistently |
| WAST Performance Improvements | Review of Performance | Across the steps | Core requirements | Compliance with core requirements of care standards reported on a six monthly basis. | Nicola Bowen - NEPTS Head of Transformation | <12 Months | Unknown | Position unknown |
| WAST Performance Improvements | Review of Performance | Across the steps | Improvement in Activity Performance | WAST to demonstrate how activity performance is improved in each HB following enactment of the plurality model. | Nicola Bowen - NEPTS Head of Transformation | >12 Months | ongoing | In progress - will be completed once Transfer of Work undertaken - 3 Health Boards left to transfer (AB, CTMUHB & PTUHB) |
| WAST Performance Improvements | Review of Performance | Across the steps | Improvement in Efficiencies | WAST to demonstrate savings and efficiencies in each HB following enactment of the plurality model | James Haley - Finance Business Partner | >12 Months | Unknown | In progress - will be completed once Transfer of Work undertaken - 3 Health Boards left to transfer (AB, CTMUHB & PTUHB) |
| WAST Performance Improvements | Review of Performance | Across the steps | Staff Experience | Report & consider improvements following measuring staff experience | Mark Harris - Interim Deputy Director | <12 Months | ongoing | work in progress |
| WAST Performance Improvements | Review of Performance | Across the steps | Patient Experience | Report & consider improvements following measuring patient experience. | Mark Harris - Interim Deputy Director | <12 Months | ongoing | work in progress |

Appendix 3: Mid-year progress review of EMS & NEPTS Joint Performance improvements

| CAREMORE | 5 Step Model | NEPTS/EMS | Short Title | Summary Description | Organisation | Operational Leads | Timescale | Implementation Stage | Implementation Comment | Q1 & 2 updates |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| to be confirmed |  | to be confirmed | Further enhance access to Alternative Pathways of Care | Work closely with Health Board leads to identify opportunities to enhance and develop Alternative Care Pathways. Actions to include: (i) Monitoring referral and compliance of established ACPs, (ii) Review WAST & ABM data to identify opportunities to develop new ACPs (iii) Undertake an evidence based approach to establish new ACPs based upon clinical need. | ABUHB | Jeff Morris | <12 Months | Planned Roll Out | Pathways will be implemented on an individual basis as per the agreed roll out plan | Due mid November 2019 |
| to be confirmed | Step 1 - Help me to choose | to be confirmed | Frequent Callers - Phase 2 | Phase 2 scoping: Nursing/care homes to avoid unnecessary 999 calls & admission to hospital. Working in partnership with 53 care homes within Aneurin Bevan, I stumble, manger elks, aeds, education & support. | ABUHB | Ken Smith |  |  | Planning / local HB implementation | Due mid November 2027 |
| to be confirmed | Step 4 - Give me treatment | to be confirmed | ETTF Telemetry Project: Telemetry of Diagnostic ECGs direct to Primary Percutaneous Coronary Intervention Facilities | To improve early recognition of cardiac conditions in the community / aligned to national delivery plans e,g, identifying new AF cases. Paramedic interpretation of ECG with ability for clinicians at receiving unit to view ECG via telemetry to inform clinical decisions. Phase 3 roll out to GPs - pathway complete, awaiting GPC Wales confirmation. | ABUHB | Greg Lloyd |  |  | Gone live in tertiary centre (UHW). Phase 3 implementation discussions - awaiting GPC Wales confirmation | Due mid November 2028 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Falls | Falls Vehicle: Operational 7 days a week, (aligned with community resource teams) Paramedic and Physiotherapist on a Specialised Falls Vehicle adapted to store additional equipment and full paramedic kit as per RRV. Emergency response capable. Falls Tier 1 assistants for winter period. Consider in context of Strategic Falls WAST work and any further opportunities. | ABUHB | James Gough | In Place |  | Live | Due mid November 2029 |
| to be confirmed |  | to be confirmed | Potential roll out of 111 | Roll out 111 within AB | ABUHB | Chris Powell |  |  | As per national programme | Due mid November 2030 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Pathways | Programme to review and where necessary refresh pathways including trauma, obs & gynae, ENT, back pain | ABUHB | Tim Rogerson |  |  | Live | Due mid November 2031 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Changes to the provision of obstetrics, neonatal, gynae and paediatric services | Planning for any potential interim solution, prior to relocation to The Grange Hospital | ABUHB | Deborah Kingsbury |  |  | Contingency planning | Due mid November 2032 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Vascular (arterial surgery) | Centralisation of arterial vascular surgery in South East Wales | ABUHB | Ian Morris |  |  | Plannng stage | Due mid November 2033 |
| to be confirmed | Across the Steps | to be confirmed | Clinical Futures Strategy | Clinical Futures Strategy overarching clinical, workforce and estates strategy that encompasses reconfiguration of primary, community, LGHs and the development of The Grange University Hospital | ABUHB | Sarah Parks Jones |  |  | Planning stage | Due mid November 2034 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | HCP Pilot | Pilot to diarise HCP admissions utilising booked UCS crews | ABUHB | Rachel Taylor |  |  | Winter pilot | Due mid November 2035 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Acute Coronary Syndrome Pathway Development | Redesign Acute Coronary Syndrome service to meet the NICE guidelines for the ACS pathway for Heart Disease. The ACS pathways pilot has seen a reduction in referral to transfer times down to 2 days in 2017. Further evaluation will take place ahead of potential roll out in 2018 Dedicated transport being piloted for 3 months as part of pathway. | ABUHB | Paula Goode |  |  | Transport pilot 3 months intitially, continued as cost pressure. | Due mid November 2036 |
| to be confirmed |  | to be confirmed | APP | Further roll out of Advanced Paramedic Practitioners into ABUHB following pilot. Pilot Operational 18 hours per day 7 days a week. APPs rotate between Clinical Contact Centre (CCC) and operational RRV. APP in CCC dispatches APPs in RRV to ensure tasked with most appropriate calls. | ABUHB | Mike Jenkins |  | Planned Roll Out |  | Due mid November 2037 |
| to be confirmed |  | to be confirmed | Frailty | Development of direct access pathway to frailty beds, advanced care plans and end of life care. | ABUHB | Sian Millar |  |  |  | Due mid November 2038 |
| to be confirmed |  | to be confirmed | Physician Response Unit (PRU) | WAST provide vehicle, equipment, PPE for consultants and RRV paramedic. LHB provide consultant from Nevill Hall 9-5 (approx 3 days) and any other equipment & medications. Additional appropriate jobs selected from stack. If patient requires admission then patient can be referred direct to appropriate speciality team therefore bypassing ED. | ABUHB |  |  |  | Live | Due mid November 2039 |
| to be confirmed | Step 2 - Answer my call | to be confirmed | Frequent Callers - Phase 2 | Work in Wrexham and Flintshire to provide basic first aid training by CFRs in nursing homes, which has had a positive impact on call numbers. Linked to Community Team. Joint work to identify top 10 Nursing Homes and measure admissions - link with Integrated Clinical Hub. Monthly meeting to consider frequent calls by nursing and residential care settings. Group reports formally to BC UHB West Area Director and BC UHB Clinical Director. ISTUMBLE model shared amongst BCUHB colleagues and BC UHB Conwy Falls Group. Frequent caller work also undertaken with Vulnerable Adult Review Meetings chaired by N Wales Police and being piloted in Anglesey area - suggests expansion across BC UHB. Work completed to identify FCs across Anglesey, N Gwynedd, Conwy and Denbighshire over 12 month period (Dec 2016 - Nov 2017) and common themes. Monthly frequent caller group established at Ysbyty Gwynedd Hospital chaired by an ED consultant. Referals to most appropriate agency for support, with collective support of the group. Contact with GP practice is integral to the process. | BCUHB | Liz Hughes | > 12 Months | Active Development | Pilot areas | Due mid November 2040 |
| to be confirmed |  | to be confirmed | ETTF Telemetry Project: Telemetry of Diagnostic ECGs direct to Primary Percutaneous Coronary Intervention Facilities | To improve early recognition of cardiac conditions in the community / aligned to national delivery plans e,g, identifying new AF cases. Paramedic interpretation of ECG with ability for clinicians at receiving unit to view ECG via telemetry to inform clinical decision at LHB area. The funding for the project is until end March 2019 and WAST is currently collating the data that will inform the decision as to whether this is handed over as business as usual from 1st April 2019. | BCUHB | Greg Lloyd |  | Active Development |  | Due mid November 2041 |
| to be confirmed | Across the Steps | EMS | Single Integrated Clinical Assessment and Triage (SICAT) Hub | Other actions in this template support the development of the SICAT. This brings together work on the Clinical Desks and health board Clinical Hubs. SICAT clinicians provide secondary clinical assessment and triage for 999 calls (including HCP calls) and calls from WAST operational crews on scene with patients. APPs in the CCC will identify suitable calls on the WAST stack for enhanced triage to be undertaken by BC UHB clinicians. | BCUHB | Mark Timmins | > 12 Months | Fully Embedded | Fully embedded. Phased implementation building on phase 1 which is currently in place: - improved integration between WAST and OOH to maximise use of alternative pathways: Oct 2018 to Jan 2019 - development of a physical contact centre for SICAT: Oct 2018 to Jan 2019 - review of pathways for Mental Health, Falls, MIU and District Nursing: Oct 2018 to Jan 2019 | Due mid November 2042 |
| to be confirmed | Across the Steps | EMS | Advanced Paramedic Practitioners | Following the successful 5 month study pilot in BC UHB area with 10 APPs, this will be rolled out on a permanent basis across BC UHB. The business case outlines a rotational model and 3 year Pacesetter funding was received for the APP pilot to support the provision of Primary Healthcare. A joint WAST/HB project group is currently being established. | BCUHB | Andy Swinburn | <12 Months | Active Development | 2019-20 | Due mid November 2043 |
| to be confirmed | Step 1 - Help me to choose | to be confirmed | Preparatory work for 111 | National programme timescales in development. WAST and health board to work together to prepare for implementation once timescales confirmed. Current timeline is suggesting that the 111 programme will be completed in Q3/4 of 2020-21. It is necessary to confirm anticipated dates so that the preparatory work can be scoped. | BCUHB | Chris Powell | > 12 Months | Planned Roll Out | Preparation actions - in line with national programme timescales | Due mid November 2044 |
| to be confirmed | Step 2 - Answer my call | to be confirmed | Develop the alcohol treatment centre model | Alcohol Treatment Centre in Wrexham (Wrexham Welfare Centre). This project is supported by WAST, BC UHB and the Local Authority on a seasonal basis with the service delivered by The British Red Cross. There is anecdotal evidence of its success as a concept and initial data shows that A&E attendances are reduced (Jan - Oct 2018: 12,742 people treated; 56 ambulances cancelled or referred to more appropriate alternatives). It should be noted that the centre also impacts on the wider drug and alcohol agenda as part of the North Wales Area Planning Board (APB) work on Reducing Harm from Alcohol programme. Projects may also flex up and down in different areas such as Rhyl on a less frequent basis, depending on service need. | BCUHB | Vicky Jones | > 12 Months | Active Development | Testing in Practice | Due mid November 2045 |
| to be confirmed | Across the Steps | to be confirmed | Maximising utilisation of GP OOH pathways | GP OOH provision in Emergency Dept OOH. Standardisation of criteria across EDs. Linked to SICAT and directory of services. Part of current 90 day planning includes feasibility study to understand the potential increases in Primary Care capacity through use of Tele Health for urgent referrals. Work commenced in October 2018 and will continue into 2019 - immediate focus on reviewing existing business case for use of telehealth, engagement with GP clusters and options appraisal with associated scale and scope of benefits. | BCUHB | Meinir Williams, Duncan Robertson | <12 Months | Testing in Practice | Active Development | Due mid November 2046 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Develop and implement new alternative care pathways | The following care pathways are now in place: GGP & OOH/drug & alcohol/cardiac care/COPD/epilepsy/falls/diabetic/midwife/palliative care/mental health/specialist practitioner/mental health/social care. A reporting template/data set is being developed to assess the referral rates from ambulance crews. Referral pathways and improving their utilisation is also be a project under the BCUHB Unscheduled Care Programme. This action is being delivered to plan and is a core work stream within the BCU USC Transformation Programme with a specific 90 Day Action Plan concerning Clinically Safe Admission Avoidance. Existing performance has been baselined and a stretch target set for Q3 of increasing MIU utilisation by 25% | BCUHB | Duncan Robertson, Meinir Williams | <12 Months | Active Development | Testing in Practice | Due mid November 2047 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Implement referral pathway for mental health | Mental health pathway in place with Glan Clwyd Hospital and went live on 20th November 2017. The on call Psychiatric Liaison Team Professional will discuss the case with the referring paramedic. Over the Christmas period a pilot was put in place across police, clinicians and mental health. There is an opportunity to widen out to CAMHS. Referral of patients to other healthcare professionals in appropriate setting. Some further work being done around real time utilisation of pathways and information on use. Need to publicise pathways. Awaiting confirmation of HB colleagues of capcity to support MH Pathway in West and East (pathway is ready to be implemented once assurance of capacity in the system to support referrals) | BCUHB | Jon Sweet, Chris Lines | <12 Months | Testing in Practice | Testing in Practice | Due mid November 2048 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Implement referral pathway for MIU | MIU pathways in place with a need for increased number of conveyances via this route. WAST has developed and distributed the policy to crews and work is ongoing to ensure that access to MIUs is supported by appropriately trained staff and services. Some further work being done around real time utilisation of pathways and information on use. Need to publicise pathways. | BCUHB | Jon Sweet, Chris Lines, Meinir Williams | <12 Months | Testing in Practice | Testing in Practice | Due mid November 2049 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Rapid handover - Paramedic Pathfinder to be implemented in Ysbyty Gwynedd and Ysbyty Glan Clwyd EDs | Maximising the utilisation of existing pathways of care supported by use of Paramedic Pathfinder. Rapid handover to be explored in further detail by both WAST and health board - consideration of Fit to Sit and assessment in ED to progress 15minute handover - part of the Unscheduled Care Programme. Working with Ysbyty Glan Clwyd to work up rapid handover protocols and training for ED staff in early 2019. Paramedic Pathfinder is for our paramedics to use to triage patients, we are emphasising the pathfinder through the B5-6 competencies this year (Ieuan copied in has details). New paramedics are being trained on Pathfinder as part of their conversion course. | BCUHB | Duncan Robertson | <12 Months | Fully Embedded | Planned Roll Out | Due mid November 2050 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Falls pathways | CAT pilot has ended and there is a need to link in with the national WAST falls work. The health board and WAST will work together to determine the model required and this may require additional resource. CFRs currently being issues with Manger Elk lifting devices and trained in their use along with diagnostic equipment to assist with clinical assessment support from CCCl. WAST in early liaison with health board re falls management as part of unscheduled care programme. WAST CFRs continue to be utilised as Tier 1 falls response with additional resources from BC UHB primary care and community services being identified who could also provide Tier 1 response e.g. Anglesey Night Owls. Resource mapping exercise to be completed identifying additional resources. | BCUHB | Gareth Evans | > 12 Months | Planned Roll Out | Planned Roll Out | Due mid November 2051 |
| to be confirmed | Across the Steps | to be confirmed | Service change across the BC UHB region | Unscheduled care system - work streams split between 2 AOM's in the North. Liz Hughes to lead on SICAT and represent WAST on the Unscheduled care board (USB) and Jon Sweet to lead on Pathway utlisation. All tasks from the USB to be reported via feedback after each meeting. | BCUHB | Jon Sweet, Liz Hughes, Jo Williams, Rob Smith | <12 Months | Fully Embedded | Fully embedded | Due mid November 2052 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service change across the BC UHB region | Stroke and thrombectomy services - health board currently considering options for acute and hyper acute stroke care, as well as wider model for rehabilitation. WAST is engaged in this work | BCUHB | Jon Sweet, Liz Hughes, Jo Williams, Wendy Hooson | > 12 Months | Planned Roll Out | Planned Roll Out | Due mid November 2053 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service change across the BC UHB region | Vascular surgery - changes due to be implemented in April 2019 with centralisation at YGC. Hybrid theatre currently in development. WAST working with the health board to identify potential patient numbers, and clinical flows. | BCUHB | Jon Sweet, Liz Hughes, Jo Williams, Jo Garzoni | <6 Months | Planned Roll Out | Planned Roll Out | Due mid November 2054 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service change across the BC UHB region | Orthopaedics - potential three year move from 5 sites to 3. FURTHER DETAIL TO BE PROVIDED | BCUHB |  | <12 Months | Planned Roll Out | Planned Roll Out | Due mid November 2055 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service change across the BC UHB region | Orthopaedics - potential three year move from 5 sites to 3. FURTHER DETAIL TO BE PROVIDED | BCUHB |  | <12 Months | Planned Roll Out | Planned Roll Out | Due mid November 2056 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service change across the BC UHB region | Urology. FURTHER DETAIL TO BE PROVIDED | BCUHB |  | <12 Months | Planned Roll Out | Planned Roll Out | Due mid November 2057 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service change across the BC UHB region | Eye care - provision of some ophthalmology services closer to home. FURTHER DETAIL TO BE PROVIDED | BCUHB |  | <12 Months | Planned Roll Out | 0 | Due mid November 2058 |
| to be confirmed |  | to be confirmed | Falls pathway development | Pathway to be reviewed , also considering models across Wales as part of the Falls Framework developed within WAST and implementation of the falls assistant pilot for winter 2018/19. Needs consideration jointly with CT Transformational plan; Stay Well in Your Community. Also work in partnership with regards the roll out of the virtual ward. | CTMUHB | Sonia Thompson |  |  | Planning stage | Due mid November 2071 |
| to be confirmed | Across the Steps | to be confirmed | Potential roll out of 111 | Implementation of the national 111 programme in the C&V area - this is subject to nationally agreed timescales and will be updated once confirmed dates are known. | CTMUHB | Chris Powell |  |  | Planning stage | Due mid November 2072 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service reconfiguration: Vascular (arterial surgery) | Centralisation of arterial vascular surgery in South East Wales | CTMUHB | Deb Lewis |  |  | Planning stage | Due mid November 2073 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service reconfiguration: Major Trauma | Live major trauma network by October 2019 and functioning major trauma centre at UHW and designated trauma units by April 2020. | CTMUHB | Jonathan Watts |  |  | Planning stage | Due mid November 2074 |
| to be confirmed |  | to be confirmed | Changes to the provision of obstetrics, neonatal and paediatric services | Implementation of the recommendations of the South Wales Programme; centralisation of paediatric inpatient services at Prince Charles with a Paediatric Assessment Unit developed at Royal Glamorgan Hospital . Centralisation of obstetric services at Prince Charles Hospital with a free standing midwifery unit at the Royal Glamorgan | CTMUHB | Deborah Kingsbury |  |  | Planning stage | Due mid November 2075 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Acute Coronary Syndrome Pathway Development | Redesign Acute Coronary Syndrome service to meet the NICE guidelines for the ACS pathway for Heart Disease. The ACS pathways pilot has seen a reduction in referral to transfer times down to 2 days in 2017. Further evaluation will take place ahead of potential roll out in 2018. Dedicated transport piloted as part of pathway. | CTMUHB |  | In Place |  | Transport pilot 3 months extended through non recurrent funding. Business case being prepared to EASC for additional funding to continue on a permanent basis | Due mid November 2076 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Boundary change in Bridgend & Ambulance handovers policy, review of explorer 3. | Ambulance handover and our continued work to ensure that we adopt a zero tolerance approach to ambulance delays across the Cwm Taf area – implicit in this statement is the need to work with POW post transferring into the Cwm Taf management area. Continue to engage and support the future planning and manage the operational impacts of the Bridgend Locality boundary change to Cwm Taf UHB. | CTMUHB | Jonathan Watts | In Place |  | Live | Due mid November 2077 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | ENT | Reconfiguration of ear, nose and throat (ENT) services within CT; hub & spoke model. Hub at Royal Glam for adults and paediatrics at POW TBC | CTMUHB | Greg Lloyd |  |  | Planning stage | Due mid November 2078 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Orthopaedics | Implications of Rapid review of Orthopaedic services undertaken by GIRFT. Proposed model for PCH and POW to receive HOT, RGH to be cold only. | CTMUHB | Greg Lloyd | <6 Months |  | Planning stage | Due mid November 2079 |
| to be confirmed |  | to be confirmed | Frequent Callers & CHIST | Phase 2 WAST: Nursing/care homes to avoid unnecessary 999 calls & admission to hospital. Building on the pilot in Cardiff and Vale UHB; expanding from 8 to 11 care homes. Further development of the Care Home Integrated Support Team (CHIST). linked to Transformational Funding. Linked work to supoprt care homes to reduce the calls make to WAST and the number of residents who are admitted to the Emergency Department | CVUHB | Robin Petterson, Lynne Topham |  |  | Planning / local HB implementation | Due mid November 2059 |
| to be confirmed |  | to be confirmed | Direct Access Pathway | Develop and implement additional ‘direct-access’ care pathways via WAST: • Ambulatory Emergency Care- further develop pathway linked t o ambulatory transformation • Cardiology care (for certain conditions) | CVUHB | Mark Cadman |  |  | Planning stage | Due mid November 2060 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Falls Response Team | WAST/CRT Falls Response Team Operating Mon-Fri, 08:30-16:30, patients referred via 999 following a fall to receive same day urgent home based assessment by paramedic and CRT therapist. To provide confirmation of physical injury and advice/signposting to other community based services as appropriate | CVUHB | Sue Morgan |  |  | Pilot | Due mid November 2061 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Code Stroke | Continue to review Code Stroke processes to identify opportunities to improve performance including working with WAST on refining pre-hospital pathways to reduce door to needle time | CVUHB | Greg Lloyd, Geraldine Johnstone |  |  | Continuous review | Due mid November 2062 |
| to be confirmed |  | to be confirmed | Focus on Amber/ Green Calls | Analysis and understanding of Amber/Green performance to support improvement Pilot Hospital Avoidance Vehicle | CVUHB | Lee Davies |  |  | Pilot | Due mid November 2063 |
| to be confirmed |  | to be confirmed | Potential roll out of 111 | Implementation of the national 111 programme in the C&V area - this is subject to nationally agreed timescales and will be updated once confirmed dates are known. | CVUHB | Chris Powell |  |  | Planning stage | Due mid November 2064 |
| to be confirmed |  | to be confirmed | APP Trial | Introduction of Advanced Paramedic Practitioners into SE | CVUHB | Mike Jenkins |  |  | Planning stage | Due mid November 2065 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service reconfiguration: Vascular (arterial surgery) | Centralisation of arterial vascular surgery in South East Wales | CVUHB | Marie Davies |  |  | Planning stage | Due mid November 2066 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Service reconfiguration: Major Trauma | Live major trauma network by October 2019 and functioning major trauma centre at UHW and designated trauma units by April 2020. | CVUHB | Jonathan Watts |  |  | Planning stage | Due mid November 2067 |
| to be confirmed |  | to be confirmed | Service reconfiguration: Relocation of Rockwood Hospital to UHL | Reprovision of Specialist Neuro and Spinal Rehabilitation Services and Clinical Gerontology Services | CVUHB | Deborah Kingsbury |  |  | Planning stage | Due mid November 2068 |
| to be confirmed |  | to be confirmed | Service reconfiguration: Hyper Acute Stroke Unit | Work with regional partners on the establishment of HASU | CVUHB | Deborah Kingsbury |  |  | Planning stage | Due mid November 2069 |
| to be confirmed | Step 5 - Take me to Hospital | to be confirmed | Acute Coronary Syndrome Pathway Development | Redesign Acute Coronary Syndrome service to meet the NICE guidelines for the ACS pathway for Heart Disease. The ACS pathways pilot has seen a reduction in referral to transfer times down to 2 days in 2017. Further evaluation will take place ahead of potential roll out in 2018. Dedicated transport piloted as part of pathway. | CVUHB | Paula Goode | In Place |  | Transport pilot 3 months extended through non recurrent funding. Business case being prepared to EASC for addtiional fudnign to continue on a permanent basis | Due mid November 2070 |
| to be confirmed |  | to be confirmed | Enhance access and utilisation of Alternative Care Destinations / Pathways (other than ED) | Increase the utilisation of ambulance patients accessing care at their local Minor Injury unit or alternative care pathway. Action (i) Engage with Heath Board to review admission criteria for Cardigan MIU Action (ii) Engage with Health Board to review admission criteria in Llandovery MIU Action (iii) Review utilisation rates and put into place mechanisms to ensure the clinically appropriate patients are directed to the most appropriate unit. Action (iv) Implement a Mental Health Pathway (aligned to pathways developed in other Health Boards). | HDUHB | Rob Jeffery |  |  | Action (i) & Action (ii) Ongoing engagement with clinical leads | Due mid November 2080 |
| to be confirmed |  | to be confirmed | Enhance the provision of Advanced Paramedic Practitioners across HDda | Fully embed the Advanced Paramedic Practitioner rotational model across HDda. Actions to include: Action (i) Recruit and fully embed the 4 x additional APPs across the three rotational pillars (Primary care / WAST community response and CCC) following Winter investment monies Action (ii) Support the Trust wide initiative to expedite a national APP model (subject to business case approval) | HDUHB | Rob Jeffery |  |  | Action (i) Funding approved for additional APP posts, recruitment ongoing Action (ii) Business Case in development / approval stages | Due mid November 2081 |
| to be confirmed |  | to be confirmed | Improve service for non injury / low risk fallers across Hywel Dda | Preliminary discussions underway to support various County led bids for funding to improve response to elderly frail fallers Action (i) IAA bid for 'pick me up service' for Llanelli (bid to be submitted) Carmarthenshire Action (ii) Referral pathway via ART under discussion across Carmarthenshire Action (iii)Potential referral via Social Services pathway (bid to be submitted) by Ceredigion Action (iv) Preliminary discussions underway with MWWFRS regarding UFRs also attending non injured fallers for 'pick me up' service. Action (v) Explore the feasibility of introducing a Falls Response Service. | HDUHB | Rob Jeffery |  |  | Planning stages | Due mid November 2082 |
| to be confirmed |  | to be confirmed | Reduce 999 demand from Nursing / Residential Homes across Hywel Dda | Continue to engage and work collaboratively with Nursing / Residential Home providers to reduce 999 activity. Action to include: Action (i) Fully roll out 'IStumble' falls assessment tool across all Residential & Nursing homes in HDda to improve the management of non-injury falls patents to avoid unnecessary ambulance attendance and onward conveyance to ED. Action (ii) Support delivery of lifting aids to all CSSIW registered Nursing & Residential Homes across HD Action (iii) Proactively review and monitor activity data to identify opportunities to better manage demand through direct engagement and education with Nursing / Care Home providers | HDUHB | Rob Jeffery |  |  | Action (i) Continued roll out Action (ii) Ongoing engagement with key stakeholders | Due mid November 2083 |
| to be confirmed |  | to be confirmed | Joint Conveyance reduction programme with HDda | A joint group has been established to identify joint opportunities to reduce the number of patients conveyed to hospital. Actions to include: Action (i) Fully establish conveyance reduction working group Action (ii) Undertake a systematic review of WAST & Health Board clinical audit data to identify patient case mix and improvement opportunities Action (ii) Develop a robust joint conveyance reduction action plan | HDUHB | Rob Jeffery |  |  | Action (i) Group being formalised Action (ii) Initial work underway Action (iii) Yet to be developed | Due mid November 2084 |
| to be confirmed |  | to be confirmed | Transforming Clinical Services | The TCS Programme has been established to transform the delivery of health care for patients in Hywel Dda. The scope of the project includes the re-design of all Planned, Urgent & Emergency and Out of Hospital care. A new clinical model is being developed and capital investment in new health infrastructure is required. Actions include: Support key TCS Programme Groups including (i) Regional Clinical Strategy Group; (ii) WAST Partnership Model; and (iii) Explore options to undertake bespoke modelling to understand operational, resource and capacity impacts of the future clinical model | HDUHB | Rob Jeffery |  |  | Long Term Planning: Programme is in Phase 2: Design. Timescales determined by the TCS Programme Plan | Due mid November 2085 |
| to be confirmed |  | to be confirmed | Support the Mid & West Regional Stroke Model work stream | Continue to engage and support the development of a regional Stroke model for Mid & West Wales. Actions to include: (i) Continue to attend and support the Stroke Project Group, (ii) Support the development of the regional model and undertake bespoke ambulance modelling to identify the ambulance specific impacts. (iii) Explore WASTs role to support the preferred clinical model | HDUHB | Rob Jeffery |  |  | Planning stage | Due mid November 2086 |
| to be confirmed |  | to be confirmed | Pro-active monitoring and management of service change proposals. | WAST will continue to engage proactively with Health Boards to identify and jointly plan for all local service change . Actions to include: (i) WAST & the three M&W regional Health Boards (ABMU, HDda & Powys) to regularly meet and review service change with planning and operational leads via the Joint Mid & West Wales Planning Forum; | HDUHB | Rob Jeffery |  |  | Both groups have been established | Due mid November 2087 |
| to be confirmed |  | to be confirmed | Transforming Clinical Services - Hywel Dda UHB | The TCS Programme has been established to transform the delivery of health care for patients in Hywel Dda. The scope of the project includes the re-design of all Planned, Urgent & Emergency and Out of Hospital care. A new clinical model is being developed and capital investment in new health infrastructure is required. Actions include: Support key TCS Programme Groups including (i) Regional Clinical Strategy Group; and (ii) WAST Partnership Model (iii) Explore options to undertake bespoke modelling to understand operational, resource and capacity impacts of the future clinical model | HDUHB | Rob Jeffery |  |  | Long Term Planning: Programme is in Phase 2: Design. Timescales determined by the TCS Programme Plan | Due mid November 2099 |
| to be confirmed |  | to be confirmed |  |  | HDUHB |  |  |  |  |  |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Enhanced services to manage Falls Patients | Continue to develop and enhance care for the management of non-injury and low-acuity falls patients. Actions to include: (i) Fully roll out 'IStumble' falls assessment toolkits across all Residential & Nursing homes across Powys to improve the management of non-injury falls patents. (i) Establish a Falls Pathway for Paramedics to access and refer clinically appropriate falls patients to the Powys Urgent Response Service at Home (PURSH) | PTHB | Heather Ransom |  |  | Action (i) Continued roll out Action (ii) Initial Planning Stage | Due mid November 2088 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Increase the availability and access to Alternative Care Pathways | Explore and scope with the PTHB the following additional Care Pathways: Action (i) Explore and scope the development of a Respiratory Pathway (aligned to the ongoing review of Respiratory care across PTHB) Action (ii) Develop a Single Point of Access Pathway | PTHB | Heather Ransom |  |  | Action (i) Pre-planning stage Action (ii) P{re-planning stage | Due mid November 2089 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Enhance the provision of Advanced Paramedic Practitioners across Powys | Fully embed the Advanced Paramedic Practitioner rotational model across Powys THB Actions to include: Action (i) Engage with PTHB and support the Trust wide initiative to expedite a national APP model (subject to business case approval). | PTHB | Heather Ransom |  |  | Action (i) and (ii) Planning Stage - funding / resource to be discussed and agreed. | Due mid November 2090 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | SaTH Future Fit Programme | Cross border service change: The Future Fit Programme is a regional transformation programme reviewing hospital services across Shropshire, Telford & Wrekin. Two proposed options the reconfigure all planned and Urgent & Emergency Care, identifying the two following options: Option 1: The Royal Shrewsbury Hospital becomes the Emergency Care site and the Princess Royal Hospital becomes the Planned Care site. Option 2: The Princess Royal Hospital becomes an Emergency Care site and the Royal Shrewsbury Hospital becomes a Planned Care site. Under either option, both hospitals would have an Urgent Care Centre that is open 24 hours a day, seven days a week. | PTHB | Heather Ransom |  |  | Planning Stage - pre business case | Due mid November 2091 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Hereford & Worcester Regional Stroke Model | Cross border service change: Proposals have been put forward to re reconfigure stroke services across Hereford & Worcester. The two core options being considered are: Option 1: HASU at Hereford and ASU at Worcester with a Triage, Thrombolise and Transfer service Option 2: HASU at Worcester and ASU at Hereford with a Triage, Thrombolise and Transfer service | PTHB | Heather Ransom |  |  | Planning Stage - pre business case | Due mid November 2092 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Support the Mid & West Regional Stroke Model work stream | Continue to engage and support the development of a regional Stroke model for Mid & West Wales. Actions to include: (i) Continue to attend and support the Stroke Project Group, (ii) Support the development of the regional model and undertake bespoke ambulance modelling to identify the ambulance specific impacts. (iii) Explore WASTs role to support the preferred clinical model | PTHB | Heather Ransom |  |  | Planning stage | Due mid November 2093 |
| to be confirmed | Step 3 - Come to see me | to be confirmed | Other regional service transformation | There are a range of other regional service transformational agendas, including: Action (i) Mid & West Region Stroke reconfiguration proposals Action (ii) Mid Wales Joint Committee for Health & Social Care Action (iii) WAST & the three M&W regional Health Boards (ABMU, HDda & Powys) to regularly meet and review service change with planning and operational leads via the Joint Mid & West Wales Planning Forum; | PTHB | Heather Ransom |  |  | Action (i) Planning Stage - pre business case Action (ii) Planning Stage | Due mid November 2094 |
| to be confirmed |  | to be confirmed | Hereford & Worcester Regional Stroke Model - Powys tHB | Cross border service change: Proposals have been put forward to re reconfigure stroke services across Hereford & Worcester. The two core options being considered are: Option 1: HASU at Hereford and ASU at Worcester with a Triage, Thrombolise and Transfer service Option 2: HASU at Worcester and ASU at Hereford with a Triage, Thrombolise and Transfer service | PTHB | Heather Ransom |  |  | Planning Stage - pre business case | Due mid November 2095 |
| to be confirmed |  | to be confirmed | Other regional service transformation - Powys tHB | There are a range of other regional service transformational agendas, including: Action (i) Mid & West Region Stroke reconfiguration proposals Action (ii) Mid Wales Joint Committee for Health & Social Care | PTHB | Heather Ransom |  |  | Action (i) Planning Stage - pre business case Action (ii) Planning Stage | Due mid November 2096 |
| to be confirmed |  | to be confirmed | SaTH Future Fit Programme - Powys tHB | Cross border service change: The Future Fit Programme is a regional transformation programme reviewing hospital services across Shropshire, Telford & Wrekin. Two proposed options the reconfigure all planned and Urgent & Emergency Care, identifying the two following options: Option 1: The Royal Shrewsbury Hospital becomes the Emergency Care site and the Princess Royal Hospital becomes the Planned Care site. Option 2: The Princess Royal Hospital becomes an Emergency Care site and the Royal Shrewsbury Hospital becomes a Planned Care site. Under either option, both hospitals would have an Urgent Care Centre that is open 24 hours a day, seven days a week. | PTHB | Heather Ransom |  |  | Planning Stage - pre business case | Due mid November 2097 |
| to be confirmed |  | to be confirmed | Enhanced management of Frequent Service users | (i) Continue the Multi-disciplinary team approach with Health Board clinical / service leads to identify, review and manage frequent service users. (ii) Regular review activity data to identify high volume service users and engage with service leads to understand the reasons and put into place mitigating actions to reduce demand (for example continue to work closely with Parc Prison, Bridgend to reduce 999 generated attendances). | SBUHB | Jeff Morris | <12 Months | Active Development | Work streams already established | Due mid November 2020 |
| to be confirmed |  | to be confirmed | Enhanced services to manage Falls Patients | Continue to develop and enhance care for the management of non-injury and low-acuity falls patients. Actions to include: (i) Fully roll out 'IStumble' and 'I Fell Down' falls assessment toolkits across all Residential & Nursing homes in ABMU to improve the management of non-injury falls patents to avoid unnecessary ambulance attendance and onward conveyance to ED. (ii) Seek funding to establish a dedicated Joint Falls Response vehicle in collaboration with Health Board clinical leads to manage low acuity falls patients in the community (Risk - availability of funding). (iii) Work closely with Health Board to identify and trial any new initiatives to improve the care and management of non-injury / low acuity falls patients. | SBUHB | Jeff Morris | <12 Months | Planned Roll Out | Action (i) Continued roll out Action (ii) Planning Stage Action (iii) Continued dialogue with Health Board | Due mid November 2021 |
| to be confirmed |  | to be confirmed | Enhance the provision of Advanced Paramedic Practitioners across ABMU | Fully embed the Advanced Paramedic Practitioner rotational model across ABMU. Actions to include: (i) Recruit and fully embed the new 6 x APPs across the three rotational pillars (Primary care / WAST community response and CCC) following Winter investment monies (ii) Support the Trust wide initiative to expedite a national APP model (subject to business case approval) | SBUHB | Jeff Morris | <12 Months | Active Development | Action (i) Funding approved for additional APP posts, recruitment ongoing Action (ii) Business Case in development / approval stages | Due mid November 2022 |
| to be confirmed |  | to be confirmed | Management of Hospital Handover Delays | Joint working between WAST & Health Board to proactively manage and minimise hospital handover delays. Actions to include: Action (i) Implement robust operational arrangements to proactively manage periods of peak hospital activity to improve patient flow and minimise delayed ambulance handover Action (ii) Put in place clear action plans to manage handover delays (including Joint Winter Plans). | SBUHB | Jeff Morris | <12 Months | Testing in Practice | Actions being put into place and tested this Winter period | Due mid November 2023 |
| to be confirmed |  | to be confirmed | Support the Mid & West Regional Stroke Model work stream | Continue to engage and support the development of a regional Stroke model for Mid & West Wales. Actions to include: (i) Continue to attend and support the Stroke Project Group, (ii) Support the development of the regional model and undertake bespoke ambulance modelling to identify the ambulance specific impacts. (iii) Explore WASTs role to support the preferred clinical model | SBUHB |  | <12 Months | Early Exploration | Planning stage | Due mid November 2024 |
| to be confirmed |  | to be confirmed | Bridgend Locality Boundary Proposals | Continue to engage and support the future planning and manage the operational impacts of the Bridgend Locality boundary change to Cwm Taf UHB. | SBUHB |  | <12 Months | Planned Roll Out | Due to go live April 2019/20 | Due mid November 2025 |
| to be confirmed |  | to be confirmed | Pro-active monitoring and management of service change proposals. | WAST will continue to engage proactively with Health Boards to identify and jointly plan for all local service change . Actions to include: (i) WAST & the three M&W regional Health Boards (ABMU, HDda & Powys) to regularly meet and review service change with planning and operational leads via the Joint Mid & West Wales Planning Forum; and (ii) WAST to support the ABMU Joint Evaluation Group (inc Health Board & Local Authority leads) | SBUHB |  | <12 Months | Active Development | Both groups have been established | Due mid November 2026 |
| to be confirmed |  | to be confirmed | Support the Mid & West Regional Stroke Model work stream - ABM UHB | Continue to engage and support the development of a regional Stroke model for Mid & West Wales. Actions to include: (i) Continue to attend and support the Stroke Project Group, (ii) Support the development of the regional model and undertake bespoke ambulance modelling to identify the ambulance specific impacts. (iii) Explore WASTs role to support the preferred clinical model | SBUHB | Jeff Morris |  |  | Planning stage | Due mid November 2098 |