EASC ACTION PLAN

| Issue | Action | Lead | Start Date | End Date | Current Position |
| --- | --- | --- | --- | --- | --- |
| Enhancing Ambulance Capacity | Additional Emergency medical technicians recruitment | WAST | Now | March 2022 | First cohort training starts w/c 8th November |
|  | Relief gap recruitment | WAST | Apr 21 | March 2022 | On track to deliver year 2 of the D&C |
|  | Agency staffing | WAST | Now | March 2022 | Agency staff currently being sourced as part of the cohorting plan |
|  | Increase payment to double time Increased opportunities | WAST | Now | March 2022 | Uptake likely low |
|  | Military support | WAST | Now | March 2022 | Ongoing work/discussions around timelines and scale |
|  | Fire service support | WAST | Now | Ongoing | Progressing with MAWWFRS |
|  | Reduce post production lost hours | WAST | Sep 21 | Ongoing | Internal WAST programme with Trade Union colleagues “Leading Service Change Together” |
|  | Roster review | WAST | Sept 21 | 22/2023 | Rosters currently in development by WAST |
| Winter Forecast | Winter forecast - using optima predict software to understand forecast demand, performance and escalation levels | WAST | Sept 21 | Oct 21 | Forecast available and in use for planning mitigations |
| System Escalation | Emergency Department Demand Management Plans | NCCU | In development |  | Stakeholder engagement underway |
|  | System wide escalation | NCCU | In development |  | Stakeholder engagement underway. Presentation provided to EASC |
|  | WAST Clinical Safety Plan | WAST | Live | - | Ongoing monitoring. Links to system wide escalation development |
| Cohorting | Cohorting - Utilising ambulance service staff to hold multiple patients, allowing ambulances to return to community response | Ysbyty Glan Clwyd, BCUHB | TBC |  | Further discussions to be held between BCU and CASC |
|  |  | Grange University Hospital, ABUHB | End of Nov 2021 indicative |  | Procurement of staff and vehicles underway |
|  |  | Morriston, SBUHB | Indicative 15th November |  | Aiming for a Go live of the 15th November subject to staff availability |
|  |  | System Deployable Assets | As per above. |  | Temporary assets have been sourced and procurement is progressing. Cost benefit analysis of capital purchase underway with ongoing discussions with supplier around deliverability |
| Handover Delays | Reduce to sustainable levels | ABUHB | Core component of system wide escalation plan currently being shared with stakeholders |  |  |
|  |  | C&VUHB |  |  |  |
|  |  | CTMUHB |  |  |  |
|  |  | HDUHB |  |  |  |
|  |  | SBUHB |  |  |  |
|  |  | BCUHB |  |  |  |
| Demand & Capacity Review Update | Demand & Capacity Review Update modelling to reflect system changes since 2018 | WAST/EASC | 19-Aug-21 | Complete | Findings being presented to EASC 9th November |
| Remote Clinical Support | Emergency Communications Nurse System (ECNS) - Implementation | WAST | 01-Sept –21 | 31–Mar 22 | On track |
|  | PTAS (Physician Triage and Assessment and Screening) provides direct access to the WAST incident stack to manage appropriate patients | ABUHB | TBC | Mar 22 | Aneurin Bevan are awaiting sign off internally of the MOU, DPIA and JCA. WAST is awaiting an updated list of users from ABUHB and they are chasing this internally |
|  |  | BCUHB | Live | Mar 22 | Betsi Cadwaladr's Acute Care Director has contacted WAST to progress with PTaS and the SOP, MOU, DPIA and JCA (Joint Controller Agreement) have been shared. WAST is currently liaising with the Training Team and BCUHB to agree a suitable training date |
|  |  | C&VUHB | TBC | Mar 22 | Cardiff and Vale's PRU team (Syed) are supportive of PTaS and the documents were resent to them last week and we requested a list of names for training but so far no further response. We expect the PTaS to offer See and Treat benefits to the PRU team, rather than Hear and Treat |
|  |  | CTMUHB | TBC | Mar 22 | Cwm Taf are producing a bid for funding for PTaS support. WAST has contacted CTM for an update on this |
|  |  | HDUHB | Live | Mar 22 | Hywel Dda went live with PTaS on 09 September and a good news story has been published internally to WAST on Siren. There are two pending actions with HDUHB. Firstly the JCA needs to be approved; this is with Hywel Dda's IG team for review. Secondly, the main user of PTaS is experiencing ICT issues which remain unresolved. As an interim measure, the user will work from CCC until the ICT issue is resolved. WAST are chasing ICT on this |
|  |  | SBUHB | TBC | Mar 22 | Swansea Bay are reviewing the MOU and DPIA with a view to holding one version of these for all their services. WAST is chasing a response on this |
|  |  | PTHB | TBC | Mar 22 | Powys have contacted WAST to request an introductory meeting to PTaS. This is being scheduled |
|  |  | Health Boards | Now | 3rd Nov 2021 | National event held. Follow up letter from CASC to all HB asking to confirm implementation plans |
|  | Mental Health Support to CSD | WAST | Now | Ongoing | Recruitment underway |
| Same day emergency Care | Increase opportunities for direct access to same day emergency care | NCCU | Now | Ongoing | National referral policy in development, stakeholder engagement taking place |
| Utilisation | Utilisation measure development | WAST | Now | Ongoing | Recently develop utilisation measure was recently presented at EASC Management Group and a number of stakeholder groups. Work is underway to embed into day to day system planning and escalation |