## Slide 1
Emergency Ambulance Services Committee
IMTP Tracker
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK

## Slide 2
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
Introduction
  The 2023-26 EASC IMTP set out a number of performance improvement ambitions and performance enablers for Emergency Ambulance Services
  Whilst the EASC IMTP has not yet been formally approved by the Minister for Health and Social Services, the Committee remain committed to the delivery of these improvements.
  This slide deck sets out the progress to date against each of the commitments.
  The Committee agreed to review these commitments during the year in light of system progress, this presentation suggest a number of areas for review during Q1 as a result of early delivery of ambitions.
EASC IMTP 23/26 Tracker

## Slide 3
Summary – Performance Improvement
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker

## Slide 4
“Cant Sends” - Reduced by 75-95% over 2023/24
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
*CSP Can’t sends only
Chart: 
| April | May | June | July | Aug | Sep
2022 | 670 | 161 | 611 | 683 | 358 | 348
2023 | 46 | 61 | 57 | 154 | 208 | 628

## Slide 5
Red Performance – 60% by end of Q1
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Requirement to achieve 65% by end of Q2
Chart: 
| April | May | June | July | August | September
 | 0.53 | 0.54 | 0.55 | 0.526 | 0.505 | 0.487

## Slide 6
Longest Red – 95th Percentile 30 min by end of Q1
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Chart: 
Apr | 0.015938
May | 0.014965
Jun | 0.015405
Jul | 0.017176
Aug | 0.016377
Sep | 0.016887
In July 2023 EASC agreed to update their Q2 ambition– to be less than 18 min
Sustained incremental improvement in Q3/4

## Slide 7
Amber Median - < 90 min by end of Q1
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Requirement to achieve 45 min by end of Q2
Less than 30 min required by end of 2023/24
Chart: 
Apr | 0.04412
May | 0.040394
Jun | 0.042431
Jul | 0.049421
Aug | 0.055984
Sep | 0.058264

## Slide 8
Longest Amber – 95th Percentile 8 hours by end Q1
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
At the July 2023 meeting EASC agreed to revise the improvement ambitions to Quarter 2 less than 4.5 hours and Quarter 3 less than 3.5 hours.
Sustained incremental improvement by in Q4
Chart: 
Apr | 0.2323
May | 0.20976
Jun | 0.20294
Jul | 0.25315
Aug | 0.30861
Sep | 0.35824

## Slide 9
Handover Hours – 15,000 Lost per month by end of Q2
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Requirement to achieve 12,000 hours per month by end of Q3
Sustained and incremental improvement in Q4
Chart: 
Apr | 22990.3639
May | 20440.6122
Jun | 18548
Jul | 19119
Aug | 19060
Sep | 19610

## Slide 10
Longest Handover – No Handover >4 Hours in 2023/24
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Requirement for all sites to eradicate waits over 1 hour by end of April 2025
Chart: 
Apr | 2030
May | 1625
Jun | 1440
Jul | 1452
Aug | 1475
Sep | 1528

## Slide 11
Longest Handover – No Handover >1 Hours by April 2025
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Requirement for all sites to eradicate waits over 1 hour by end of April 2025
WG requested HB forecast to end of March 2024.
Chart: 
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Trajectory | 6519 | 5687 | 4975 | 5039 | 4665 | 4476 | 4505 | 4380 | 4560 | 4744 | 4156 | 4317
Actual | 6116 | 5808 | 5308 | 5724 | 5674 | 5708

## Slide 12
Summary – Performance Enablers – WAST
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker

## Slide 13
Summary – Performance Enablers – Six Goals
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker

## Slide 14
Summary – Performance Enablers – Targeted
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker