Six Goals for Urgent & Emergency Care: Highlight Report

Goal 4: Rapid response in a physical or mental health crisis

| Author: Sian Ashford |  |  |  |  | Previous RAG Rating: | Overall RAG Rating: |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Submission Date: 14/06/2023 |  |  | Period covered: May 2023 |  |  |  |  |
| Goal 4: Key Deliverables 23/24 |  |  |  |  |  |  |  |
| Workstreams | Current RAG | Workstream Progress | Key Activities & Achievements | Priorities for Next Period |  |  | Performance Trend |
| Optimising Response |  | Connected Care Cymru scoping work Full roll out of CHARU commenced All Wales roster reviews completed | Future D&C model Commissioned Review of Remote Clinical Support underway Red Improvement plan progress | Continue to deliver priorities in EASC action plan and ICAPs |  |  |  |
| Optimising Conveyance |  | Multiple ambulance Flow/Navigation models now in operation across Wales Continued us of mental health transport service provided by St John Plans for APP perfect days underway | Incident and Conveyance Review linked to Welsh Deprivation index UCS, T&C Demand and Capacity models underway | Continue to deliver priorities in EASC action plan and ICAPs |  |  |  |
| Data gathering / digital improvements |  | Getting it Right First Time (GIRFT) to identify unwarranted clinical variation using The Summary Emergency department Indicator Table (SEDIT). Exploratory work underway to understand what data is available at each health board. Information reporting group meeting in 17 May chaired by Simon Jones | GIRFT – Deep dive into what data is available across all UHB’s in development, (to be completed by end of June). AA draft ToR and project plan will be taken to next Information Reporting Group in June. E-Triage- Devices ready for deployment | GIRFT- Continue gathering data, meeting in June to agree draft ToR and project plan. E-Triage – understand where ABUHB and Cardiff, gather learning and review impact |  |  |  |
| ED Improvement |  | Previous ED improvement initiatives being reviewed and an updated plan in development with newly appointed Clinical Lead. Endorsement of Emergency Medicine Quality Statement development | EDQDF has identified some good learning opportunities, we will use these opportunities and develop revised priorities for ED improvement Task and Finish Group stood up, communication and engagement plan created | Meeting with local ED leaders, gathering confidence and building network. Explore opportunities for improvement by visiting other areas. Exploring continuous flow in Southmead Stakeholder engagement Goal 4 Board |  |  |  |
| Escalation |  | National Escalation Framework signed off by senior leaders and ready for team engagement and deployment. | National system wide escalation framework created. | Review resources and scope implementation plans |  |  |  |
| Additional Workstreams – Not listed under latest plans on a page |  |  |  |  |  |  |  |
| Workstreams | Current RAG |  | Key Activities & Achievements | Priorities for Next Period |  |  | Performance Trend |
| Integrated Commissioning Action Plans (ICAP’s) |  | ICAP process established, relationships built, structure in place. Versions 1 of ICAP created, discussed at local levels and initiatives input by UHB’s and WAST to create version 2 and 3. | The structure of ICAPs is now established resulting in refined membership and version 4 of ICAPS updated. | Production of version 5 of ICAPS |  |  |  |
| Review of the remote clinical assessment of 999 calls |  | Terms of reference set, meetings with stakeholders arranged | Data gathering exercises underway | Completion of report by end of June 2023 |  |  |  |

| Performance Measures & Metrics (In place, or to be defined) |  |  |  | Additional Comments |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Goal 4 4 dashboard (April 2023- May not yet available) |  |  |  | Significant improvement in ambulance handover delays noted in CVUHB, CTMUHB and ABUHB. There is ongoing work to support measurement of 111 press 2. |  |  |  |
| Risks & Issues |  |  |  | Business Case Management |  |  |  |
| Description | Outcome / Impact | Escalation / Support | Flag to Board (Y/N) | Lead(s) | Purpose/Aim | Date Submitted | Decision |
| Actions in ICAPS are dependent on funding and resource availability | If WAST / UHBs do not have the resource to deliver the initiative this will impact upon flow, patient experience, clinical outcomes and value. | Aligns to IMTP ambitions, raised through management group and joint committee |  | SA | To support funding of resource requirements for the delivery of Goal 4 (in progress) |  |  |
| Lack of resources to deliver Goal 4- ED improvements / Escalation Framework | Limited improvements impacting clinical outcomes, experience and value | Business case in development to request funding for resource support |  |  |  |  |  |
| Unwarranted variation around Health Board executive ownership and use of ED triage and assessment data to enable service improvement | Variation in time to triage across Wales which could mean variable patient experience and outcomes by site / UHB | OD piece around GIRFT may mitigate this eventually but opportunities may be being missed due to a lack of health board ownership |  |  |  |  |  |