HIGHLIGHT REPORT

| EASC MANAGEMENT GROUP |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Author: Gwenan Roberts |  |  |  |  |  |  |  |  | Report no: 1 |  |  |
| Date: 21/02/2020 |  |  | Period covered: Jan-Feb |  |  |  |  |  | File reference: |  |  |
| Decisions required from the EASC Committee: |  |  |  |  |  |  |  |  |  |  |  |
| - Whether this highlight report provides enough information and seeking approval for its use |  |  |  |  |  |  |  |  |  |  |  |
| Key Issues / Red Flags: |  |  |  |  |  |  |  |  |  |  |  |
| - All Health Boards represented at the meeting either Director of Assistant Director level |  |  |  |  |  |  |  |  |  |  |  |
| - New approach to AQIs using PowerBI as a powerful tool to provide more local information – which is raising awareness and more specific questions including increase in ‘user left calls’ and the reduction in ‘ideal’ response percentages; more user friendly version being developed; WAST developing AQI dashboard |  |  |  |  |  |  |  |  |  |  |  |
| - WAST Major Trauma Readiness assessment – added as a standing agenda item |  |  |  |  |  |  |  |  |  |  |  |
| - Implementation plan for Demand and Capacity Review - standing agenda item; agreed to receive key metrics to provide a baseline position; detailed financial plan to be developed; potential utilisation of the additional staff (136WTE) and key risks to be received at the next meeting. |  |  |  |  |  |  |  |  |  |  |  |
| - Safe cohorting of patients - actions appear to be having an impact |  |  |  |  |  |  |  |  |  |  |  |
| - WAST IMTP delivery plan will distinguish between commissioning and delivery responsibilities |  |  |  |  |  |  |  |  |  |  |  |
| - Loss of ‘Launchpad’ discussed and timescale for restoration of service requested from WAST |  |  |  |  |  |  |  |  |  |  |  |
| - RED Calls and clinical outcome information to be provided |  |  |  |  |  |  |  |  |  |  |  |
| Update/ Progress against Plan: |  |  |  |  |  |  |  |  |  |  |  |
| - Have been concentrating on EASC IMTP and Commissioning Intentions now implementation |  |  |  |  |  |  |  |  |  |  |  |
| - Integrated performance dashboard being developed and next steps planned |  |  |  |  |  |  |  |  |  |  |  |
| - Escalation template developed to assist 11am call – still teething problems but progress made |  |  |  |  |  |  |  |  |  |  |  |
| - 1% A Healthier Wales in year funding utilisation to be clarified before year end |  |  |  |  |  |  |  |  |  |  |  |
| - EASC Management Group Annual Report drafted – will be submitted before end of June 2020 |  |  |  |  |  |  |  |  |  |  |  |
| Work completed against plans |  |  |  |  |  |  |  |  |  |  |  |
| - IMTP Finance schedules updated |  |  |  |  |  | - EASC Website updated for recent changes |  |  |  |  |  |
| Critical Tasks for Coming Period: |  |  |  |  |  |  |  |  |  |  |  |
| Task |  |  |  |  | Owner |  | Due Date |  | % Complete | Forecast Date |  |
| Ministerial Ambulance Availability Taskforce |  |  |  |  | SMH |  | Summer 2020 |  | 5% | Summer 2020 |  |
| EASC IMTP delivery plan |  |  |  |  | JR |  | 23 April |  | 40% | 23 April |  |
| WAST IMTP delivery plan |  |  |  |  | RM |  | 23 April |  | 40% | 23 April |  |
| Demand and Capacity Implementation |  |  |  |  | WAST |  | March 2021 |  | 15% | March 2021 |  |
| Presentation on Optima Predict |  |  |  |  | WAST |  | TBC |  | TBC | TBC |  |
| Serious Adverse Incident analysis |  |  |  |  | WAST |  | Next meeting |  | TBC | 23 April |  |
| Evaluation of Winter |  |  |  |  | WAST |  | Spring 2020 |  | TBC | ?23 April |  |
| Update the monitoring report to finance report |  |  |  |  | SD |  | May 2020 |  | TBC | May 2020 |  |
| Risk Update: |  |  |  |  |  |  |  |  |  |  |  |
| REF | Risk | Owner |  | Due Date |  |  |  | Countermeasure |  |  | Probability/Impact |
|  | Training plan for D&C Review | CV |  | 23 April 2020 |  |  |  | Work commenced |  |  | High |
|  | Ongoing staffing arrangements for safe patient cohorting beyond 31 March 2020 | COOs in HBs |  | End of March |  |  |  |  |  |  | High |